## Total 2025
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| COL | PAN | AKR | INS | LULU | SWA | FRO | PAN2 | STU | STU2 | FAL | TRI | LIN | KAR | UGG | FAL2 | TES | HOK | LUSH | DRE | PAN3 | MIL
contract amount | 46000 | 59771.61 | 15496 | 60000 | 38063.1 | 145000 | 23863.6219 | 75326.52 | 29275 | 28721.0038 | 32248 | 49600 | 96000 | 110000 | 217968.89 | 140000 | 23000 | 436134.78 | 108322.61 | 118500 | 60866.14 | 658853.39 |  | 1914157.2757
additional works | 0 | 7538.2 | 0 | 0 | 0 | 10574.43 | 5500 | 9698.1 | 0 | 15387.47 | 12035.28 | 1858.66 | 13116.87 | 22635 | 10000 | 2161.77 | 0 | 82558.89 | 5679.47 | 6000 | 5598.03 | 24164.34 |  | 210342.17
total income | 46000 | 67309.81 | 15496 | 60000 | 38063.1 | 155574.43 | 29363.6219 | 85024.62 | 29275 | 44108.4738 | 44283.28 | 51458.66 | 109116.87 | 132635 | 227968.89 | 142161.77 | 23000 | 518693.67 | 114002.08 | 124500 | 66464.17 | 683017.73 |  | 2124499.4457
project manager | Kaspars | Kaspars | Alens | Alens | Alens, Māris | Alens | Alens | Kristaps | Alens | Kaspars | Kaspars | Alens | Kaspars | Alens | Alens, Māris | Kaspars | Kaspars | Māris, Valters | Alens | Kaspars | Kristaps | Alens
planned hours | 606 | 519 | 0 | 201 | 0 | 1036.92 | 188 | 1195 | 349.74 | 457.04 | 593.75 | 843 | 1225 | 1389.6 | 1522 | 1596 | 304 | 2762.4483 | 740 | 1584.4 | 764.3 | 0
worked hours | 721.58 | 734.6 | 0 | 223.47 | 27.84 | 979.9 | 166.47 | 969.8 | 359 | 467.05 | 617.32 | 791.36 | 1150.65 | 1380.78 | 1641.27 | 1501.24 | 271 | 2551.44 | 781.36 | 1512.29 | 739.3 | 184.78
stundu bilance | -115.58 | -215.6 | 0 | -22.47 | -27.84 | 57.02 | 21.53 | 225.2 | -9.26 | -10.01 | -23.57 | 51.64 | 74.35 | 8.82 | -119.27 | 94.76 | 33 | 211.0083 | -41.36 | 72.11 | 25 | -184.78
profit % | 25.01% | 12.96% | 22.61% | 29.61% | 26.14% | 7.371% | 43% | 25.67% | 48.74% | 50.01% | 43.66% | 22.8% | 27.91% | 18.04% | 28.45% | 17.05% | 41.02% | 35.65% | 37.93% | 20.37% | 20.17% | 30.35% | 28.77%
profit EUR | 11504.1763 | 8726.002 | 3502.8944 | 17767.1342 | 9950.5572 | 11467.7182 | 12625.4974 | 21821.832 | 14268.8913 | 22060.161 | 19331.8914 | 11730.2193 | 30458.0691 | 23933.5907 | 64868.0318 | 24233.8115 | 9434.8141 | 184913.6446 | 43237.8177 | 25360.8181 | 13403.1138 | 207302.1745 |  | 584600.6862
administrative costs 7% | 3220 | 4711.6867 | 1084.72 | 4200 | 280.6452 | 10890.2101 | 2055.4535 | 5951.7234 | 2049.25 | 3087.5932 | 3099.8296 | 3602.1062 | 7638.1809 | 9284.45 | 15957.8223 | 9951.3239 | 1610 | 36308.5569 | 7980.1456 | 8715 | 4652.4919 | 47811.2411 |  | 146331.1894 | 27.52%

## Profit
Object | object total | Profit (%) | Project manager
PAN3 | 66464.17 | 20.17% | Kristaps | 13403.1138
DRE | 124500 | 20.37% | Kaspars | 25360.8181
LUSH | 114002.08 | 37.93% | Alens, Valters | 43237.8177
HOK | 518693.67 | 35.65% | Māris, Valters, Alens | 184913.6446
FAL2 | 142161.77 | 17.05% | Kaspars | 24233.8115
STU2 | 44108.4738 | 50.01% | Kaspars | 22060.161
STU | 29275 | 48.74% | Alens | 14268.8913
FAL | 44283.28 | 43.66% | Kaspars | 19331.8914
FRO | 29363.6219 | 43% | Alens | 12625.4974
TES | 23000 | 41.02% | Kaspars | 9434.8141
UGG | 227968.89 | 28.45% | Alens, Māris | 64868.0318
LIN | 109116.87 | 27.91% | Kaspars | 30458.0691
INS | 60000 | 29.61% | Alens | 17767.1342
KAR | 132635 | 18.04% | Alens | 23933.5907
PAN2 | 85024.62 | 25.67% | Kristaps | 21821.832
LULU | 38063.1 | 26.14% | Alens | 9950.5572
COL | 46000 | 25.01% | Kaspars | 11504.1763
TRI | 51458.66 | 22.8% | Alens | 11730.2193
AKR | 15496 | 22.61% | Alens | 3502.8944
PAN | 67309.81 | 12.96% | Kaspars | 8726.002
SWA | 155574.43 | 7.371% | Alens | 11467.7182
MIL | 683017.73 | 30.35% | Alens | 207302.1745

## MIL
MIL | UGG MILANO SAN BABILA, Piazza San Babila 5, 20122 Milano |  |  |  | 19/11/2025-9/03/2026 |  |  | Payment conditions, Clause 5.2.
[7 empty] | 197656.02 | 30% | upon signing the contract | 15 days
| Sales (m2): | 181.52 | 2499.3048 |  | Contract amount EUR | 658853.39 | 197656.02 | 30% | upon beginning of the construction site | 30 days
| BOH (m2): | 115.98 |  |  | Additional works, EUR | 24164.34 | 197656.02 | 30% | upon delivery of furniture/ fittings | 30 days
| TOTAL (m2) | 297.5 | 1524.954 |  | Administrative costs (7% from income) | 47811.2411 | 65885.33 | 10% | upon completion of teh work and final delivery, subject to verification and closure of the list of defects | 30 days
| Position | Planned costs | Actual costs | PROFIT | Profit | 207302.1745 | 658853.39
1 | SALARY | 7000 | 6029.0544 | 970.9456 |  | 30.35%
2 | MATERIALS |  | 6038.85 | -6038.85 |  |  |  | Contract for Works and Services in relation to the Project UGG MILANO SAN BABILA
3 | HOTEL | 6000 | 1833.2 | 4166.8 | hours costs planned | #DIV/0!
4 | GASOLINE |  |  | 0 | hours per m2 planned | 0
5 | AVIO+TRAVEL | 1000 | 193.63 | 806.37 | m2 costs planned | #DIV/0!
6 | SUB: reklāmas baneris Prima Visione | 3042 | 2969 | 73
| SUB: "SIRTEC" epoxy floor | 43510 | 43510 | 0
| SUB: CONSTRUCTION "Tarqiunio" | 149715.52 | 149715.52 | 0
7 | SUB: ELECTRICITY "Tarqiunio" | 46940 | 46940 | 0 | hours cost in fact | 32.6283
8 | SUB: DEMOLITION "Tarqiunio" | 27373.95 | 27373.95 | 0 | hours per m2 in fact | 0.62111
9 | SUB: PLUMBING"Tarqiunio" | 1809 | 1809 | 0 | m2 costs in fact | 20.2657
10 | SUB: AIR CONDITION"Tarqiunio" | 136119 | 136119 | 0
11 | Insurance, Ziedonis |  | 1593.55 | -1593.55 | hours costs, incl. travel and living | 43.5972
12 | PM travel costs | 7000 | 3779.56 | 3220.44 | living costs per person per day | 61.1067
13 | ADD 1- smoke detectors | 24164.34 |  | 24164.34
| TOTAL | 453673.81 | 427904.3144 | 25769.4956 |  | 475715.5555
33.58%
| Hours workers |  | 184.78 | -184.78
| Hours SM/PM |  |  | 0
ADD HOURS
| TOTAL | 0 | 184.78 | -184.78
Avansi | 4500
Ripo IT
Stēģi, durvis | 4500
Sirtex/Resimix | 10000
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa
Note on D14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa
Note on D15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa
Note on D16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa
Note on D17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa
Note on D18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa

## PAN3
PAN3 | Pandora SC Rocca al Mare Mall Paldiski mnt 102, 13522 Tallinn, Estonia |  |  |  | 30/09/2025-18/10/2025
| Sales (m2): | 38.7 | 1378.4401 |  | Contract amount EUR | 60866.14 | 18259.84 | avanss, 10 dienas
| BOH (m2): | 11.5 |  |  | Additional works, EUR | 5598.03 | 36519.68 | pēc pabeigšanas, 30 dienas
| TOTAL (m2) | 50.2 | 1062.662 |  | Administrative costs (7% from income) | 4652.4919 | 6086.61 | pēc garantijas perioda beigām, 30 dienas
| Position | Planned costs | Actual costs | PROFIT | Profit | 13403.1138
1 | SALARY | 16939.26 | 19274.3643 | -2335.1043 |  | 20.17%
2 | MATERIALS | 6883.41 | 8238.22 | -1354.81
3 | HOTEL | 4000 | 3537.06 | 462.94 | hours costs planned | 22.1631
4 | GASOLINE | 500 |  | 500 | hours per m2 planned | 15.2251
5 | AVIO+TRAVEL | 400 | 18.97 | 381.03 | m2 costs planned | 337.4355
6 | TRANSPORT COSTS | 800 | 350 | 450
7 | SUB: ELECTRICITY "ELEKTROLAT" | 12050 | 12024.84 | 25.16 | hours cost in fact | 26.0711
8 | SUB: EL MESS PROT |  |  | 0 | hours per m2 in fact | 14.7271
9 | WASTE | 3600 | 2468.88 | 1131.12 | m2 costs in fact | 383.9515
10 | MECHANISMS | 2574.93 | 1186.23 | 1388.7
11 | ADD 1 | 3135.73 |  | 3135.73 | hours costs, incl. travel and living | 30.8811
12 | ADD 2 | 542.4 |  | 542.4 | living costs per person per day | 37.2322
13 | ADD 3 | 413.4 |  | 413.4
| ADD 4 | 126.5 | 110 | 16.5 |  |  |  |  | 47747.6
| ADD 5 | 1380 | 1200 | 180
| TOTAL | 53345.63 | 48408.5643 | 4937.0657 |  | 53061.0562
19.74%
| Hours workers | 568 | 583.2 | -15.2
| Hours SM/PM | 142 | 156.1 | -14.1
| ADD HOURS | 54.3 |  | 54.3
| TOTAL | 764.3 | 739.3 | 25
0

## DRE
DRE | Intimissimi and Calzedonia Prager Str. 8, 01069 Dresden, Germany |  |  |  | 7.10.2025- 7.11.2025
[8 empty] | avanss | 2.maksājums | gala rēķins
| Sales (m2): | 105.14 | 959.0922 |  | Contract amount EUR | 118500 |  | 35550 | 71100 | 11850
| BOH (m2): | 24.4 |  |  | Additional works, EUR | 6000 | CAL | 17550 | 35100 | 5850
| TOTAL (m2) | 129.54 | 778.4387 |  | Administrative costs (7% from income) | 8715 | INT | 18000 | 36000 | 6000
| Position | Planned costs | Actual costs | PROFIT | Profit | 25360.8181 |  | 15 dienas | 21/10/2025 izrakstīt, 30 dienas | 7/11/2025 izrakstīt, 30 dienas
1 | SALARY | 40190.49 | 36851.2119 | 3339.2781 |  | 20.37% |  | 3.2.1 | 3.2.2. | 3.2.3.
2 | MATERIALS | 17362.81 | 14995.99 | 2366.82
3 | HOTEL | 4200 | 5211.69 | -1011.69 | hours costs planned | 25.3664
4 | GASOLINE | 1100 | 804.93 | 295.07 | hours per m2 planned | 12.231
5 | AVIO+TRAVEL | 1800 | 679.03 | 1120.97 | m2 costs planned | 310.2554
6 | TRANSPORT COSTS | 1000 | 1830 | -830
7 | SUB: ELECTRICITY | 24976.8 | 21193 | 3783.8 | hours cost in fact | 24.3678
8 | SUB: EL MESS PROT | 2300 | 2847.44 | -547.44 | hours per m2 in fact | 11.6743
9 | WASTE | 2200 | 912.07 | 1287.93 | m2 costs in fact | 284.4775
10 | MECHANISMS | 844.85 | 1643.57 | -798.72
11 | ADD 1 | 4864 | 3455.25 | 1408.75 | hours costs, incl. travel and living | 28.2631
12 | ADD 2 |  |  | 0 | living costs per person per day | 26.1248
13 |  |  |  | 0
| TOTAL | 100838.95 | 90424.1819 | 10414.7681 |  | 99139.1819
19%
| Hours workers | 1282 | 1251.02 | 30.98
| Hours SM/PM | 256.4 | 261.27 | -4.87
| ADD HOURS | 46 | 0 | 46
| TOTAL | 1584.4 | 1512.29 | 72.11
| Avansi | 0

## LUSH
LUSH | Lush store refurmishment, list with addresses |  |  |  | time plan
| shops nr | 25 | 3331.6352 |  | Contract amount EUR | 108322.61 |  | 45% avanss 14 dienās
| BOH (m2): |  |  |  | Additional works, EUR | 5679.47 |  | 45% pēc darbu pabeigšanas 14 dienās
| TOTAL (m2) | 25 | 3331.6352 |  | Administrative costs (7% from income) | 7980.1456 | 10832.26 | 10% pēc defektu novēršanas 14 dienās
| Position | Planned costs | Actual costs | PROFIT | Profit | 43237.8177
1 | SALARY | 32157.75 | 25528.9051 | 6628.8449 |  | 37.93%
2 | MATERIALS | 26839.5 | 24538.55 | 2300.95
3 | HOTEL | 5500 | 5589.3167 | -89.3167 | hours costs planned | 43.4564
4 | GASOLINE | 1500 | 1072.775 | 427.225 | hours per m2 planned | 29.6
5 | AVIO+TRAVEL | 1200 | 181.7 | 1018.3 | m2 costs planned | 1286.31
6 | TRANSPORT COSTS | 4500 | 3470 | 1030
7 | SUB: ELECTRICITY |  |  | 0 | hours cost in fact | 32.6724
8 | SUB: EL MESS PROT |  |  | 0 | hours per m2 in fact | 31.2544
9 | WASTE | 2000 | 163.95 | 1836.05 | m2 costs in fact | 1021.1562
10 | MECHANISMS | 5894.8 | 2238.92 | 3655.88
11 | ADD 1 | 3698.83 |  | 3698.83 | hours costs, incl. travel and living | 40.0583
12 | ADD 2 |  |  | 0 | living costs per person per day
13 |  |  |  | 0
| TOTAL | 83290.88 | 62784.1167 | 20506.7633 |  | 70764.2623
26.94%
| Hours workers | 704 | 781.36 | -77.36
| Hours SM/PM |  |  | 0
| ADD HOURS | 36 |  | 36
| TOTAL | 740 | 781.36 | -41.36
Avansi
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa!

## HOKA
HOK | Neue Schönhauser Str. 9, 10178 Berlin, Germany |  |  |  | 26/08/2025-07/11/2025
maksājumi
| Sales (m2): | 85 | 4981.7639 |  | Contract amount EUR | 436134.78 | pēc līguma parakstīšanas | 143924.48 | 43613.48 | 143924.48
| BOH (m2): | 115 |  |  | Additional works, EUR | 82558.89 | pēc darbu pabeigšanas | 270403.5636 | 8255.89 | 262147.6736
| TOTAL (m2) | 200 | 2117.2496 |  | Administrative costs (7% from income) | 36308.5569 | pēc garantijas perioda -5 gadi! | 21806.74 |  | 21806.74 | The security deposit according to Sec. 6.2 and 6.3 will be paid out in return of an unlimited, directly enforceable, unconditional and irrevocable guarantee by a major EU insurance domiciled and with service address in the European Union in the retained amount. The guarantee may not include a deposit clause, must be governed by German law and stipulate the location of the construction project as place of court jurisdiction. The guarantee deed must state clearly that claims based on the guarantee will in no case become time-barred before the claims that the guarantee covers. The security (deposit or bank guarantee) will be returned to the Contractor as soon as and to the extent no more secured claims exist.
| Position | Planned costs | Actual costs | PROFIT | Profit | 184913.6446 |  |  |  | 427878.8936
1 | SALARY | 98467.77 | 57587.8835 | 40879.8865 |  | 35.65% |  | 436134.7836
2 | MATERIALS | 113138.44 | 104836.01 | 8302.43
3 | HOTEL | 9800 | 19194.25 | -9394.25 | hours costs planned | 35.6451
4 | GASOLINE | 1025 | 1232.785 | -207.785 | hours per m2 planned | 13.8122
5 | AVIO+TRAVEL | 3500 | 2876.18 | 623.82 | m2 costs planned | 492.3389
6 | TRANSPORT COSTS | 3000 | 6620.99 | -3620.99
7 | TRAVEL COSTS PM |  | 5857.56 | -5857.56
8 | SUB: HVAC ekosilti | 14272.8 | 21834.3 | -7561.5
9 | SUB: ALARM vorsiher | 7343.54 | 11720.48 | -4376.94
10 | SUB: ELECTRICITY elektrolat | 44870.1 | 43368.25 | 1501.85 | hours cost in fact | 22.5707
11 | SUB: EL MESS PROT | 3000 | 7292.47 | -4292.47 | hours per m2 in fact | 12.7572
12 | WASTE | 8000 | 7826.12 | 173.88 | m2 costs in fact | 287.9394
13 | MECHANISMS | 34473.39 | 5392.45 | 29080.94
14 | ADD 1 | 3927 | 1831.74 | 2095.26 | hours costs, incl. travel and living | 31.2209
15 | ADD 2 | 9260 |  | 9260 | living costs per person per day | 31
16 | ADD 3 | 8234.8 |  | 8234.8
17 | ADD 4 | 25315.5 |  | 25315.5
18 | ADD 5 | 2100 |  | 2100
19 | ADD 6 | 7638.6 |  | 7638.6
20 | ADD 7 | 17000 |  | 17000
21 | ADD 8 | 5638.43 |  | 5638.43
22 | ADD 9 | 3444.56 |  | 3444.56
| TOTAL | 423449.93 | 297471.4685 | 125978.4615 |  | 333780.0254
18.36%
| Hours workers | 2125.85 | 2172.69 | -46.84
| Hours SM/PM | 354.3083 | 118.75 | 235.5583
| ADD HOURS | 282.29 | 260 | 22.29
| TOTAL | 2762.4483 | 2551.44 | 211.0083
Avansi
Hoka Kudamm | 10625.85
Systemair, avanss | 1510
Optimera | 70.89
Viesnīca | 265.4267
algas | 1035.64
depo | 33.83
wurth | 47.95
parking | 20.75
Shop Maintenance GMBH | 2645
adm 7% | 743.8095
degviela | 84.55
janvāra brauciens | 705.99
3462.0138
Note on K3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: netika ieturēts

## TES
TES | TESLA_AU_VIENNA extra works |  |  |  | 11/07/2025-20/07/2025
| Sales (m2): | 100 | 182.23 |  | Contract amount EUR | 23000
| BOH (m2): |  |  |  | Additional works, EUR
| TOTAL (m2) | 100 | 182.23 |  | Administrative costs (7% from income) | 1610
| Position | Planned costs | Actual costs | PROFIT | Profit | 9434.8141
1 | SALARY | 9728 | 7208.9059 | 2519.0941 |  | 41.02%
2 | MATERIALS | 3295 | 2101.84 | 1193.16
3 | HOTEL | 2000 | 1591 | 409 | hours costs planned | 32
4 | GASOLINE | 650 | 226.49 | 423.51 | hours per m2 planned | 3.04
5 | AVIO+TRAVEL | 1000 | 539.85 | 460.15 | m2 costs planned | 97.28
6 | TRANSPORT COSTS | 100 |  | 100
7 | SUB: ELECTRICITY | 0 |  | 0 | hours cost in fact | 26.6011
8 | SUB: EL MESS PROT | 0 |  | 0 | hours per m2 in fact | 2.71
9 | WASTE | 720 |  | 720 | m2 costs in fact | 72.0891
10 | MECHANISMS | 730 | 287.1 | 442.9
11 | ADD 1 |  |  | 0 | hours costs, incl. travel and living | 34.464
12 | ADD 2 |  |  | 0 | living costs per person per day | 33.225
13 |  |  |  | 0
| TOTAL | 18223 | 11955.1859 | 6267.8141 |  | 13565.1859
20.77%
| Hours workers | 228 | 191 | 37
| Hours SM/PM | 76 | 80 | -4
ADD HOURS
| TOTAL | 304 | 271 | 33
Avansi
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa!

## FAL2
FAL2 | Falconeri Insbruck Maria-Theresien-Straße 38, 6020 Innsbruck, Austria |  |  |  |  | 29/08/2025-26/09/2025
estimated
| Sales (m2): | 108.1 | 1065.5113 |  |  | Contract amount EUR | 140000 | 140000
| BOH (m2): | 42.74 |  |  |  | Additional works, EUR | 2161.77 | 100408.17
| TOTAL (m2) | 150.84 | 763.6023 |  |  | Administrative costs (7% from income) | 9951.3239 | 9800
| Position | Planned costs | Actual costs | PROFIT |  | Profit | 24233.8115 | 29791.83
1 | SALARY | 42073 | 37770.9646 | 4302.0354 | 26.57% |  | 17.05% | 21.28%
2 | MATERIALS | 16680 | 17459.47 | -779.47
3 | HOTEL | 4950 | 6264.6 | -1314.6 |  | hours costs planned | 26.3615
4 | GASOLINE | 450 | 170.9 | 279.1 |  | hours per m2 planned | 10.5807
5 | AVIO+TRAVEL | 1200 | 2662.54 | -1462.54 |  | m2 costs planned | 763.6023
6 | TRANSPORT COSTS | 1000 | 2000 | -1000
7 | SUB: ELECTRICITY | 16431 | 17520.94 | -1089.94 |  | hours cost in fact | 25.1598
8 | SUB: EL MESS PROT | 1500 | 1415 | 85 |  | hours per m2 in fact | 9.9525
| SUB: HVAC Kaltepol | 20000 | 20000 | 0
9 | WASTE | 5370 | 833.2 | 4536.8 |  | m2 costs in fact | 715.8356
10 | MECHANISMS | 3366 | 1879.02 | 1486.98
11 | ADD 1 | 2161.77 |  | 2161.77 |  | hours costs, incl. travel and living | 31.1064
12 | ADD 2 |  |  | 0 |  | living costs per person per day | 34
13 |  |  |  | 0
| TOTAL | 115181.77 | 107976.6346 | 7205.1354 |  |  | 117927.9585
18.98%
| Hours workers | 1330 | 1212.52 | 117.48
| Hours SM/PM | 266 | 288.72 | -22.72
ADD HOURS
| TOTAL | 1596 | 1501.24 | 94.76
| Avansi | 0

## UGG
UGG | Neue Schönhauser Str. 3, 10178 Berlin, Germany |  |  |  |  | 11/07/2025-09/09/2025
maksājumi
| Sales (m2): | 95.2 | 1906.3661 |  |  | Contract amount EUR | 217968.89 | pēc līguma parakstīšanas | 71929.7 | 21796.89 | 50132.81
| BOH (m2): | 68.4 |  |  |  | Additional works, EUR | 10000 | pēc darbu pabeigšanas | 146039.19 | 10898.44 | 135140.75
| TOTAL (m2) | 163.6 | 1109.3279 |  |  | Administrative costs (7% from income) | 15957.8223 | pēc garantijas perioda -5 gadi! | 32695.33 |  | 32695.33 |  | The security deposit according to Sec. 6.2 and 6.3 will be paid out in return of an unlimited, directly enforceable, unconditional and irrevocable guarantee by a major EU insurance domiciled and with service address in the European Union in the retained amount. The guarantee may not include a deposit clause, must be governed by German law and stipulate the location of the construction project as place of court jurisdiction. The guarantee deed must state clearly that claims based on the guarantee will in no case become time-barred before the claims that the guarantee covers. The security (deposit or bank guarantee) will be returned to the Contractor as soon as and to the extent no more secured claims exist.
| Position | Planned costs | Actual costs | PROFIT |  | Profit | 64868.0318 |  |  |  | 217968.89
1 | SALARY | 58398 | 42742.5859 | 15655.4141 | 18.75% |  | 28.45%
2 | MATERIALS | 41957.94 | 28958.29 | 12999.65 | 13.29% | [5 empty] | 10898.4445
3 | HOTEL | 6500 | 6590.76 | -90.76 |  | hours costs planned | 38.3693
4 | GASOLINE | 1025 | 516.28 | 508.72 |  | hours per m2 planned | 9.3032 |  |  |  |  | 326.9532
5 | AVIO+TRAVEL COSTS | 1500 | 2135.19 | -635.19 |  | m2 costs planned | 356.956 |  |  |  |  | 1634.766
6 | TRANSPORT COSTS | 2000 | 3740 | -1740
| TRAVEL COSTS PM | 3000 | 5930.25 | -2930.25
| SUB: VENTILATION | 500 | 4749.38 | -4249.38
| SUB: HVAC | 1300 | 2666.79 | -1366.79
| SUB: SECURITY Vorsicher | 7417 | 5515.84 | 1901.16
| SUB: FIRE ALARM | 1100 |  | 1100
7 | SUB: ELECTRICITY | 31898 | 30106.35 | 1791.65 |  | hours cost in fact | 26.0424
8 | SUB: EL MESS PROT | 2500 | 6705.65 | -4205.65 |  | hours per m2 in fact | 10.0322
9 | WASTE | 2400 | 1764.67 | 635.33 |  | m2 costs in fact | 261.2627
10 | MECHANISMS | 9990.11 | 3973 | 6017.11
11 | ADD 1 | 10000 | 1048 | 8952 |  | hours costs, incl. travel and living | 31.359
12 | ADD 2 |  |  | 0 |  | living costs per person per day | 30
13 |  |  |  | 0
| TOTAL | 181486.05 | 147143.0359 | 34343.0141 |  |  | 163100.8582
20.39%
| Hours workers | 1112 | 1284.46 | -172.46
| Hours SM/PM | 278 | 291.53 | -13.53
| ADD HOURS | 132 | 65.28 | 66.72
| TOTAL | 1522 | 1641.27 | -119.27
Avansi |  | 0
Note on D12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 530 paraugu sūtīšana
Note on D17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa
Note on D24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: jūlijs

## PAN2
PAN2 | PANDORA, ULLEMISTE, TALLINN |  |  |  | 31/07/2025-31/08/2025
| Sales (m2): | 58.6 | 1155.651 |  | Contract amount EUR | 75326.52 | 22597.956
| BOH (m2): | 45.5 |  |  | Additional works, EUR | 9698.1 | 67793.868
| TOTAL (m2) | 104.1 | 650.5394 |  | Administrative costs (7% from income) | 5951.7234 | 7532.652 | pēc gada
| Position | Planned costs | Actual costs | PROFIT | Profit | 21821.832
1 | SALARY | 25181.19 | 18037.0446 | 7144.1454 |  | 25.67%
2 | MATERIALS | 10234.11 | 14320.27 | -4086.16
3 | HOTEL | 2500 | 5415.96 | -2915.96 | hours costs planned | 21.0721
4 | GASOLINE | 460 | 469.74 | -9.74 | hours per m2 planned | 11.4793
5 | AVIO+TRAVEL COSTS | 400 | 258.97 | 141.03 | m2 costs planned | 650.5394
6 | TRANSPORT COSTS | 800 | 190 | 610
| TRAVEL COSTS PM |  |  | 0
| Internal cleaning | 703.2 | 480 | 223.2
| SUB: SECURITY | 0 |  | 0
| SUB: FIRE ALARM | 0 |  | 0
7 | SUB: ELECTRICITY | 12532 | 12396.84 | 135.16 | hours cost in fact | 18.5987
8 | SUB: EL MESS PROT | 0 |  | 0 | hours per m2 in fact | 9.316
9 | WASTE | 3536.3 | 1153.2 | 2383.1 | m2 costs in fact | 173.2665
10 | MECHANISMS | 1677.35 | 969.04 | 708.31
11 | ADD 1 | 4094 | 3560 | 534 | hours costs, incl. travel and living | 24.4504
12 | ADD 2 | 3461 |  | 3461 | living costs per person per day | 36.1064
13 | ADD 3 | 2142 |  | 2142
| TOTAL | 67721.15 | 57251.0646 | 10470.0854 |  | 63202.788
20.35%
| Hours workers | 975 | 769.8 | 205.2
| Hours SM/PM | 220 | 200 | 20
| ADD HOURS |  |  | 0
| TOTAL | 1195 | 969.8 | 225.2
Avansi |  | 0

## KAR
KAR | Intimissimi Uomo Kartnerstrasse 37, Wienna, Austria |  |  |  | 04/08/2025-28/08/2025
| Sales (m2): | 83.6 | 1307.8187 |  | Contract amount EUR | 110000
| BOH (m2): | 87.8 |  |  | Additional works, EUR | 22635
| TOTAL (m2) | 171.4 | 637.8859 |  | Administrative costs (7% from income) | 9284.45
| Position | Planned costs | Actual costs | PROFIT | Profit | 23933.5907
1 | SALARY | 37657.86 | 38961.106 | -1303.246 |  | 18.04%
2 | MATERIALS | 14222.07 | 16548.91 | -2326.84
3 | HOTEL | 4800 | 9337.2033 | -4537.2033 | hours costs planned | 27.0998
4 | GASOLINE | 950 | 829.62 | 120.38 | hours per m2 planned | 8.1074
5 | AVIO+TRAVEL | 1000 | 2455.21 | -1455.21 | m2 costs planned | 219.7075
6 | TRANSPORT COSTS | 1000 | 1320 | -320
7 | SUB: ELECTRICITY | 13763 | 15567.53 | -1804.53 | hours cost in fact | 28.2167
8 | SUB: HVAC | 4901 | 7390.07 | -2489.07 | hours per m2 in fact | 8.0559
9 | WASTE | 4775 | 1208.45 | 3566.55 | m2 costs in fact | 227.311
10 | MECHANISMS | 3629.71 | 1775.22 | 1854.49
11 | ADD 1 | 21000 | 4023.64 | 16976.36 | hours costs, incl. travel and living | 36.7571
12 | ADD 2 | 1635 |  | 1635 | living costs per person per day | 21.1111
13 |  |  |  | 0
| TOTAL | 109333.64 | 99416.9593 | 9916.6807 |  | 108701.4093
17.57%
| Hours workers | 1033 | 1197.256 | -164.256 |  |  | Zaudējumi | + Additional (actual costs)
| Hours SM/PM | 206.6 | 183.524 | 23.076 |  |  | 12782.17 | 16805.81 | 21847.553
| ADD HOURS | 150 |  | 150
| TOTAL | 1389.6 | 1380.78 | 8.82
| Avansi | 0

## LIN
LIN | Intimissimi SC Pluscity, Pluskaufstrasse 1, OVE, 4061 Linz, Austria |  |  |  | 22.07.2025-18.08.2025
| Sales (m2): | 73.36 | 1039.1111 |  | Contract amount EUR | 96000
| BOH (m2): | 14.59 |  |  | Additional works, EUR | 13116.87
| TOTAL (m2) | 87.95 | 866.7333 |  | Administrative costs (7% from income) | 7638.1809
| Position | Planned costs | Actual costs | PROFIT | Profit | 30458.0691
1 | SALARY | 32476.11 | 32872.39 | -396.28 |  | 27.91%
2 | MATERIALS | 10792 | 11426.93 | -634.93
3 | HOTEL | 3600 | 3300 | 300 | hours costs planned | 26.5111
4 | GASOLINE | 750 | 670.81 | 79.19 | hours per m2 planned | 13.9284
5 | AVIO+TRAVEL | 2440 | 735.95 | 1704.05 | m2 costs planned | 369.2565
6 | TRANSPORT COSTS | 1000 | 1170 | -170
7 | SUB: ELECTRICITY | 15926 | 14698.42 | 1227.58 | hours cost in fact | 28.5685
8 | SUB: HVAC |  |  | 0 | hours per m2 in fact | 13.083
9 | WASTE | 5379 | 4062.57 | 1316.43 | m2 costs in fact | 373.7623
10 | MECHANISMS | 3866.08 | 2083.55 | 1782.53
11 | ADD 1 |  |  | 0 | hours costs, incl. travel and living | 32.0761
12 | ADD 2 |  |  | 0 | living costs per person per day | 23.5714
13 |  |  |  | 0
| TOTAL | 76229.19 | 71020.62 | 5208.57 |  | 78658.8009
30.14%
| Hours workers | 980 | 903.37 | 76.63
| Hours SM/PM | 245 | 247.28 | -2.28
ADD HOURS
| TOTAL | 1225 | 1150.65 | 74.35
Avansi | 0

## TRIE
TRI | Calzedonia Simeonstraße 38, 54290 Trier, Germany |  |  |  | 18.06.2025-11.07.2025
| Sales (m2): | 75.2 | 542.1142 |  | Contract amount EUR | 49600 | 0.5
| BOH (m2): | 56.18 |  |  | Additional works, EUR | 1858.66
| TOTAL (m2) | 131.38 | 310.2983 |  | Administrative costs (7% from income) | 3602.1062
| Position | Planned costs | Actual costs | PROFIT | Profit | 11730.2193
1 | SALARY | 22119.42 | 21830.0445 | 289.3755 |  | 22.8%
2 | MATERIALS | 7250.94 | 7411.35 | -160.41
3 | HOTEL | 3000 | 2873.14 | 126.86 | hours costs planned | 26.2389
4 | GASOLINE | 1150 | 247.5 | 902.5 | hours per m2 planned | 6.4165
5 | AVIO+TRAVEL | 1500 | 1741.46 | -241.46 | m2 costs planned | 168.3622
6 | TRANSPORT COSTS | 1000 | 1500 | -500
7 | SUB: ELECTRICITY | 0 | 0 | 0 | hours cost in fact | 27.5855
8 | SUB: EL MESS PROT | 0 | 0 | 0 | hours per m2 in fact | 6.0234
9 | WASTE | 1100 | 44.5 | 1055.5 | m2 costs in fact | 166.1596
10 | MECHANISMS | 1788.63 | 478.34 | 1310.29
11 | ADD 1 | 1858 |  | 1858 | hours costs, incl. travel and living | 33.4167
12 | ADD 2 |  |  | 0 | living costs per person per day | 24.7675
13 |  |  |  | 0
| TOTAL | 40766.99 | 36126.3345 | 4640.6555 |  | 39728.4407
| Hours workers | 675 | 628.76 | 46.24
| Hours SM/PM | 168 | 162.6 | 5.4
ADD HOURS
| TOTAL | 843 | 791.36 | 51.64
Avansi | 0
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa!

## FAL_STU3
FAL | Falconeri Sture Galerian, Stokholma |  |  |  |  | 04/06/2025-19/06/25
| Sales (m2): | 100 | 347.7272 |  |  | Contract amount EUR | 32248
| BOH (m2): |  |  |  |  | Additional works, EUR | 12035.28
| TOTAL (m2) | 100 | 347.7272 |  |  | Administrative costs (7% from income) | 3099.8296
| Position | Planned costs | Actual costs | PROFIT |  | Profit | 19331.8914
1 | SALARY | 16097.12 | 13477.6253 | 2619.4947 |  |  | 43.66%
2 | MATERIALS | 5082.46 | 4026.7714 | 1055.6886
3 | HOTEL | 2400 | 2009.5912 | 390.4088 |  | hours costs planned | 27.1109
4 | GASOLINE | 200 | 158.16 | 41.84 |  | hours per m2 planned | 5.9375
5 | AVIO+TRAVEL | 600 | 1085.78 | -485.78 |  | m2 costs planned | 160.9712
6 | TRANSPORT COSTS | 250 | 49.21 | 200.79
7 | SUB: ELECTRICITY |  |  | 0 |  | hours cost in fact | 21.8325
8 | SUB: EL MESS PROT |  |  | 0 |  | hours per m2 in fact | 6.1732
9 | WASTE | 700 | 391.4711 | 308.5289 |  | m2 costs in fact | 134.7763
10 | MECHANISMS | 541.14 | 652.95 | -111.81
11 | ADD 1 | 3044 |  | 3044 |  | hours costs, incl. travel and living | 26.8467
12 | ADD 2 | 1763 |  | 1763 |  | living costs per person per day | 22.3288
13 | ADD 3 | 4095 |  | 4095
| TOTAL | 34772.72 | 21851.559 | 12921.161 |  |  | 24951.3886
| Hours workers | 417.06 | 487.36 | -70.3
| Hours SM/PM | 83.4 | 129.96 | -46.56
| ADD HOURS | 93.29 |  | 93.29
| TOTAL | 593.75 | 617.32 | -23.57
Buildup |  |  |  |  | 10.9475
living | Easy Flat | 50775 | 18150 | 1657.9128 | 2009.5912
|  | 50787 | 3300 | 301.4387
|  | 50844 | 550 | 50.2398
0
0
0
0
0
materials | Optimera | 18988683 | 7820.16 | 714.333 | 1800.1014
|  | 19036128 | 11060.94 | 1010.3622
|  | 19127505 | 508.8 | 46.4764
|  | 19256551 | 3530.88 | 322.5284
|  | 19405455 | -3214.17 | -293.5985
0
0
0
0
waste | BigBag | 163215692 | 4285.63 | 391.4711 | 391.4711
0
0
0
0
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa!

## STU2
STU2 | Calzedonia Sture Galerian, Stokholma |  |  |  |  | 27/5/2025-9/6/2025
| Sales (m2): | 64.78 | 500.604 |  |  | Contract amount EUR | 28721.0038
| BOH (m2): |  |  |  |  | Additional works, EUR | 15387.47
| TOTAL (m2) | 64.78 | 500.604 |  |  | Administrative costs (7% from income) | 3087.5932
| Position | Planned costs | Actual costs | PROFIT |  | Profit | 22060.161
1 | SALARY | 10421.24 | 10226.9332 | 194.3068 |  |  | 50.01%
2 | MATERIALS | 2954.79 | 3985.4446 | -1030.6546
3 | HOTEL | 2100 | 2129.3266 | -29.3266 |  | hours costs planned | 22.8016
4 | GASOLINE | 250 | 123.76 | 126.24 |  | hours per m2 planned | 7.0553
5 | AVIO+TRAVEL | 500 | 516.45 | -16.45 |  | m2 costs planned | 160.8713
6 | TRANSPORT COSTS | 500 |  | 500
7 | PARKING | 300 | 131.03 | 168.97
8 | SUB: ELECTRICITY | 0 | 0 | 0 |  | hours cost in fact | 21.8969
9 | SUB: BASU | 0 | 875.6971 | -875.6971 |  | hours per m2 in fact | 7.2098
10 | WASTE | 815 | 564.3481 | 250.6519 |  | m2 costs in fact | 157.8718
11 | MECHANISMS | 666.02 | 407.73 | 258.29
12 | ADD 1 | 13922.08 |  | 13922.08 |  | hours costs, incl. travel and living | 27.5617
13 | ADD 2 |  |  | 0 |  | living costs per person per day | 25.3491
14 |  |  |  | 0
| TOTAL | 32429.13 | 18960.7196 | 13468.4104 |  |  | 22048.3128
| Hours workers | 366.34 | 399.38 | -33.04
| Hours SM/PM | 73 | 67.67 | 5.33
| ADD HOURS | 17.7 |  | 17.7
| TOTAL | 457.04 | 467.05 | -10.01
Buildup |  |  |  |  | 10.8485
living | Easy Flat | 50616 | 14850 | 1368.8528 | 2129.3266
|  | 50667 | 8250 | 760.4738
0
0
0
0
0
0
materials | Optimera | 18617860 |  | 0 | 2094.9246
|  | 18672774 | 16023.23 | 1476.9996
|  | 18862193 | 2683.09 | 247.3236
|  | 18970665 | 557.27 | 51.3684
|  | 18988675 | 3463.2 | 319.2331
0
0
0
waste | BigBag | 162398390 | 2448.93 | 225.739 | 564.3481
|  | 162710495 | 3673.4 | 338.609
0
0
0
subcontractor | Stromfeldt | 25004 | 9500 | 875.6971 | 875.6971
0
Note on D14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa!

## STU
STU | Intimissimi Sture Galerian, Stokholma |  |  |  |  | 18/05/2025-25/05/2025
| Sales (m2): | 63 | 348.0683 |  |  | Contract amount EUR | 29275
| BOH (m2): |  |  |  |  | Additional works, EUR
| TOTAL (m2) | 63 | 348.0683 |  |  | Administrative costs (7% from income) | 2049.25
| Position | Planned costs | Actual costs | PROFIT |  | Profit | 14268.8913
1 | SALARY | 8431.15 | 7752.3918 | 678.7582 |  |  | 48.74%
2 | MATERIALS | 4620.41 | 1877.433 | 2742.977
3 | HOTEL | 2100 | 755.2386 | 1344.7614 |  | hours costs planned | 24.1069
4 | GASOLINE | 500 | 123.76 | 376.24 |  | hours per m2 planned | 5.5514
5 | AVIO+TRAVEL | 2800 | 979.51 | 1820.49 |  | m2 costs planned | 133.8278
6 | TRANSPORT COSTS | 500 | 80 | 420
7 | PARKING | 300 | 139.21 | 160.79
8 | SUB: ELECTRICITY | 0 | 0 | 0 |  | hours cost in fact | 21.5944
9 | SUB: EL MESS PROT | 0 | 0 | 0 |  | hours per m2 in fact | 5.6984
10 | WASTE | 800 | 205.0587 | 594.9413 |  | m2 costs in fact | 123.0538
11 | MECHANISMS | 1876.74 | 1044.2566 | 832.4834
12 | ADD 1 |  |  | 0 |  | hours costs, incl. travel and living | 26.4266
13 | ADD 2 |  |  | 0 |  | living costs per person per day | 15.7341
14 |  |  |  | 0
| TOTAL | 21928.3 | 12956.8587 | 8971.4413 |  |  | 15006.1087
| Hours workers | 289.74 | 324 | -34.26
| Hours SM/PM | 60 | 35 | 25
ADD HOURS
| TOTAL | 349.74 | 359 | -9.26
Buildup |  |  |  |  | 10.9237
living | Easy Flat | 50600 | 8250 | 755.2386 | 755.2386
0
0
0
0
0
0
0
materials | Optimera | 18502179 | 3398.86 | 311.1455 | 535.553
|  | 18523241 | 1075.9 | 98.4923
|  | 18617860 | 1375.46 | 125.9152
0
0
0
0
0
0
waste | BigBag | 162233399 | 2240 | 205.0587 | 205.0587
0
0
0
0
mechanisms | Cramo | 12078296 | 626 | 57.3066 | 57.3066
Note on D14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa!

## SWA
SWA | Swarovski store in shopping center Mall of Scandinavia Stjärntorget 2, 169 79 Solna, Sweden |  |  |  |  | 1/4/2025-30/4/2025, 6/5/2025-15/5/2025
| Sales (m2): | 64.39 | 1903.7976 |  |  | Contract amount EUR | 145000 | Payment conditions
| BOH (m2): | 17.16 |  |  |  | Additional works, EUR | 10574.43 | 30% | 43500 | 10d
| TOTAL (m2) | 81.55 | 1503.1947 |  |  | Administrative costs (7% from income) | 10890.2101 | 60% | 87000 | 30 d
| Position | Planned costs | Actual costs | PROFIT |  | Profit | 11467.7182 | 10% | 14500 | 30 d
1 | SALARY | 24742.51 | 23759.7505 | 982.7595 |  |  | 7.371%
2 | MATERIALS | 14720.52 | 15259.0518 | -538.5318
3 | HOTEL (4 eur/h) | 3183.68 | 4889.0909 | -1705.4109 |  | hours costs planned | 23.8615
4 | GASOLINE+DRIVER |  |  | 0 |  | hours per m2 planned | 12.7151
5 | AVIO+TRAVEL (1 eur/h) | 795.92 | 3496.89 | -2700.97 |  | m2 costs planned | 303.4029
6 | TRANSPORT COSTS | 1000 | 1680 | -680
7 | SUB: ELECTRICITY | 31500 | 30550 | 950 |  | hours cost in fact | 24.2471
8 | SUB: KWIKWORKS | 30020 | 30719.42 | -699.42 |  | hours per m2 in fact | 12.0159
9 | SUB: SPRINKLERS |  |  | 0 |  | m2 costs in fact | 291.3519
10 | MECHANISMS | 6048.47 | 10788.3623 | -4739.8923
11 | ADD 1 | 155.83 |  | 155.83 |  | hours costs, incl. travel and living | 32.8051
12 | ADD 2 | 10418.6 | 8090.2 | 2328.4 |  | living costs per person per day | 32.5939
13 | Project manager travels |  | 3983.7362 | -3983.7362
| TOTAL | 122585.53 | 133216.5017 | -10630.9717 |  |  | 144106.7118
| Hours workers | 795.92 | 707.46 | 88.46
| Hours SM/PM | 214 | 245.44 | -31.44
| ADD HOURS | 27 | 27 | 0
| TOTAL | 1036.92 | 979.9 | 57.02
| Buildup |  |  |  |  | 11
living | Easy Flat | 49982 | 39060 | SEK | 3550.9091 | EUR
|  | 50358 | 420 | SEK | 38.1818
|  | 50450 | 8250 | SEK | 750
|  | 50475 | 3300 | SEK | 300
|  | 50530 | 2750 | SEK | 250
materials | Optimera | 17292053 | 13400.92 |  | 1218.2655 | 4057.6018
|  | 17309717 | 1319.7 |  | 119.9727
|  | 17327107 | 1695.36 |  | 154.1236
|  | 17370198 | 9863.25 |  | 896.6591
|  | 17399783 | 2293.43 |  | 208.4936
|  | 17437336 | 611.98 |  | 55.6345
|  | 17417874 | 726.19 |  | 66.0173
|  | 17456344 | 3467.25 |  | 315.2045
|  | 17583584 | 1975.03 |  | 179.5482
|  | 17645284 | 3356.59 |  | 305.1445
|  | 17727991 | 1870.61 |  | 170.0555
|  | 18041699 | -1499.41 |  | -136.31
|  | 18302596 | 218.95 |  | 19.9045
|  | 18409466 | 2928.82 |  | 266.2564
| Bevego | 11974794 | 433.95 |  | 39.45
0
| Wurth | 216352 | 1971 |  | 179.1818
0
0
mechanisms | Cramo | 11998907 | 526.48 |  | 47.8618 | 6324.4373
|  | 12010834 | 8009.02 |  | 728.0927
|  | 12019010 | 9768.96 |  | 888.0873
|  | 12037378 | 9263.34 |  | 842.1218
|  | 12056938 | 10238.8 |  | 930.8
| Flinks | 3610416 | 750 |  | 68.1818
|  | 3612958 | 1056 |  | 96
0
|  | 3615468 | 1059 |  | 96.2727
| Urban services | 26029 | 2057.06 |  | 187.0055
|  | 26261 | 1299.15 |  | 118.1045
| Kranpunkten | 10250015624 | 241 |  | 21.9091
| Fortnox | 7307 | 25300 |  | 2300
subcontractor | Artel AB | 34800 | 100800 |  | 9163.6364 | 30545.4545 | -4.5455
|  | 34816 | 100000 |  | 9090.9091
|  | 34820 | 101600 |  | 9236.3636
|  | 34822 | 33600 |  | 3054.5455
Add works 2 | A-Sprinkler AB | 2365003663 | 22892 |  | 2081.0909 | 8112
|  | 2365003724 | 7575 |  | 688.6364
| Säkerhetsbolaget FST AB | 7092 | 31595 |  | 2872.2727
| Elteknikbolaget i Stockholm AB | 10095 | 22345 |  | 2031.3636
| Avarn | 19882117 | 4825 |  | 438.6364
| Avansi | 0
Note on D12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa!
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: līguma summa

## FRO
FRO | Calzedonia and Intimissimi, Frölunda torg, 421 42 Västra Frölunda, Sweden 25/03/2025-31/03/2025
Object costs
|  | Marts |  | Aprīlis | [5 empty] | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 23863.6219 |  | 5500 | [5 empty] | 29363.6219 |  | Contract amount EUR | 23863.6219 | 25/03-31/03 | 26/02-03/03 | 2025-04-01 | [8 empty] | total
Objekta tiešie izdevumi | Direct costs | 12212.3988 |  | 4525.7258 |  | 0 |  | 0 |  | 16738.1245 |  | Additional works, EUR | 5500 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
mtr. un aprīkojuma iegāde | materials and equipment | 1029.31 | 3595.9918 | 320.19 | 2250.19 |  | 0 |  | 0 | 1349.5 | 5846.1818 | square m2 | 38.5 | 25/03-31/03 1: 188 | 188
mtr. piegādes izdevumi | delivery |  |  | 1930 | [5 empty] | 1930 |  | object square | hours optimal/ m2 | 25/03-31/03 1: 134; 26/02-03/03 2: 32.47 | 166.47
apakšuzņēmēji | subcontractors | 2566.6818 | [7 empty] | 2566.6818 |  | m2<50 | 13
darba algas | salaries | 1946.1177 | 6068.077 | 931.3057 | 1928.0808 |  | 0 |  | 0 | 2877.4234 | 7996.1577 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 459.0892 |  | 219.695 |  | 0 |  | 0 |  | 678.7842
uzkrājums atvaļinājumam | vacation allowance | 192.4166 |  | 92.0801 |  | 0 |  | 0 |  | 284.4966 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 1670.4535 |  | 385 |  | 0 |  | 0 |  | 2055.4535 |  | planned | 804.01
kom. dienas naudas | travel allowance | 1800 |  | 300 | [5 empty] | 2100 |  | in fact | 3279.5
kom. izdevumi- naktsmītne | travel expenses (hotels) | 945.48 | 2548.33 | 203 | 347.455 |  | 0 |  | 0 | 1148.48 | 2895.785
kom. izdevumi- ceļš | travel expenses ( tickets, road costs) | 300.35 | [7 empty] | 300.35 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | 471.73 | [7 empty] | 471.73 |  | planned | 6568.84
citi izdevumi | other expenses | 830.77 |  | 144.455 | [5 empty] | 975.225 |  | in fact | 5940.7042
peļņa bruto | profit/ loss | 11651.2231 | 48.82% | 974.2742 | 17.71% | 0 | #DIV/0! | 0 | #DIV/0! | 12625.4974 | 43% | hours costs planned | 34.9406
plānotā peļņa | planned profit | [8 empty] | 5921.8319 | 24.82% | hours cost in fact | 35.6863 | 25/03-31/03 1: travel and living costs
[14 empty] | 25/03-31/03 | 26/02-03/03 | 2025-04-01 | 20/03-26/03 | 27/03-02/04 | 03/04-09/04 | 10/04-12/04 | 23/04-30/04 | 01/05-04/05 | 0 | 0 | total
Direct costs | actual costs | planned costs | [9 empty] | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Materials, incl.delivery, and subcontractors | 34.93% | 4.481% | [9 empty] | planned | 4.8831 | 1: 3400 | 3400
Salaries and taxes | 47.77% | 36.61% | [9 empty] | in fact | 4.3239 | 1: 1245.83; 3: 203 | 1448.83
Other costs | 17.3% | 58.91% | [9 empty] | m2 costs | 154.304
travel and living costs
[12 empty] | planned | 3400
[12 empty] | in fact | 1448.83
[12 empty] | living costs per worked hour | 8.7032
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2025-05-08
|  | 50% | 50%
tāmes summa SEK | 262559.5 | 131279.75 | 131279.75
kurss 19.03.2025 | 11.0025
tāmes summa EUR | 23863.62 | 11931.81 | 11931.81
| Alena trūkstošie čeki | 310.03
| Buildup, Ragn Sells | 4758.5 | sek | [6 empty] | 432.5909 | eur
| Buildup, Ragn Sells | 8779 | sek | [6 empty] | 798.0909
Note on C42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Alena trūkstošie čeki

## LULU
LULU | garantijas darbi februārī, kondicioniera uzstādīšana jūnijā
Object costs
|  | Februāris |  | Jūnijs/ jūlijs |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 0 |  | 38063.1 |  | 38063.1 | 0 | Contract amount EUR | 38063.1 | 11/2-14/2 | [10 empty] | total
Objekta tiešie izdevumi | Direct costs | 5119.4555 |  | 22993.0873 |  | 28112.5428 |  | Additional works, EUR |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 2845.9153 | 2845.9153 | 2478.9229 | 16584.3053 | 5324.8382 | 19430.2207 | square m2
materiālu piegādes izdevumi | delivery |  |  |  |  | 0 |  | object square | hours optimal/ m2 | 11/2-14/2 1: 27.84 | 27.84 | 197.0119
apakšuzņēmēji | subcontractors |  |  | 14105.3824 |  | 14105.3824 |  | m2<50 | 13
darba algas | salaries | 595.57 | 1194.9502 | 2254.48 | 4289.862 | 2850.05 | 5484.8121 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 140.495 |  | 531.8318 |  | 672.3268
uzkrājums atvaļinājumam | vacation allowance | 58.8852 |  | 222.9049 |  | 281.7901 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 0 |  | 280.6452 |  | 280.6452 |  | planned
komandējuma dienas naudas | travel allowance | 400 |  | 1000 |  | 1400 |  | in fact | 5324.8382
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 239.46 | 1078.59 |  | 2118.92 | 239.46 | 3197.51
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 627.38 |  |  |  | 627.38 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | 211.75 |  |  |  | 211.75 |  | planned
citi izdevumi | other expenses |  |  | 2118.92 |  | 2118.92 |  | in fact | 5204.1669
peļņa bruto | profit/ loss | -5119.4555 | #DIV/0! | 15070.0127 | 39.59% | 9950.5572 | 26.14% | hours costs planned | #DIV/0!
plānotā peļņa | [6 empty] | 0% | hours cost in fact | 186.9313
travel and living costs
Direct costs | actual costs | planned costs | [5 empty] | hours per m2 |  | 11/2-14/2 1: 11/2-14/2 | total
Materials, incl.delivery, and subcontractors | 69.12% | = | [5 empty] | planned | #DIV/0! | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 19.51% | = | [5 empty] | in fact | #DIV/0! | 11/2-14/2 1: 0; 11/2-14/2 2: 0 | 0
Other costs | 11.37% | = | [5 empty] | m2 costs | #DIV/0! | 11/2-14/2 1: 866.84 | 866.84
travel and living costs
planned
[8 empty] | in fact | 866.84
[8 empty] | living costs per worked hour | 31.1365
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2025-03-03
27903.64
Bevego | 11922063 | 3708 | 11.2895
Optimera | 15960198 | 795.64
Vent assistants | 5322 | 20000
PRB Injustering | 1272 | 3400

## INS
INS | Intimissimi Insbruck Rathaus Galerian, Austria, 3/3/2025-19/3/2025
Object costs
|  | Marts |  |  |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 60000 | 435.2 |  |  | 60000 | 435.2 | Contract amount EUR | 60000 | 3/3-9/3 | 10/3-16/3 | [9 empty] | total
Objekta tiešie izdevumi | Direct costs | 42232.8658 |  | 0 |  | 42232.8658 |  | Additional works, EUR |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 5096.2 | 22749.64 |  | 0 | 5096.2 | 22749.64 | square m2 | 54.52 | 3/3-9/3 1: 201; 10/3-16/3 2: 201 | 402
materiālu piegādes izdevumi | delivery | 650 |  |  |  | 650 |  | object square | hours optimal/ m2 | 3/3-9/3 1: 223.47; 10/3-16/3 2: 211.73 | 435.2
apakšuzņēmēji | subcontractors | 17003.44 |  |  |  | 17003.44 |  | m2<50 | 13
darba algas | salaries | 4991.4036 | 17506.1558 |  | 0 | 4991.4036 | 17506.1558 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 1177.4721 |  | 0 |  | 1177.4721
uzkrājums atvaļinājumam | vacation allowance | 493.5101 |  | 0 |  | 493.5101 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 4200 |  | 0 |  | 4200 |  | planned | 6874.93
BUAK |  | 2593.77 |  |  |  | 2593.77 |  | in fact | 5746.2
komandējuma dienas naudas | travel allowance | 4050 |  |  |  | 4050
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2534.84 | 4570.84 |  | 0 | 2534.84 | 4570.84
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 687.36 |  |  |  | 687.36 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | [6 empty] | planned | 12318.22
citi izdevumi | other expenses | 1348.64 |  |  |  | 1348.64 |  | in fact | 13306.1558
peļņa bruto | profit/ loss | 17767.1342 | 29.61% | 0 | #DIV/0! | 17767.1342 | 29.61% | hours costs planned | 30.6423
plānotā peļņa | planned profit |  |  |  |  | 14598.94 | 24.33% | hours cost in fact | 30.5748 | 3/3-9/3 1: travel and living costs
[10 empty] | 3/3-9/3 1: 3/3-9/3; 10/3-16/3 2: 10/3-16/3 | total
Direct costs | actual costs | planned costs | [5 empty] | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Materials, incl.delivery, and subcontractors | 53.87% | 15.14% | [5 empty] | planned | 7.3734 | 3/3-9/3 1: 2500; 10/3-16/3 2: 2500 | 5000
Salaries and taxes | 41.45% | 27.13% | [5 empty] | in fact | 7.9824 | 3/3-9/3 1: 2981.85; 10/3-16/3 2: 240.35 | 3222.2
Other costs | 10.82% | 58.17% | [5 empty] | m2 costs | 244.0601
travel and living costs
[8 empty] | planned | 5000
[8 empty] | in fact | 3222.2
[8 empty] | living costs per worked hour | 7.404
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2025-05-09
avanss | 0

## AKR
AKR | Calzedonia un Intimissimi Akropole, Latgales iela 257, 03/02/2025-
Object costs
|  | Februāris |  | Februāris |  | Total |  | General data |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 15496 | 284.43 |  |  | 15496 | 284.43 | Contract amount EUR | 15496 | Time shedule, weeks | [11 empty] | total
Objekta tiešie izdevumi | Direct costs | 11993.1056 |  | 0 |  | 11993.1056 |  | Additional works, EUR |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 1652.63 | 2600.8 |  | 0 | 1652.63 | 2600.8 | square m2 |  |  | 1: 0; 2: 0
materiālu piegādes izdevumi | delivery |  |  |  |  | 0 |  | object square | hours optimal/ m2 |  | 1: 278.93; 2: 5.5
apakšuzņēmēji | subcontractors | 948.17 |  |  |  | 948.17 |  | m2<50 | 13
darba algas | salaries | 5942.5996 | 9016.7356 |  | 0 | 5942.5996 | 9016.7356 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 1401.8592 |  | 0 |  | 1401.8592
uzkrājums atvaļinājumam | vacation allowance | 587.5567 |  | 0 |  | 587.5567 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 1084.72 |  | 0 |  | 1084.72 |  | planned
komandējuma dienas naudas | travel allowance |  |  |  |  | 0 |  | in fact | 2600.8
komandējuma izdevumi- naktsmītne | travel expenses (hotels) |  | 375.57 |  | 0 | 0 | 375.57
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) |  |  |  |  | 0 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) |  |  |  |  | 0 |  | planned
citi izdevumi | other expenses | 375.57 |  |  |  | 375.57 |  | in fact | 7932.0156
[8 empty] | hours costs planned | #DIV/0!
peļņa bruto | profit/ loss | 3502.8944 | 22.61% | 0 | #DIV/0! | 3502.8944 | 22.61% | hours cost in fact | #DIV/0!
plānotā peļņa | planned profit | [5 empty] | 0%
[8 empty] | hours per m2 |  | Object address | 1: travel and living costs
Direct costs | actual costs | planned costs | [5 empty] | planned | #DIV/0! | Time shedule, weeks | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | total
Materials, incl.delivery, and subcontractors | 21.69% | [6 empty] | in fact | #DIV/0! |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 75.18% | [6 empty] | m2 costs | #DIV/0! |  | 1: 0
Other costs | 3.132% | [9 empty] | 1: 0 | 0
travel and living costs
[8 empty] | planned | 0
[8 empty] | in fact | 0
[8 empty] | living costs per worked hour | 0
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2025-03-28
avansi | 0

## PAN
PAN | PANDORA SC Viru Keskus, Viru väljak 4-6, 10111 Tallinn, Estonia, 10/3/2025-31/3/2025
Object costs
|  | Marts |  | 2023-02-01 |  |  |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 67309.81 | 734.6 |  |  |  |  | 67309.81 | 734.6 | Contract amount EUR | 59771.61 | 10/03-16/03 | 17/03-23/03 | 24/03-31/03 | [8 empty] | total
Objekta tiešie izdevumi | Direct costs | 58583.808 |  | 0 |  | 0 |  | 58583.808 |  | Additional works, EUR | 7538.2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 5852.63 | 31486.59 |  | 0 |  | 0 | 5852.63 | 31486.59 | square m2 | 33.2 | 10/03-16/03 1: 173; 17/03-23/03 2: 173; 24/03-31/03 3: 173 | 519
materiālu piegādes izdevumi | delivery | 810 | [5 empty] | 810 |  | object square | hours optimal/ m2 | 10/03-16/03 1: 210; 17/03-23/03 2: 304.5; 24/03-31/03 3: 220.1 | 734.6 | 215.6 | pārtēriņš
apakšuzņēmēji | subcontractors | 24823.96 | [5 empty] | 24823.96 |  | m2<50 | 13 | [12 empty] | 55.99 | bez Kaspara K.
darba algas | salaries | 11659.6028 | 24074.598 |  | 0 |  | 0 | 11659.6028 | 24074.598 | 50<m2<100 | 12 | [12 empty] | 1399.75
DD VSAOI | tax for salaries | 2750.5003 |  | 0 |  | 0 |  | 2750.5003
uzkrājums atvaļinājumam | vacation allowance | 1152.8082 |  | 0 |  | 0 |  | 1152.8082 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 4711.6867 |  | 0 |  | 0 |  | 4711.6867 |  | planned | 5797.35
komandējuma dienas naudas | travel allowance | 3800 | [5 empty] | 3800 |  | in fact | 6662.63
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2114.12 | 3022.62 |  | 0 |  | 0 | 2114.12 | 3022.62
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | [6 empty] | 0 |  | Salaries and taxes
komandējuma izdevumi- administrācija | travel expenses (administration) | 320.64 | [7 empty] | planned | 11954.1
citi izdevumi | other expenses | 908.5 | [5 empty] | 908.5 |  | in fact | 19362.9113
peļņa bruto | profit/ loss | 8726.002 | 12.96% | 0 | #DIV/0! | 0 | #DIV/0! | 8726.002 | 12.96% | hours costs planned | 34.5494
plānotā peļņa | planned profit | [6 empty] | 14722.01 | 24.63% | hours cost in fact | 26.3584
Direct costs | actual costs | planned costs | [7 empty] | hours per m2
Materials, incl.delivery, and subcontractors | 53.75% | 12.19% | [7 empty] | planned | 15.6325 | 10/03-16/03 1: travel and living costs
Salaries and taxes | 41.09% | 25.14% | [7 empty] | in fact | 22.1265 | 10/03-16/03 1: 10/03-16/03; 17/03-23/03 2: 17/03-23/03; 24/03-31/03 3: 24/03-31/03 | total
Other costs | 5.159% | 62.67% | [7 empty] | m2 costs | 583.2202 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
[12 empty] | 10/03-16/03 1: 1000; 17/03-23/03 2: 1000; 24/03-31/03 3: 1000 | 3000
[10 empty] | travel and living costs |  | 10/03-16/03 1: 1905.12; 24/03-31/03 3: 209 | 2114.12
[10 empty] | planned | 3000
[10 empty] | in fact | 2114.12
[10 empty] | living costs per worked hour | 2.8779
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2025-04-10
30 | 17931.48
60 | 35862.97
10 | 5977.16
59771.61
avansi | 0

## COL
COL | Intimissimi KÖLN SC RHEIN CENTER, 10/02/2025-27/02/2025
Object costs
|  | 2025-02-24 |  | 2025-03-24 |  | 2025-04-24 |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 46000 |  |  |  | 0 |  | 46000 |  | Contract amount EUR | 46000 | 10/2-16/2 | 17/2-23/2 | 24/2-27/2 | [8 empty] | total
Objekta tiešie izdevumi | Direct costs | 34495.8237 |  | 0 |  | 0 |  | 34495.8237 |  | Additional works, EUR | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 5903.82 | 8321.74 |  | 0 |  | 0 | 5903.82 | 8321.74 | square m2 | 60.49 | 10/2-16/2 1: 202; 17/2-23/2 2: 202; 24/2-27/2 3: 202 | 606
materiālu piegādes izdevumi | delivery | 1230 | [5 empty] | 1230 |  | object square | hours optimal/ m2 | 10/2-16/2 1: 269.43; 17/2-23/2 2: 243.6; 24/2-27/2 3: 208.55 | 721.58
apakšuzņēmēji | subcontractors | 1187.92 | [5 empty] | 1187.92 |  | m2<50 | 13
darba algas | salaries | 9594.78 | 22655.4537 |  | 0 |  | 0 | 9594.78 | 22655.4537 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 2263.4086 |  | 0 |  | 0 |  | 2263.4086
uzkrājums atvaļinājumam | vacation allowance | 948.6551 |  | 0 |  | 0 |  | 948.6551 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 3220 |  | 0 |  | 0 |  | 3220 |  | planned | 8247.34
SOKA BAU |  | 1578.61 | [5 empty] | 1578.61 |  | in fact | 8321.74
komandējuma dienas naudas | travel allowance | 5050 | [5 empty] | 5050
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2831 | 5097.24 |  | 0 |  | 0 | 2831 | 5097.24
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1350.52 | [5 empty] | 1350.52 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | [6 empty] | 0 |  | planned | 17538.71
citi izdevumi | other expenses | 915.72 | [5 empty] | 915.72 |  | in fact | 19435.4537
[10 empty] | hours costs planned | 32.7215
peļņa bruto | profit/ loss | 11504.1763 | 25.01% | 0 | #DIV/0! | 0 | #DIV/0! | 11504.1763 | 25.01% | hours cost in fact | 26.9346
plānotā peļņa | planned profit | [6 empty] | 6333.19 | 13.77% |  |  | 10/2-16/2 1: travel and living costs
[10 empty] | hours per m2 |  | 10/2-16/2 1: 10/2-16/2; 17/2-23/2 2: 17/2-23/2; 24/2-27/2 3: 24/2-27/2 | total
Direct costs | actual costs | planned costs | [7 empty] | planned | 8.861 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Materials, incl.delivery, and subcontractors | 24.12% | 20.79% | [7 empty] | in fact | 11.9289 | 10/2-16/2 1: 1400; 17/2-23/2 2: 1400; 24/2-27/2 3: 1400 | 4200
Salaries and taxes | 65.68% | 44.22% | [7 empty] | m2 costs | 321.3003 | 10/2-16/2 1: 3613.8; 17/2-23/2 2: 305.17; 24/2-27/2 3: 262.55 | 4181.52
Other costs | 14.78% | 34.91%
travel and living costs
[10 empty] | planned | 4200
[10 empty] | in fact | 4181.52
[10 empty] | living costs per worked hour | 5.7949
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2025-04-01
avansi | 0

## EXAMPLE
| Sales (m2): | 47.8 | 982.06 |  | INNSBRUCK UOMO
| BOH (m2): | 6.72
| TOTAL (m2) | 54.52 | 861.0138
| Position | Planned costs | Actual costs | PROFIT
1 | SALARY | 13466.13 |  | 13466.13
2 | MATERIALS | 6772.73 |  | 6772.73
3 | HOTEL | 3500 |  | 3500
4 | GASOLINE | 1100 |  | 1100
5 | AVIO+TRAVEL | 1500 |  | 1500
6 | TRANSPORT COSTS | 1000 |  | 1000
7 | SUB: ELECTRICITY | 13686.4 | 13686.4 | 0
8 | SUB: EL MESS PROT | 1800 |  | 1800
9 | WASTE | 1100 |  | 1100
10 | MECHANISMS | 3017.21 |  | 3017.21
11 | ADD 1 |  |  | 0
12 | ADD 2 |  |  | 0
13 |  |  |  | 0
| TOTAL | 46942.47 | 13686.4 | 33256.07
| Hours workers | 402.63 | 312 | 90.63
| Hours SM/PM | 100 | 123 | -23
ADD HOURS
| TOTAL | 502.63 | 435 | 67.63

## PAN3 (Kristaps)
PAN3 | Pandora SC Rocca al Mare Mall Paldiski mnt 102, 13522 Tallinn, Estonia |  |  |  |  | 30/09/2025-18/10/2025
| Sales (m2): | 38.7 | 1354.062 |  |  | Contract amount EUR | 60866.14 | 18259.84 | avanss, 10 dienas
| BOH (m2): | 11.5 |  |  |  | Additional works, EUR | 5598 | 36519.68 | pēc pabeigšanas, 30 dienas
| TOTAL (m2) | 50.2 | 1043.8685 |  |  | Administrative costs (7% from income) | 4652.5 | 6086.61 | pēc garantijas perioda beigām, 30 dienas
| Position | Planned costs | Actual costs | PROFIT |  | Profit | 13403.0757
1 | SALARY | 18133.86 | 19274.3643 | -1140.5043 | 1140.5 |  | 20.17%
2 | MATERIALS | 8491.91 | 8238.22 | 253.69
3 | HOTEL | 4000 | 3537.06 | 462.94 |  | hours costs planned | 23.7261
4 | GASOLINE | 500 |  | 500 |  | hours per m2 planned | 15.2251
5 | AVIO+TRAVEL | 400 | 18.97 | 381.03 |  | m2 costs planned | 361.2323
6 | TRANSPORT COSTS | 800 | 350 | 450
7 | SUB: ELECTRICITY "ELEKTROLAT" | 12050 | 12024.84 | 25.16 |  | hours cost in fact | 26.0711
8 | SUB: EL MESS PROT |  |  | 0 |  | hours per m2 in fact | 14.7271
9 | WASTE | 3600 | 2468.88 | 1131.12 |  | m2 costs in fact | 383.9515
10 | MECHANISMS | 2919.93 | 1186.23 | 1733.7
11 | ADD 1 |  |  | 0 |  | hours costs, incl. travel and living | 30.8811
12 | ADD 2 |  |  | 0 |  | living costs per person per day | 37.2322
13 | ADD 3 |  |  | 0
| ADD 4 | 126.5 | 110 | 16.5 | [5 empty] | 50895.7
| ADD 5 | 1380 | 1200 | 180
| TOTAL | 52402.2 | 48408.5643 | 3993.6357 |  |  | 53061.0643
21.16%
| Hours workers | 568 | 583.2 | -15.2
| Hours SM/PM | 142 | 156.1 | -14.1
| ADD HOURS | 54.3 |  | 54.3
| TOTAL | 764.3 | 739.3 | 25
0

## PAN2 (Kristaps)
PAN2 | PANDORA, ULLEMISTE, TALLINN |  |  |  | 31/07/2025-31/08/2025
| Sales (m2): | 58.6 | 1141.9935 |  | Contract amount EUR | 75326.52 | 22597.956
| BOH (m2): | 45.5 |  |  | Additional works, EUR | 9698.1 | 67793.868
| TOTAL (m2) | 104.1 | 642.8513 |  | Administrative costs (7% from income) | 5951.7234 | 7532.652 | pēc gada
| Position | Planned costs | Actual costs | PROFIT | Profit | 21821.832
1 | SALARY | 27076.62 | 18037.0446 | 9039.5754 |  | 25.67%
2 | MATERIALS | 12784.11 | 14320.27 | -1536.16
3 | HOTEL | 2500 | 5415.96 | -2915.96 | hours costs planned | 21.4676
4 | GASOLINE | 460 | 469.74 | -9.74 | hours per m2 planned | 12.116
5 | AVIO+TRAVEL COSTS | 400 | 258.97 | 141.03 | m2 costs planned | 642.8513
6 | TRANSPORT COSTS | 800 | 190 | 610
| TRAVEL COSTS PM |  |  | 0
| Internal cleaning | 703.2 | 480 | 223.2
| SUB: SECURITY | 0 |  | 0
| SUB: FIRE ALARM | 0 |  | 0
7 | SUB: ELECTRICITY | 12532 | 12396.84 | 135.16 | hours cost in fact | 18.5987
8 | SUB: EL MESS PROT | 0 |  | 0 | hours per m2 in fact | 9.316
9 | WASTE | 3536.3 | 1153.2 | 2383.1 | m2 costs in fact | 173.2665
10 | MECHANISMS | 2034.59 | 969.04 | 1065.55
11 | ADD 1 | 4094 | 3560 | 534 | hours costs, incl. travel and living | 24.4504 | 4094
12 | ADD 2 |  |  | 0 | living costs per person per day | 36.1064 | 3461
13 | ADD 3 |  |  | 0 |  |  | 2142
| TOTAL | 66920.82 | 57251.0646 | 9669.7554 |  | 63202.788
21.29%
| Hours workers | 975 | 769.8 | 205.2
| Hours SM/PM | 220 | 200 | 20
| ADD HOURS | 66.28 |  | 66.28
| TOTAL | 1261.28 | 969.8 | 291.48
Avansi |  | 0