## Total 2024
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
| MOS | GAL | SWA | KOB | VIL | BRA | GRA | KLA | WDON | STO | LEI | MAT | OLA | FRA | LULU | STK | SEI | KRE | WIE | BERG | LIN | LULU2 | ING | MUN | WIE2 | HAM | SPICE
contract amount | 43564.77 | 56957.32 | 14988.39 | 48000 | 48000 | 136747.57 | 41000 | 12955.25 | 43500 | 50368.84 | 72434.83 | 40811.18 | 129183.05 | 119402.13 | 630472.08 | 7504.45 | 68000 | 40000 | 39000 | 71500 | 55000 | 12910 | 59000 | 89825.47 | 83000 | 57000 | 4728.19 | 2075853.52
additional works | 11547.57 | 1963.79 | -1611.38 | 7924.07 | 4875.23 | 9121.36 | 5715.75 | 2797.7 | 0 | 17392.32 | 14891.4 | 47337.07 | 1728 | 52684.17 | 0 | 0 | 5896.3 | 0 | 0 | 17228.25 | 0 | 11947.66 | 3500 | 2703.54 | 0 | 7030.01 | 0 | 224672.81
total income | 55112.34 | 58921.11 | 13377.01 | 55924.07 | 52875.23 | 145868.93 | 46715.75 | 15752.95 | 43500 | 67761.16 | 87326.23 | 88148.25 | 130911.05 | 172086.3 | 630472.08 | 7504.45 | 73896.3 | 40000 | 39000 | 88728.25 | 55000 | 24857.66 | 62500 | 92529.01 | 83000 | 64030.01 | 4728.19 | 2300526.33
project manager | Alens | Alens | Māris | Alex | Mauro | Alens | Mauro | Kristaps | Mauro | Māris | Alens | Alex | Alex | Kristaps | Alens | Kristaps | Alens | Alexander | Alens | Alens | Alens | Alens | Alexander | Kaspars | Alex | Kaspars
planned hours | 537 | 511 | 97.25 | 214 | 597.08 | 1494.02 | 489.05 | 217.35 | 496.87 | 730 | 840 | 560 | 1139.51 | 904.59 | 3502.97 | 0 | 715.22 | 363 | 375.75 | 992.72 | 680 | 0 | 624.51 | 1055.8 | 826 | 495.97
worked hours | 797.95 | 595.38 | 62.5 | 207.61 | 522.18 | 1444.72 | 428.3 | 205.51 | 398.31 | 0 | 783.32 | 554.46 | 1304.16 | 1076.2 | 3437.31 | 87.79 | 826.23 | 400.47 | 240.47 | 1391.09 | 598.78 | 200.75 | 801.15 | 1107.98 | 841.17 | 475.35
stundu bilance | -260.95 | -84.38 | 34.75 | 6.39 | 74.9 | 49.3 | 60.75 | 11.84 | 98.56 | 730 | 56.68 | 5.54 | -164.65 | -171.61 | 65.66 | -87.79 | -111.01 | -37.47 | 135.28 | -398.37 | 81.22 | -200.75 | -176.64 | -52.18 | -15.17 | 20.62
profit % | 31.95% | 48.52% | 46.6% | 22.88% | 30.8% | 31.3% | 18.63% | 40.69% | 39.95% | 21.84% | 11.17% | 15.55% | 9.139% | 15.13% | 35.65% | 7.384% | 17.05% | 30.96% | 26.05% | 25.68% | 21.75% | 37.01% | 11.51% | 28.97% | 27.65% | 19.2% | 53.56% | 26.61%
profit EUR | 17607.5308 | 28587.2663 | 6233.2271 | 12795.2178 | 16287.7248 | 45650.4933 | 8701.6815 | 6409.1208 | 17376.1506 | 14795.9581 | 9756.8395 | 13705.6558 | 11963.3433 | 26034.5257 | 224740.9253 | 554.137 | 12600.4988 | 12385.8285 | 10160.9624 | 22784.271 | 11960.011 | 9200.7684 | 7194.1275 | 26805.2326 | 22945.7691 | 12295.0657 | 2532.537 | 612064.8696
construction works profit/ loss | 17607.5308 | 28587.2663 | 6233.2271 | 12795.2178 | 16287.7248 | 45650.4933 | 8701.6815 | 6409.1208 | 17376.1506 | 58439.2519 | 9756.8395 | 13705.6558 | 11963.3433 | 32034.5257 | 224740.9253 | 554.137 | 12600.4988 | 0 | #REF! | 25094.111 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
construction works budget | 55112.34 | 58921.11 | 13377.01 | 55924.07 | 52875.23 | 145868.93 | 46715.75 | 15752.95 | 43500 | 27962.27 | 87326.23 | 88148.25 | 130911.05 | 172086.3 | 630472.08 | 7504.45 | 73896.3 | 40000 | #REF! | 88728.25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 37504.8092 | 30333.8437 | 7143.7829 | 43128.8522 | 36587.5052 | 100218.4367 | 38014.0685 | 9343.8292 | 26123.8494 | -30476.9819 | 77569.3905 | 74442.5942 | 118947.7067 | 140051.7743 | 405731.1547 | 6950.313 | 41051.1212 | 0 | 20199.3476 | 63634.139 | #REF! | 15656.8916 | 0 | 51569.8274 | 41148.2809 | 0
| 31.95% | 48.52% | 46.6% | 22.88% | 30.8% | 31.3% | 18.63% | 40.69% | 39.95% | 209% | 11.17% | 15.55% | 9.139% | 18.62% | 35.65% | 7.384% | 17.05% | 0% | #REF! | 28.28% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
subcontractors work profit/loss | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5474.05 | -5200 | 0 | 0 | -6000 | 0 | 0 | -20244.68 | 0 | #REF!
subcontractors budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39798.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45272.94 | 5200 | 0 | 0 | 6000 | 0 | 0 | 20244.68 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -13.75% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
administrative costs 7% | 3994.1914 | 4124.4777 | 936.3907 | 3360 | 3701.2661 | 10172.2763 | 3270.1025 | 956.1775 | 3045 | 4743.2819 | 6112.8361 | 6170.3775 | 9163.7735 | 12046.041 | 75026.1775 | 525.3115 | 5172.741 | 2800 | 2730 | 5005 | 3850 | 1740.0362 | 4375 | 6477.0307 | 5810 | 4482.1007 | 330.9733 | 190120.563 | 26.61%

## Profit
Object | object total | Profit (%) | Project manager
GAL | 58921.11 | 48.52% | Alens | 28587.2663
SWA | 13377.01 | 46.6% | Māris | 6233.2271
HAM | 64030.01 | 19.2% | Kaspars | 12295.0657
LULU2 | 24857.66 | 37.01% | Alens | 9200.7684
KLA | 15752.95 | 40.69% | Kristaps | 6409.1208
WDON | 43500 | 39.95% | Mauro | 17376.1506
LULU | 630472.08 | 35.65% | Alens | 224740.9253
KRE | 40000 | 30.96% | Alexander | 12385.8285
MOS | 55112.34 | 31.95% | Alens | 17607.5308
WIE | 39000 | 26.05% | Alens | 10160.9624
BRA | 145868.93 | 31.3% | Alens | 45650.4933
VIL | 52875.23 | 30.8% | Mauro | 16287.7248
WIE2 | 83000 | 27.65% | Alexander | 22945.7691
BERG | 88728.25 | 25.68% | Alens | 22784.271
MUN | 92529.01 | 28.97% | Kaspars | 26805.2326
KOB | 55924.07 | 22.88% | Alex | 12795.2178
STO | 67761.17 | 21.84% | Māris | 14795.9581
LIN | 55000 | 21.75% | Alens | 11960.011
GRA | 46715.75 | 18.63% | Mauro | 8701.6815
FRA | 172086.3 | 15.13% | Kristaps/ Kaspars/Alex | 26034.5257
SEI | 73896.3 | 17.05% | Alens | 12600.4988
MAT | 88148.25 | 15.55% | Māris/ Jevgēņijs | 13705.6558
ING | 62500 | 11.51% | Alexander | 7194.1275
LEI | 87326.23 | 11.17% | Alens | 9756.8395
OLA | 130911.05 | 9.139% | Alexander | 11963.3433
STK | 7504.45 | 7.384% | Kristaps | 554.137
SPICE | 4728.19 | 53.56% |  | 2532.537

## Bezpeļņas objekti
VSV | Vesuvio
Object costs | [11 empty] | KPI
|  | Janvāris |  | Februāris |  | Marts |  | Aprīlis |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract
Objekta ieņēmumi kopā | Budget total | [8 empty] | 16301.5055 |  | Time shedule, weeks | 09/05-15/05 | 16/05-22/05 | 23/05-29/05 | 30/05-05/06 | 06/06-12/06 | 13/06-21/06 | total | planned
Objekta tiešie izdevumi | Direct costs | 5618.1367 |  | 2175.3267 |  | 5325.8514 |  | 605.9625 |  | 14686.0469 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact
materiālu un aprīkojuma iegāde | materials and equipment | 2240.5 | 2440.69 | 133.08 | 228.62 | 1198.57 | 1241.79 | 105.02 | 105.02 | 3677.17 | 4016.12 |  | 20% | 40% | 60% | 80% | 100% |  | 100%
materiālu piegādes izdevumi | delivery | [8 empty] | 0 |  |  | 20% | 40% | 60% | 80% | 100% |  | 100% | planned
apakšuzņēmēji | subcontractors | 200.19 |  | 95.54 |  | 43.22 |  |  |  | 338.95 | [8 empty] | 0% | in fact | bar: 1 to 6
darba algas | salaries | 2301.252 | 3071.6467 | 1447.8178 | 1932.5067 | 3000.034 | 4004.3614 | 363.165 | 484.7425 | 7112.2688 | 10454.0269
DD VSAOI | tax for salaries | 542.8653 |  | 341.5402 |  | 707.708 |  | 85.6706 |  | 1677.7842 | [9 empty] | Contract amount EUR | 16301.5055
uzkrājums atvaļinājumam | vacation allowance | 227.5294 |  | 143.1486 |  | 296.6194 |  | 35.9068 |  | 703.2042 | [9 empty] | Additional works, EUR
administratīvie izdevumi 7% | administrative costs 7% | [8 empty] | 960.7696
komandējuma dienas naudas | travel allowance | [8 empty] | 0 | [9 empty] | square m2
komandējuma izdevumi- naktsmītne | travel expenses (hotels) |  | 105.8 |  | 14.2 |  | 79.7 |  | 16.2 | 0 | 215.9 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | [8 empty] | 0 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 105.8 |  | 14.2 |  | 79.7 |  | 16.2 |  | 215.9 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | -5618.1367 | #DIV/0! | -2175.3267 | #DIV/0! | -5325.8514 | #DIV/0! | -605.9625 | #DIV/0! | 1615.4586 | 9.91%
[12 empty] | Object address | 1: materials and equipments costs |  | materials and equipment costs
Direct costs | % | [10 empty] | Time shedule, weeks | 09/05-15/05 | 16/05-22/05 | 23/05-29/05 | 30/05-05/06 | 06/06-12/06 | 13/06-21/06 | total | planned
Materials, incl.delivery, and subcontractors | 27.3465 | [11 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 3677.17
Salaries and taxes | 71.1834 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | travel and living costs
Other costs | 1.4701 | [17 empty] | 0 | planned | 0
[20 empty] | in fact | 0
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-04-15
Unas darbs- transporta organizēšana, dokumentu kārtošana
Kristapa darbs- preču pieņemšana, piegādes, būvgružu izvešana
A9 | Alberta iela
Object costs | [11 empty] | KPI
|  | Marts |  | Aprīlis |  | Maijs |  |  |  | Total |  | Object address | 1: execution of contract |  | execution of the contract
Objekta ieņēmumi kopā | Budget total | 3000 |  | 4000 | [5 empty] | 7000 |  | Time shedule, weeks | 09/05-15/05 | 16/05-22/05 | 23/05-29/05 | 30/05-05/06 | 06/06-12/06 | 13/06-21/06 | total | planned | 100%
Objekta tiešie izdevumi | Direct costs | 7081.5553 |  | 0 |  | 727.83 |  | 0 |  | 7081.5553 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 233.3%
materiālu un aprīkojuma iegāde | materials and equipment | 766.79 | 2565.17 |  | 0 | 727.83 | 727.83 |  | 0 | 766.79 | 2565.17 |  | 20% | 40% | 60% | 80% | 100% |  | 100% | hours per m2
materiālu piegādes izdevumi | delivery | [8 empty] | 0 |  |  | 20% | 40% | 60% | 80% | 100% |  | 100% | planned | 0
apakšuzņēmēji | subcontractors | 1798.38 | [7 empty] | 1798.38 |  |  | 6: 133.3% | 133.3% | in fact | 0
darba algas | salaries | 2981 | 4188.9553 |  | 0 |  | 0 |  | 0 | 2981 | 4188.9553
DD VSAOI | tax for salaries | 703.2179 |  | 0 |  | 0 |  | 0 |  | 703.2179 | [9 empty] | Contract amount EUR | 3000
uzkrājums atvaļinājumam | vacation allowance | 294.7374 |  | 0 |  | 0 |  | 0 |  | 294.7374 | [9 empty] | Additional works, EUR | 4000
administratīvie izdevumi 7% | administrative costs 7% | 210 |  | 0 |  | 0 |  | 0 |  | 210
komandējuma dienas naudas | travel allowance | [8 empty] | 0 | [9 empty] | square m2
komandējuma izdevumi- naktsmītne | travel expenses (hotels) |  | 327.43 |  | 0 |  | 0 |  | 0 | 0 | 327.43 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | [8 empty] | 0 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 327.43 | [7 empty] | 327.43 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | -4081.5553 | -136.1% | 4000 | 100% | -727.83 | #DIV/0! | 0 | #DIV/0! | -81.5553 | -1.165%
[12 empty] | Object address | 1: materials and equipments costs |  | materials and equipment costs
Direct costs | % | [10 empty] | Time shedule, weeks | 09/05-15/05 | 16/05-22/05 | 23/05-29/05 | 30/05-05/06 | 06/06-12/06 | 13/06-21/06 | total | planned
Materials, incl.delivery, and subcontractors | 36.2233 | [11 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 766.79
Salaries and taxes | 59.153 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | travel and living costs
Other costs | 4.6237 | [17 empty] | 0 | planned | 0
[20 empty] | in fact | 0
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-04-30
M61, ofiss | 3653.96 |  |  | K18-22 | 5052.4049 |  | H36-34 | 8783.4363 |  | K18-33 | 5570.166
GSS, krāsošana | 1108.4 |  |  | Ikea | 4147.17 |  | Ikea | 6957.6 |  | Ikea | 4995.28
Beļajevs, atslēgu maiņa | 261.19 |  |  | PTA (veļasmašīna) | 359
4Room, lampas | 918.84
4Room, lampas | 326.61 |  |  | krāsošana (19.2 h*10) | 336.9558 |  | krāsošana, grīdas seguma maiņa | 774.2963 |  | Alens, 13.78 h | 241.836
Ikea, biroja galds Jevgenijam | 370.25 |  |  | Jysk, gultas veļa, dvieļi, 56.94 | 56.94 |  |  |  |  | Beļajevs, atslēgu maiņa | 290
Interdepo, biroja galds, apspriežu | 189.26 |  |  | būvgružu izvešana, 4 h*10, 78.26 eur | 148.4591 |  | būvgružu izvešana | 347.11 |  | būvgružu izvešana | 43.05
Euronics, monitori Jevgenijam/ Kristapam | 390.02 |  |  | Optimera, 3.88 | 3.88 |  | Optimera, grīdas segums | 704.43
PTA, mikroviļņu krāsns | 79.34
Optimera, lampa | 10.05
M61, 58.dzīvoklis | 5096.23
Beļajevs, atslēgu maiņa | 135.81
Ikea, interjera projekts+ mēbeles | 3866.32
GSS, krāsošana | 521.6
Jysk, gultas veļa, dvieļi | 191.91
PTA, veļasmašīna | 283.47
Rimi, virtuves piederumi | 97.12
4620.85
PTA, trauku mašīna, 27/12/2024 | 369
VSV | Vesuvio
Object costs | [11 empty] | KPI
|  | Oktobris |  | Novembris |  | Decembris |  |  |  | Total |  | Object address | 1: execution of contract |  | execution of the contract
Objekta ieņēmumi kopā | Budget total | [8 empty] | 4463.9647 |  | Time shedule, weeks | 09/05-15/05 | 16/05-22/05 | 23/05-29/05 | 30/05-05/06 | 06/06-12/06 | 13/06-21/06 | total | planned
Objekta tiešie izdevumi | Direct costs | 2530.1824 |  | 1452.1522 |  | 75.815 |  | 0 |  | 4058.1497 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact
materiālu un aprīkojuma iegāde | materials and equipment | 488.45 | 488.45 | 1264.51 | 1264.51 |  | 0 |  | 0 | 1752.96 | 1752.96 |  | 20% | 40% | 60% | 80% | 100% |  | 100%
materiālu piegādes izdevumi | delivery | [8 empty] | 0 |  |  | 20% | 40% | 60% | 80% | 100% |  | 100% | planned
apakšuzņēmēji | subcontractors | [8 empty] | 0 | [8 empty] | 0% | in fact | bar: 1 to 6
darba algas | salaries | 1497.958 | 1999.4324 | 140.58 | 187.6422 | 56.8 | 75.815 |  | 0 | 1695.338 | 2262.8897
DD VSAOI | tax for salaries | 353.3683 |  | 33.1628 |  | 13.3991 |  | 0 |  | 399.9302 | [9 empty] | Contract amount EUR | 4463.9647
uzkrājums atvaļinājumam | vacation allowance | 148.1061 |  | 13.8994 |  | 5.6159 |  | 0 |  | 167.6215 | [9 empty] | Additional works, EUR
administratīvie izdevumi 7% | administrative costs 7%
komandējuma dienas naudas | travel allowance | [8 empty] | 0 | [9 empty] | square m2
komandējuma izdevumi- naktsmītne | travel expenses (hotels) |  | 42.3 |  | 0 |  | 0 |  | 0 | 0 | 42.3 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | [8 empty] | 0 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 42.3 | [7 empty] | 42.3 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | -2530.1824 | #DIV/0! | -1452.1522 | #DIV/0! | -75.815 | #DIV/0! | 0 | #DIV/0! | 405.815 | 9.091%
[12 empty] | Object address | 1: materials and equipments costs |  | materials and equipment costs
Direct costs | % | [10 empty] | Time shedule, weeks | 09/05-15/05 | 16/05-22/05 | 23/05-29/05 | 30/05-05/06 | 06/06-12/06 | 13/06-21/06 | total | planned
Materials, incl.delivery, and subcontractors | 43.196 | [11 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 1752.96
Salaries and taxes | 55.7616 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | travel and living costs
Other costs | 1.0423 | [17 empty] | 0 | planned | 0
[20 empty] | in fact | 0
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
Akustisko paneļu montāža | [19 empty] | 2024-12-12
Ģipškartona darbi?
avanss Produs
avanss Nordeca
0

## SPICE
SPICE | Rīga, 21/10-?
Object costs
|  | Oktobris |  |  |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 4728.19 |  |  |  | 4728.19 |  | Contract amount EUR | 4728.19 | [10 empty] | total
Objekta tiešie izdevumi | Direct costs | 2195.653 |  | 0 |  | 2195.653 |  | Additional works, EUR |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
materiālu un aprīkojuma iegāde | materials and equipment | 97.81 | 97.81 |  | 0 | 97.81 | 97.81 | square m2 |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0
materiālu piegādes izdevumi | delivery |  |  |  |  | 0 |  | object square | hours optimal/ m2 | 1: 44.9 | 44.9
apakšuzņēmēji | subcontractors | 0 |  |  |  | 0 |  | m2<50 | 13
darba algas | salaries | 1323.724 | 2097.843 |  | 0 | 1323.724 | 2097.843 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 312.2665 |  | 0 |  | 312.2665
uzkrājums atvaļinājumam | vacation allowance | 130.8792 |  | 0 |  | 130.8792 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 330.9733 |  | 0 |  | 330.9733 |  | planned
komandējuma dienas naudas | travel allowance |  |  |  |  | 0 |  | in fact
komandējuma izdevumi- naktsmītne | travel expenses (hotels) |  | 0 |  | 0 | 0 | 0
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) |  |  |  |  | 0 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) |  |  |  |  | 0 |  | planned
citi izdevumi | other expenses |  |  |  |  | 0 |  | in fact | 1766.8697
[8 empty] | hours cost in fact | 39.3512 | 1: travel and living costs
peļņa bruto | profit/ loss | 2532.537 | 53.56% | 0 | #DIV/0! | 2532.537 | 53.56% | [12 empty] | total
plānotā peļņa | planned profit | [5 empty] | 0% | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
[8 empty] | planned | #DIV/0! | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
Direct costs | actual costs | planned costs | [5 empty] | in fact | #DIV/0! | 1: 0 | 0
Materials, incl.delivery, and subcontractors | 4.455% | [6 empty] | m2 costs | #DIV/0!
Salaries and taxes | 95.55%
Other costs | 0% | [6 empty] | travel and living costs
planned
[8 empty] | in fact | 0
[8 empty] | living costs per worked hour | 0
Subcontractors budget, EUR
[8 empty] | Payments to subcontractor, EUR | 0
date of report
2024-10-21

## HAM
HAM | Calzedonia store Phoenix Center, Hannoversche Str. 86, 21079 , Hamburg, Germania 1/10/2024-(22/10/2024) 12/11/2024
Object costs
|  | Oktobris |  | Novembris |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 57000 |  | 7030.01 |  | 64030.01 |  | Contract amount EUR | 57000 | 1/10-6/10 | 7/10-13/10 | 14/10-20/10 | 21/10-22/10 | 31/10-10/11 | 11/11/-12/11 |  |  |  |  | total
Objekta tiešie izdevumi | Direct costs | 22113.3095 |  | 29621.6348 |  | 51734.9443 |  | Additional works, EUR | 7030.01 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
materiālu un aprīkojuma iegāde | materials and equipment | 5769.49 | 7239.49 | 468.64 | 19542.49 | 6238.13 | 26781.98 | square m2 | 50.59 | 1: 123.9925; 2: 123.9925; 3: 123.9925; 4: 123.9925; 5: 123.9925 | 495.97
materiālu piegādes izdevumi | delivery | 1470 |  |  |  | 1470 |  | object square | hours optimal/ m2 | 1: 48.73; 2: 146.03; 3: 47.59; 5: 233 | 475.35
apakšuzņēmēji | subcontractors | 0 |  | 19073.85 |  | 19073.85 |  | m2<50 | 13
darba algas | salaries | 2222.087 | 9405.9795 | 3632.4736 | 7440.6248 | 5854.5606 | 16846.6043 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 524.1903 |  | 856.9005 |  | 1381.0908
uzkrājums atvaļinājumam | vacation allowance | 219.7022 |  | 359.1499 |  | 578.8521 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 3990 |  | 492.1007 |  | 4482.1007 |  | planned | 7013.12
komandējuma dienas naudas | travel allowance | 2450 |  | 2100 |  | 4550 |  | in fact | 7708.13
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2520 | 5467.84 | 1440.48 | 2638.52 | 3960.48 | 8106.36
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1461.07 |  | 524.91 |  | 1985.98 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) |  |  |  |  | 0 |  | planned | 12399.33
citi izdevumi | other expenses | 1486.77 |  | 673.13 |  | 2159.9 |  | in fact | 12364.5036
[8 empty] | hours cost in fact | 26.0114 | 1: travel and living costs
peļņa bruto | profit/ loss | 34886.6905 | 61.2% | -22591.6248 | -321.4% | 12295.0657 | 19.2% |  |  | 1/10-6/10 | 7/10-13/10 | 14/10-20/10 | 21/10-22/10 | 31/10-10/11 | 11/11/-12/11 |  |  |  |  | total
plānotā peļņa | planned profit |  |  |  |  | 10759.62 | 18.88% | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
[8 empty] | planned | 9.8037 | 1: 1625; 2: 1625; 3: 1625; 4: 1625 | 6500
Direct costs | actual costs | planned costs | [5 empty] | in fact | 9.3961 | 1: 2841; 3: 546.6; 4: 593.5; 5: 1508.92; 6: 456.47 | 5946.49
Materials, incl.delivery, and subcontractors | 51.77% | 15.17% | [5 empty] | m2 costs | 244.4061
Salaries and taxes | 32.56% | 26.81%
Other costs | 15.67% | 58.02% | [5 empty] | travel and living costs
[8 empty] | planned | 6500
[8 empty] | in fact | 5946.46
[8 empty] | living costs per worked hour | 8.3317
Subcontractors budget, EUR
[8 empty] | Payments to subcontractor, EUR | 19073.85
date of report
2024-12-12

## BERG
BERG | Calzedonia and Intimissimi Hauptstraße 152, 51465 Bergisch Gladbach, Germany 25/09/2024-(22/10/2024) 9/11/2024
Object costs
|  | Septembris |  | Oktobris |  | Novembris |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 17875 |  | 53625 |  | 17228.25 |  | 88728.25 |  | Contract amount EUR | 71500 | 25/09-29/09 | 30/09-06/10 | 07/10-13/10 | 14/10-20/10 | 21/10-27/10 | 28/10- |  |  |  |  | total
Objekta tiešie izdevumi | Direct costs | 23294.5819 |  | 35381.7279 |  | 8473.6467 |  | 65943.979 |  | Additional works, EUR | 17228.25 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
materiālu un aprīkojuma iegāde | materials and equipment | 8828.2 | 10577.18 | 4602.49 | 7112.06 | 422.99 | 2405.86 | 13853.68 | 20095.1 | square m2 | 111.58 | 1: 248.18; 2: 248.18; 3: 248.18; 4: 248.18; 5: 248.18 | 992.72
materiālu piegādes izdevumi | delivery | 1450 |  | 2330 |  | 151.58 |  | 3931.58 |  | object square | hours optimal/ m2 | 159.67 | 273.94 | 298.2 | 287.08 | 170.52 | 201.68 |  |  |  |  | 1391.09
apakšuzņēmēji | subcontractors | 298.98 |  | 179.57 |  | 1831.29 |  | 2309.84 |  | m2<50 | 13
darba algas | salaries | 1416.2583 | 5041.6319 | 9669.987 | 23910.9779 | 1735.1122 | 4521.9567 | 12821.3575 | 32268.589 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 334.0953 |  | 2281.1499 |  | 409.313 |  | 3024.5582
uzkrājums atvaļinājumam | vacation allowance | 140.0283 |  | 956.091 |  | 171.554 |  | 1267.6733 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 1251.25 |  | 3753.75 |  | 1205.9775 |  | 5005 |  | planned | 12879.19
komandējuma dienas naudas | travel allowance | 1900 |  | 7250 |  | 1000 |  | 10150 |  | in fact | 17785.26
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 5390.63 | 7675.77 | 1122.84 | 4358.69 | 487.45 | 1545.83 | 7000.92 | 13580.29
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1117.95 |  | 957.63 |  | 552.3 |  | 2627.88 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | 1467.78 |  | 53 |  |  |  | 1520.78 |  | planned | 23206.63
citi izdevumi | other expenses | 1167.19 |  | 2278.22 |  | 506.08 |  | 3951.49 |  | in fact | 27263.589
[10 empty] | hours cost in fact | 19.5987 | 1: travel and living costs
peļņa bruto | profit/ loss | -5419.5819 | -30.32% | 18243.2721 | 34.02% | 8754.6033 | 50.82% | 22784.271 | 25.68% |  |  | 25/09-29/09 | 30/09-06/10 | 07/10-13/10 | 14/10-20/10 | 21/10-27/10 | 28/10- |  |  |  |  | total
plānotā peļņa | planned profit | [6 empty] | 17394.54 | 24.33% | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
[10 empty] | planned | 8.8969 | 1: 1800; 2: 1800; 3: 1800; 4: 1800; 5: 1800 | 7200
Direct costs | actual costs | planned costs | [7 empty] | in fact | 12.4672 | 1: 6508.58; 2: 1232; 4: 148.3; 5: 699.98; 6: 1039.75 | 9628.61
Materials, incl.delivery, and subcontractors | 30.47% | 23.8% | [7 empty] | m2 costs | 244.3412
Salaries and taxes | 48.93% | 42.89%
Other costs | 20.59% | 32.82% | [7 empty] | travel and living costs
[10 empty] | planned | 7200
[10 empty] | in fact | 9628.8
[10 empty] | living costs per worked hour | 5.0327
Subcontractors budget, EUR
[10 empty] | Payments to subcontractor, EUR | 2309.84
date of report
2024-12-10
| avansi | 0

## WIE2
WIE2 | Calzedonia Mariahilfer Str. 88, 1070 Wien, Austria 16/09-09/10
Object costs
|  | Septembris |  | Oktobris |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 41500 |  | 41500 |  | 83000 |  | Contract amount EUR | 83000 | 16/09-22/09 | 23/09-29/09 | 30/09-6/10 | 7/10-9/10 | [6 empty] | total
Objekta tiešie izdevumi | Direct costs | 26783.3157 |  | 33270.9151 |  | 60054.2309 |  | Additional works, EUR |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
materiālu un aprīkojuma iegāde | materials and equipment | 5280.76 | 7498.81 | 787.51 | 19686.35 | 6068.27 | 27185.16 | square m2 | 82.33 | 16/09-22/09 1: 206.5; 23/09-29/09 2: 206.5; 30/09-6/10 3: 206.5; 7/10-9/10 4: 206.5; 7/10-9/10 5: 206.5 | 826
materiālu piegādes izdevumi | delivery | 1740 |  | 470.94 |  | 2210.94 |  | object square | hours optimal/ m2 | 16/09-22/09 1: 268.12; 23/09-29/09 2: 272.2; 30/09-6/10 3: 243.97; 7/10-9/10 4: 56.88 | 841.17
apakšuzņēmēji | subcontractors | 478.05 |  | 18427.9 |  | 18905.95 |  | m2<50 | 13
darba algas | salaries | 6467.1912 | 15537.2257 | 2693.9246 | 8600.7751 | 9161.1158 | 24138.0009 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 1525.6104 |  | 635.4968 |  | 2161.1072
uzkrājums atvaļinājumam | vacation allowance | 639.4241 |  | 266.3537 |  | 905.7778 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 2905 |  | 2905 |  | 5810 |  | planned | 8093.49
komandējuma dienas naudas | travel allowance | 4000 |  | 2100 |  | 6100 |  | in fact | 8279.21
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2339.08 | 3747.28 | 175 | 4983.79 | 2514.08 | 8731.07
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 881.39 |  | 184.52 |  | 1065.91 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | 60.48 |  | 804.59 |  | 865.07 |  | planned | 20641.85
citi izdevumi | other expenses | 526.81 |  | 4624.27 |  | 5151.08 |  | in fact | 18328.0009
[8 empty] | hours cost in fact | 21.7887 | 16/09-22/09 1: travel and living costs
peļņa bruto | profit/ loss | 14716.6843 | 35.46% | 8229.0849 | 19.83% | 22945.7691 | 27.65% |  |  | 16/09-22/09 1: 16/09-22/09; 23/09-29/09 2: 23/09-29/09; 30/09-6/10 3: 30/09-6/10; 7/10-9/10 4: 7/10-9/10 | total
plānotā peļņa | planned profit |  |  |  |  | 21103.79 | 25.43% | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
[8 empty] | planned | 10.0328 | 16/09-22/09 1: 1687.5; 23/09-29/09 2: 1687.5; 30/09-6/10 3: 1687.5; 7/10-9/10 4: 1687.5; 7/10-9/10 5: 1687.5 | 6750
Direct costs | actual costs | planned costs | [5 empty] | in fact | 10.2171 | 16/09-22/09 1: 3220.47; 30/09-6/10 3: 146.81; 7/10-9/10 4: 212.71 | 3579.99
Materials, incl.delivery, and subcontractors | 45.27% | 13.08% | [5 empty] | m2 costs | 222.6163
Salaries and taxes | 40.19% | 33.35%
Other costs | 14.54% | 38.27% | [5 empty] | travel and living costs
[8 empty] | planned | 6750
[8 empty] | in fact | 3579.99
[8 empty] | living costs per worked hour | 2.9888
Subcontractors budget, EUR
[8 empty] | Payments to subcontractor, EUR | 18905.95
date of report
2025-02-03

## MUN
MUN | Calzedonia and Intimissimi SC Riem Arcaden Willy-Brandt-Platz 5, 81829 München, Germany 19/08-16/09
Object costs
|  | Augusts |  | Septembris |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 44912.735 |  | 47616.275 |  | 92529.01 |  | Contract amount EUR | 89825.47 | 19/08-25/08 | 26/08-01/09 | 2/09-8/09 | 09/08-16/09 | [6 empty] | total
Objekta tiešie izdevumi | Direct costs | 33523.5234 |  | 32200.2539 |  | 65723.7774 |  | Additional works, EUR | 2703.54 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
materiālu un aprīkojuma iegāde | materials and equipment | 6980.75 | 9330.75 | 2037.73 | 15541.68 | 9018.48 | 24872.43 | square m2 | 141.54 | 19/08-25/08 1: 211.16; 26/08-01/09 2: 211.16; 2/09-8/09 3: 211.16; 09/08-16/09 4: 211.16; 09/08-16/09 5: 211.16 | 1055.8
materiālu piegādes izdevumi | delivery | 850 |  | 850 |  | 1700 |  | object square | hours optimal/ m2 | 19/08-25/08 1: 337; 26/08-01/09 2: 319; 2/09-8/09 3: 271.8; 09/08-16/09 4: 180.18 | 1107.98
apakšuzņēmēji | subcontractors | 1500 |  | 12653.95 |  | 14153.95 |  | m2<50 | 13
darba algas | salaries | 8165.426 | 17942.8734 | 3852.4742 | 12075.3139 | 12017.9002 | 30018.1874 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 1926.224 |  | 908.7987 |  | 2835.0227
uzkrājums atvaļinājumam | vacation allowance | 807.332 |  | 380.9018 |  | 1188.2338 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 3143.8915 |  | 3333.1393 |  | 6477.0307 |  | planned | 10954.74
komandējuma dienas naudas | travel allowance | 3900 |  | 3600 |  | 7500 |  | in fact | 10718.48
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 3060 | 6249.9 | 2895.4 | 4583.26 | 5955.4 | 10833.16
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1276.24 |  | 106.52 |  | 1382.76 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | 693.98 |  | 2078.28 |  | 2772.26 |  | planned | 28490.4
citi izdevumi | other expenses | 1913.66 |  | 1581.34 |  | 3495 |  | in fact | 23541.1567
[8 empty] | hours cost in fact | 21.2469 | 19/08-25/08 1: travel and living costs
peļņa bruto | profit/ loss | 11389.2116 | 25.36% | 15416.0211 | 32.38% | 26805.2326 | 28.97% |  |  | 19/08-25/08 1: 19/08-25/08; 26/08-01/09 2: 26/08-01/09; 2/09-8/09 3: 2/09-8/09; 09/08-16/09 4: 09/08-16/09 | total
plānotā peļņa | planned profit |  |  |  |  | 24824.78 | 27.64% | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
[8 empty] | planned | 7.4594 | 19/08-25/08 1: 2000; 26/08-01/09 2: 2000; 2/09-8/09 3: 2000; 09/08-16/09 4: 2000; 09/08-16/09 5: 2000 | 10000
Direct costs | actual costs | planned costs | [5 empty] | in fact | 7.828 | 19/08-25/08 1: 4336.24; 26/08-01/09 2: 2700; 2/09-8/09 3: 106.52; 09/08-16/09 4: 195.4 | 7338.16
Materials, incl.delivery, and subcontractors | 37.84% | 16.85% | [5 empty] | m2 costs | 166.3216
Salaries and taxes | 45.67% | 43.83%
Other costs | 16.48% | 39.29% | [5 empty] | travel and living costs
[8 empty] | planned | 10000
[8 empty] | in fact | 7338.16
[8 empty] | living costs per worked hour | 5.375
Subcontractors budget, EUR
[8 empty] | Payments to subcontractor, EUR | 14153.95
date of report
2024-11-11
avansi
Riga Wood
EL Support
|  | 30% | 60% | 10% | KOPĀ
| 38864.31 | 11659.29 | 23318.59 | 3886.43 | 38864.31 | Calzedonia
| 50961.16 | 15288.35 | 30576.7 | 5096.11 | 50961.16 | Intimissimi
|  |  | 53895.29 | 8982.54

## ING
ING | Calzedonia Am Westpark 6, 85057 Ingolstadt, Germany, 2/08/2024-22/08/2024
Object costs
|  | Augusts |  |  |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 62500 |  |  |  | 62500 |  | Contract amount EUR | 59000 | 2/8-11/8 | 12/08-18/08 | 19/08-25/08 | [8 empty] | total
Objekta tiešie izdevumi | Direct costs | 55305.8725 |  | 0 |  | 55305.8725 |  | Additional works, EUR | 3500 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 6089.92 | 27208.25 |  | 0 | 6089.92 | 27208.25 | square m2 | 52.39 | 208.17 | 208.17 | 208.17 | [8 empty] | 624.51
materiālu piegādes izdevumi | delivery | 1348 |  |  |  | 1348 |  | object square | hours optimal/ m2 | 376.15 | 235 | 190 | [8 empty] | 801.15 | ir ok, bez Alex
apakšuzņēmēji | subcontractors | 19770.33 |  |  |  | 19770.33 |  | m2<50 | 13
darba algas | salaries | 8685.5152 | 21468.1825 |  | 0 | 8685.5152 | 21468.1825 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 2048.913 |  | 0 |  | 2048.913
uzkrājums atvaļinājumam | vacation allowance | 858.7543 |  | 0 |  | 858.7543 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 4375 |  | 0 |  | 4375 |  | planned | 7144.64
komandējuma dienas naudas | travel allowance | 5500 |  |  |  | 5500 |  | in fact | 7437.92
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 3580.96 | 6629.44 |  | 0 | 3580.96 | 6629.44
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 658.72 |  |  |  | 658.72 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | 1196.94 |  |  |  | 1196.94 |  | planned | 16233.85
citi izdevumi | other expenses | 2389.76 |  |  |  | 2389.76 |  | in fact | 17093.1825
[8 empty] | hours cost in fact | 21.3358 | travel and living costs
peļņa bruto | profit/ loss | 7194.1275 | 11.51% | 0 | #DIV/0! | 7194.1275 | 11.51% |  |  | 2/8-11/8 | 12/08-18/08 | 19/08-25/08 | [8 empty] | total
plānotā peļņa | planned profit |  |  |  |  | 13176.55 | 22.33% | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
[8 empty] | planned | 11.9204 | 1333.3333 | 1333.3333 | 1333.3333 | [8 empty] | 4000
Direct costs | actual costs | planned costs | [5 empty] | in fact | 15.292 | 4239.68 | [10 empty] | 4239.68
Materials, incl.delivery, and subcontractors | 49.2% | 15.59% | [5 empty] | m2 costs | 326.268
Salaries and taxes | 38.82% | 28.88%
Other costs | 11.99% | 55.63% | [5 empty] | travel and living costs
[8 empty] | planned | 4000
[8 empty] | in fact | 4239.68
[8 empty] | living costs per worked hour | 4.4698
Subcontractors budget, EUR
[8 empty] | Payments to subcontractor, EUR | 19770.33
date of report
2024-10-10
|  | avansi | 1254.7
|  | Megie | 200
|  | Buchl | 1054.7

## LULU2
LULU2 | lululemon , Existing Store Demolition Works, 08/07-22/07
Object costs
|  | Jūlijs |  | Novembris |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 12910 |  | 11947.66 |  | 24857.66 |  | Contract amount EUR | 12910 | 08/07-14/07 | 15/07-21/07 | [9 empty] | total |  | total
Objekta tiešie izdevumi | Direct costs | 7479.4685 |  | 8177.4231 |  | 15656.8916 |  | Additional works, EUR | 11947.66 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | 11
materiālu un aprīkojuma iegāde | materials and equipment |  | 1985.9996 | 7341.0869 | 7341.0869 | 7341.0869 | 9327.0866 | square m2 |  | 08/07-14/07 1: 0; 15/07-21/07 2: 0; 15/07-21/07 3: 0; 15/07-21/07 4: 0
materiālu piegādes izdevumi | delivery |  |  |  |  | 0 |  | object square | hours optimal/ m2 | 08/07-14/07 1: 200.75 | 200.75 |  | 200.75
apakšuzņēmēji | subcontractors | 1985.9996 |  |  |  | 1985.9996 |  | m2<50 | 13
darba algas | salaries | 1755.12 | 4796.385 |  | 836.3362 | 1755.12 | 5632.7212 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 414.0328 |  | 0 |  | 414.0328
uzkrājums atvaļinājumam | vacation allowance | 173.5322 |  | 0 |  | 173.5322 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 903.7 |  | 836.3362 |  | 1740.0362 |  | planned
komandējuma dienas naudas | travel allowance | 1550 |  |  |  | 1550 |  | in fact | 7341.0869
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 697.0838 | 697.0838 |  | 0 | 697.0838 | 697.0838
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) |  |  |  |  | 0 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) |  |  |  |  | 0 |  | planned
citi izdevumi | other expenses |  |  |  |  | 0 |  | in fact | 3892.685
[8 empty] | hours cost in fact | 19.3907 | 08/07-14/07 1: travel and living costs
peļņa bruto | profit/ loss | 5430.5315 | 42.06% | 3770.2369 | 31.56% | 9200.7684 | 37.01% |  |  | 08/07-14/07 1: 09/09-15/09; 15/07-21/07 2: 16/09-22/09 | total |  | total
plānotā peļņa | planned profit | [5 empty] | 0% | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | 11
[8 empty] | planned | #REF! | 09/09-15/09 1: #REF!; 16/09-22/09 2: #REF!; 16/09-22/09 3: #REF!; 16/09-22/09 4: #REF! | #REF! |  | #REF!
Direct costs | actual costs | planned costs | [5 empty] | in fact | #REF! | 09/09-15/09 1: 697.0838 | 697.0838 |  | 697.0838
Materials, incl.delivery, and subcontractors | 59.57% | [6 empty] | m2 costs | #REF!
Salaries and taxes | 35.98%
Other costs | 4.452% | [6 empty] | travel and living costs
[8 empty] | planned | #REF!
[8 empty] | in fact | #REF!
[8 empty] | living costs per worked hour | #REF!
Subcontractors budget, EUR
[8 empty] | Payments to subcontractor, EUR | 1985.9996
date of report
2024-12-02
Buildup rēķini | nr. | SEK | EUR | 11.54 |  | 11.419
Big BAg | 149296691 | 2150.04 | 188.2862
| 149402893 | 16495.09 | 1444.5302
0
Easy Flat | 46008 | 7960 | 697.0838
0
Lantz | 182333111606229 | 4033 | 353.1833
Artel | 34746 |  | 54600
Cramo | 11858599 |  | 12458.16
Stromfeldt | 2414 |  | 4800
|  |  | 71858.16 | 6226.8769
Note on K5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11/2024

## LIN
LIN | Intimissimi Landstraße 9, 4020 Linz, Austria , 09/09/2024-(22)25/09/2024
Object costs
|  | Septembris |  |  |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 55000 |  |  |  | 55000 |  | Contract amount EUR | 55000 | 09/09-15/09 | 16/09-22/09 | 23/09-25/09 | [8 empty] | total
Objekta tiešie izdevumi | Direct costs | 43039.989 |  | 0 |  | 43039.989 |  | Additional works, EUR |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 2898.17 | 7336.39 |  | 0 | 2898.17 | 7336.39 | square m2 | 96.48 | 09/09-15/09 1: 340; 16/09-22/09 2: 340 | 680
materiālu piegādes izdevumi | delivery | 453.62 |  |  |  | 453.62 |  | object square | hours optimal/ m2 | 09/09-15/09 1: 211.52; 16/09-22/09 2: 269.38; 23/09-25/09 3: 117.88 | 598.78
apakšuzņēmēji | subcontractors | 3984.6 |  |  |  | 3984.6 |  | m2<50 | 13
darba algas | salaries | 14806.1909 | 27862.889 |  | 0 | 14806.1909 | 27862.889 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 3492.7804 |  | 0 |  | 3492.7804
uzkrājums atvaļinājumam | vacation allowance | 1463.9177 |  | 0 |  | 1463.9177 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 3850 |  | 0 |  | 3850 |  | planned | 6238.99
komandējuma dienas naudas | travel allowance | 4250 |  |  |  | 4250 |  | in fact | 3351.79
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2777.73 | 7840.71 |  | 0 | 2777.73 | 7840.71
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1249.92 |  |  |  | 1249.92 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | 1376.72 |  |  |  | 1376.72 |  | planned | 17771.54
citi izdevumi | other expenses | 3813.06 |  |  |  | 3813.06 |  | in fact | 24012.889
[8 empty] | hours cost in fact | 40.103 | 09/09-15/09 1: travel and living costs
peļņa bruto | profit/ loss | 11960.011 | 21.75% | 0 | #DIV/0! | 11960.011 | 21.75% |  |  | 09/09-15/09 1: 09/09-15/09; 16/09-22/09 2: 16/09-22/09; 23/09-25/09 3: 23/09-25/09 | total
plānotā peļņa | planned profit |  |  |  |  | 12652.31 | 23% | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
[8 empty] | planned | 7.0481 | 09/09-15/09 1: 2400; 16/09-22/09 2: 2400 | 4800
Direct costs | actual costs | planned costs | [5 empty] | in fact | 6.2063 | 09/09-15/09 1: 2913; 16/09-22/09 2: 241.92; 23/09-25/09 3: 872.73 | 4027.65
Materials, incl.delivery, and subcontractors | 17.05% | 14.73% | [5 empty] | m2 costs | 248.8898
Salaries and taxes | 64.74% | 41.97%
Other costs | 18.22% | 43.7% | [5 empty] | travel and living costs
[8 empty] | planned | 4800
[8 empty] | in fact | 4027.65
[8 empty] | living costs per worked hour | 4.639
Subcontractors budget, EUR
[8 empty] | Payments to subcontractor, EUR | 3984.6
date of report
2024-11-08
avansi
|  | WTW konteiners | 348.01

## WIE
WIE | Calzedonia SC Fischapark, Zehnergürtel 12/24, 2700 Wiener Neustadt, Austria, 19/08-1/09
Object costs
|  | Augusts |  | Septembris |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 19500 |  | 19500 |  | 39000 |  | Contract amount EUR | 39000 | 19/08-25/08 | 26/08-01/09 | 02/09-8/09 | 9/09-15/09 | [7 empty] | total
Objekta tiešie izdevumi | Direct costs | 20702.3476 |  | 8136.69 |  | 28839.0376 |  | Additional works, EUR |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 2337.93 | 7165.49 |  | 5792.69 | 2337.93 | 12958.18 | square m2 | 73.59 | 19/08-25/08 1: 187.875; 26/08-01/09 2: 187.875 | 375.75
materiālu piegādes izdevumi | delivery | 160.56 |  | 1820 |  | 1980.56 |  | object square | hours optimal/ m2 | 19/08-25/08 1: 145.57; 26/08-01/09 2: 94.9 | 240.47 | 135.28
apakšuzņēmēji | subcontractors | 4667 |  | 3972.69 |  | 8639.69 |  | m2<50 | 13
darba algas | salaries | 4869.961 | 9515.2876 |  | 1815 | 4869.961 | 11330.2876 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 1148.8238 |  | 0 |  | 1148.8238
uzkrājums atvaļinājumam | vacation allowance | 481.5028 |  | 0 |  | 481.5028 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 1365 |  | 1365 |  | 2730 |  | planned | 3244.78
komandējuma dienas naudas | travel allowance | 1650 |  | 450 |  | 2100 |  | in fact | 4318.49
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2010.89 | 4021.57 | 258 | 529 | 2268.89 | 4550.57 | [15 empty] | 2546.48
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 172.59 |  | 105 |  | 277.59 |  | Salaries and taxes | [14 empty] | 10.5896
komandējuma izdevumi (administrācija) | travel expenses (administration) |  |  |  |  | 0 |  | planned | 10685.56
citi izdevumi | other expenses | 1838.09 |  | 166 |  | 2004.09 |  | in fact | 8600.2876
[8 empty] | hours cost in fact | 35.7645
peļņa bruto | profit/ loss | -1202.3476 | -6.166% | 11363.31 | 58.27% | 10160.9624 | 26.05% |  |  | 19/08-25/08 1: travel and living costs
plānotā peļņa | planned profit |  |  |  |  | 8874.86 | 22.76% | hours per m2 |  | 19/08-25/08 1: 19/08-25/08; 26/08-01/09 2: 26/08-01/09; 02/09-8/09 3: 02/09-8/09; 9/09-15/09 4: 9/09-15/09; 9/09-15/09 5: 25/09-01/10; 9/09-15/09 6: 02/10-06/10 | total
[8 empty] | planned | 5.106 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Direct costs | actual costs | planned costs | [5 empty] | in fact | 3.2677 | 1: 1900; 2: 1900 | 3800
Materials, incl.delivery, and subcontractors | 44.93% | 10.77% | [5 empty] | m2 costs | 116.8676 | 1: 2183.48; 2: 363 | 2546.48
Salaries and taxes | 39.29% | 35.47%
Other costs | 15.78% | 53.76% | [5 empty] | travel and living costs
[8 empty] | planned | 3800
[8 empty] | in fact | 2546.48
[8 empty] | living costs per worked hour | 10.5896
Subcontractors budget, EUR
[8 empty] | Payments to subcontractor, EUR | 8639.69
date of report
2025-02-03
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Simone

## SEI
SEI | Intimissimi Shopping City Seiersberg, 8055 Seiersberg, Austria , 25/07/2024-25/08/2024
Object costs
|  | Jūlijs |  | Augusts |  | Septembris |  | Total |  | General data |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 24632.1 |  | 49264.2 |  |  |  | 73896.3 |  | Contract amount EUR | 68000 | Time shedule, weeks | 25/07-28/07 | 29/07-04/08 | 05/08-11/08 | 12/08-18/08 | 19/08-25/08 | 30/08-31/08 | 2024-09-01 |  |  |  |  | total
Objekta tiešie izdevumi | Direct costs | 18952.0094 |  | 39557.283 |  | 2786.5087 |  | 61295.8012 |  | Additional works, EUR | 5896.3 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 5292.31 | 6897.31 | 1328.92 | 21146.7 |  | 391.9 | 6621.23 | 28435.91 | square m2 | 53.5 |  | 1: 143.044; 2: 143.044; 3: 143.044; 4: 143.044; 5: 143.044 | 715.22
materiālu piegādes izdevumi | delivery | 1570 | [5 empty] | 1570 |  | object square | hours optimal/ m2 |  | 73 | 148 | 107.68 | 217.4 | 188.4 | 30.75 | 61 |  |  |  |  | 826.23 | ir ok, add.works
apakšuzņēmēji | subcontractors | 35 |  | 19817.78 |  | 391.9 |  | 20244.68 |  | m2<50 | 13
darba algas | salaries | 2486.846 | 6843.6194 | 4570.3978 | 14348.933 | 1606.7229 | 2394.6087 | 8663.9667 | 23587.1612 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 586.647 |  | 1078.1568 |  | 379.0259 |  | 2043.8297
uzkrājums atvaļinājumam | vacation allowance | 245.8794 |  | 451.8844 |  | 158.8599 |  | 856.6237 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 1724.247 |  | 3448.494 |  | 0 |  | 5172.741 |  | planned | 6423.92
komandējuma dienas naudas | travel allowance | 1800 |  | 4800 |  | 250 |  | 6850 |  | in fact | 8191.23
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 3148.84 | 5211.08 | 698.85 | 4061.65 |  | 0 | 3847.69 | 9272.73
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 364.93 | [5 empty] | 364.93 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | [6 empty] | 0 |  | planned | 17165.25
citi izdevumi | other expenses | 1697.31 |  | 3362.8 |  |  |  | 5060.11 |  | in fact | 18414.4202
[8 empty] | 0 |  | hours cost in fact | 22.2873
peļņa bruto | profit/ loss | 5680.0906 | 23.06% | 9706.917 | 19.7% | -2786.5087 | #DIV/0! | 12600.4988 | 17.05%
plānotā peļņa | planned profit | [6 empty] | 15140.82 | 22.27% | hours per m2
[10 empty] | planned | 13.3686 | Object address | 1: travel and living costs
Direct costs | actual costs | planned costs | [7 empty] | in fact | 15.4436 | Time shedule, weeks | 1: 25/07-28/07; 2: 29/07-04/08; 3: 05/08-11/08; 4: 12/08-18/08; 5: 19/08-25/08 | total
Materials, incl.delivery, and subcontractors | 46.39% | 12.15% | [7 empty] | m2 costs | 344.1948 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 38.48% | 32.47% | [10 empty] | 1: 740; 2: 740; 3: 740; 4: 740; 5: 740 | 3700
Other costs | 15.13% | 55.37% | [7 empty] | travel and living costs |  |  | 1: 257.85; 2: 3255.9; 5: 698.85 | 4212.6
[10 empty] | planned | 3700
[10 empty] | in fact | 4212.6
[10 empty] | living costs per worked hour | 5.0986
Subcontractors budget, EUR
[10 empty] | Payments to subcontractor, EUR | 20244.68
date of report
2024-10-10

## KRE
KRE | Calzedonia restyling Obere Landstrasse 6, Krems, Austria, 26/08-08/09
Object costs
|  | Augusts |  | Septembris |  |  |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 20000 |  | 20000 |  |  |  | 40000 | 0 | Contract amount EUR | 40000 | 26/08-01/09 | 02/09-08/09 | 05/09-07/09 | [8 empty] | total
Objekta tiešie izdevumi | Direct costs | 13937.932 |  | 13676.2395 |  | 0 |  | 27614.1715 |  | Additional works, EUR |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 3248.29 | 5839.89 | 199.82 | 6035.7 |  | 0 | 3448.11 | 11875.59 | square m2 | 73.18 | 26/08-01/09 1: 181.5; 02/09-08/09 2: 181.5; 05/09-07/09 3: 181.5; 05/09-07/09 4: 90.75 | 363
materiālu piegādes izdevumi | delivery | [6 empty] | 0 |  | object square | hours optimal/ m2 | 26/08-01/09 1: 190.15; 02/09-08/09 2: 210.32 | 400.47
apakšuzņēmēji | subcontractors | 2591.6 |  | 5835.88 |  |  |  | 8427.48 |  | m2<50 | 13
darba algas | salaries | 2039.5034 | 5472.272 | 2425.4026 | 6037.3595 |  | 0 | 4464.906 | 11509.6315 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 481.1189 |  | 572.1525 |  | 0 |  | 1053.2713
uzkrājums atvaļinājumam | vacation allowance | 201.6498 |  | 239.8044 |  | 0 |  | 441.4542 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 1400 |  | 1400 |  | 0 |  | 2800 |  | planned | 122603.78
komandējuma dienas naudas | travel allowance | 1350 |  | 1400 |  |  |  | 2750 |  | in fact | 3448.11
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 1432.25 | 2625.77 | 0 | 1603.18 | 0 | 0 | 1432.25 | 4228.95
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) |  |  | 126.32 |  |  |  | 126.32 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | [6 empty] | 0 |  | planned | 9194.43
citi izdevumi | other expenses | 1193.52 |  | 1476.86 |  |  |  | 2670.38 |  | in fact | 8709.6315
peļņa bruto | profit/ loss | 6062.068 | 30.31% | 6323.7605 | 31.62% | 0 | #DIV/0! | 12385.8285 | 30.96% | hours cost in fact | 21.7485 | 26/08-01/09 1: travel and living costs
plānotā peļņa | planned profit | [6 empty] | 8675.87 | 21.69% |  |  | 26/08-01/09 1: 26/08-01/09; 02/09-08/09 2: 02/09-08/09; 05/09-07/09 3: 05/09-07/09 | total
[10 empty] | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Direct costs | actual costs | planned costs | [7 empty] | planned | 4.9604 | 26/08-01/09 1: 2400; 02/09-08/09 2: 2400; 05/09-07/09 3: 2400; 05/09-07/09 4: 1200 | 4800
Materials, incl.delivery, and subcontractors | 43.01% | 12.02% | [7 empty] | in fact | 5.4724 | 26/08-01/09 1: 1432.25; 02/09-08/09 2: 126.32 | 1558.57
Salaries and taxes | 41.68% | 29.35% | [7 empty] | m2 costs | 119.0166
Other costs | 15.31% | 58.63%
travel and living costs
[10 empty] | planned | 4800
[10 empty] | in fact | 1558.57
[10 empty] | living costs per worked hour | 3.8919
Subcontractors budget, EUR
[10 empty] | Payments to subcontractor, EUR | 8427.48
date of report
2025-02-03

## STK
STK | Stockholm, Calzedonia and Intimissimi 22/04-28/04/2024
Object costs
|  | Aprīlis |  |  |  | Novembris |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 7504.45 |  | 0 |  |  |  | 7504.45 | 0 | Contract amount EUR | 7504.45 | 22/04-28/04 | 11/09-17/09 | 18/09-24/09 | 25/09-01/10 | 02/10-06/10 | 2023-11-01 | [5 empty] | total
Objekta tiešie izdevumi | Direct costs | 6950.313 |  | 0 |  | 0 |  | 6950.313 |  | Additional works, EUR |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 861.71 | 861.71 |  | 0 |  | 0 | 861.71 | 861.71 | square m2 |  | 1: 0; 2: 0; 3: 0; 4: 0
materiālu piegādes izdevumi | delivery | [6 empty] | 0 |  | object square | hours optimal/ m2 | 1: 87.79 | 87.79
apakšuzņēmēji | subcontractors | [6 empty] | 0 |  | m2<50 | 13
darba algas | salaries | 1586.0548 | 3692.333 |  | 0 |  | 0 | 1586.0548 | 3692.333 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 374.1503 |  | 0 |  |  |  | 374.1503
uzkrājums atvaļinājumam | vacation allowance | 156.8164 |  | 0 |  |  |  | 156.8164 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 525.3115 |  | 0 |  |  |  | 525.3115 |  | planned
komandējuma dienas naudas | travel allowance | 1050 | [5 empty] | 1050 |  | in fact | 861.71
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 766.52 | 2396.27 |  | 0 |  | 0 | 766.52 | 2396.27
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1540.34 | [5 empty] | 1540.34 |  | Salaries and taxes
komandējuma izdevumi- administrācija | travel expenses (administration) | [6 empty] | 0
citi izdevumi | other expenses | 89.41 | [5 empty] | 89.41 |  | planned
peļņa bruto | profit/ loss | 554.137 | 7.384% | 0 | #DIV/0! | 0 | #DIV/0! | 554.137 | 7.384% | in fact | 3167.0215
[10 empty] | hours cost in fact | #DIV/0! | 1: travel and living costs
Direct costs | % | [10 empty] | 1: 22/04-28/04; 2: 11/09-17/09; 3: 18/09-24/09; 4: 25/09-02/10; 5: 02/10-06/10; 6: 2023-11-01 | total
Materials, incl.delivery, and subcontractors | 12.3981 | [8 empty] | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 53.1247 | [8 empty] | planned | #DIV/0! | 1: 0; 2: 0; 3: 0; 4: 0
Other costs | 34.4772 | [8 empty] | in fact | #DIV/0! | 1: 2306.86 | 2306.86
[10 empty] | m2 costs | #DIV/0! | bar: 2
travel and living costs
planned
[10 empty] | in fact | 2306.86
[10 empty] | living costs per worked hour | #DIV/0!
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-05-07

## LULU
LULU | lululemon store Biblioteksgatan nr. 9, 11146 Stockholm, Sweden 06/05/2024-28/06/2024
Object costs
|  | Maijs |  | Jūnijs |  | Jūlijs |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 315236.04 |  | 315236.04 |  | 441330.456 |  | 630472.08 | 0 | Contract amount EUR | 630472.08 | 06/05-12/05 | 13/05-19/05 | 20/05-26/05 | 27/05-02/06 | 03/06-09/06 | 10/06-16/06 | 17/06-23/06 | 24/06-30/06 | 01/07-07/07 | 08/07-14/07 |  | total
Objekta tiešie izdevumi | Direct costs | 135618.1837 |  | 141437.4224 |  | 128675.5487 |  | 405731.1547 |  | Additional works, EUR |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 42486.9087 | 78079.436 | 48834.6354 | 63278.6909 | 11148.1816 | 86858.2833 | 102469.7257 | 228216.4102 | square m2 | 555 | 437.8712 | 437.8712 | 437.8712 | 437.8712 | 437.8712 | 437.8712 | 437.8712 | 437.8712 |  |  |  | 3502.97
materiālu piegādes izdevumi | delivery |  |  | 4360 |  | 3135 |  | 7495 |  | object square | hours optimal/ m2 | 94.58 | 362.89 | 293.38 | 391.88 | 375 | 485.8 | 485.08 | 441.48 | 306.47 | 200.75 |  | 3437.31 | 81898.1072
apakšuzņēmēji | subcontractors | 35592.5273 |  | 10084.0555 |  | 72575.1018 |  | 118251.6845 |  | m2<50 | 13 | [12 empty] | 23.8262
darba algas | salaries | 10640.06 | 43918.577 | 20087.1354 | 60778.2687 | 3840.2764 | 38419.0253 | 34567.4718 | 143115.871 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 2509.9902 |  | 4738.5552 |  | 905.9212 |  | 8154.4666 | 68089.6935 | [14 empty] | 87120.4138
uzkrājums atvaļinājumam | vacation allowance | 1052.004 |  | 1986.0553 |  | 379.6958 |  | 3417.7551 |  | materials and equipment costs | [13 empty] | 25.3455
administratīvie izdevumi 7% | administrative costs 7% | 22066.5228 |  | 22066.5228 |  | 30893.1319 |  | 75026.1775 |  | planned | 122603.78
komandējuma dienas naudas | travel allowance | 7650 |  | 11900 |  | 2400 |  | 21950 |  | in fact | 109964.7257
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2740.4679 | 13620.1707 | 6872.9258 | 17380.4628 |  | 3398.24 | 9613.3938 | 34398.8735
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 636.28 |  | 1742.71 |  | 1816.03 |  | 4195.02 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | 4343.44 |  | 2225.66 |  | 917.42 |  | 7486.52 |  | planned | 126505.68
citi izdevumi | other expenses | 5899.9828 |  | 6539.167 |  | 664.79 |  | 13103.9398 |  | in fact | 68089.6935
peļņa bruto | profit/ loss | 179617.8563 | 56.98% | 173798.6176 | 55.13% | 312654.9073 | 70.84% | 224740.9253 | 35.65% | hours cost in fact | 19.809
plānotā peļņa | planned profit | [6 empty] | 330625.08 | 52.44%
[10 empty] | hours per m2 |  | 1: travel and living costs
Direct costs | actual costs | planned costs | [7 empty] | planned | 6.3117 | 02/05-12/05 | 13/05-19/05 | 20/05-26/05 | 27/05-02/06 | 03/06-09/06 | 10/06-16/06 | 17/06-23/06 | 24/06-28/06 | 01/07-07/07 | 08/07-14/07 |  | total
Materials, incl.delivery, and subcontractors | 56.25% | 42.19% | [7 empty] | in fact | 6.1934 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 35.27% | 40.89% | [7 empty] | m2 costs | 122.6841 | 1912.5 | 1912.5 | 1912.5 | 1912.5 | 1912.5 | 1912.5 | 1912.5 | 1912.5 |  |  |  | 15300
Other costs | 8.478% | 16.92% | [9 empty] | 3313.4279 |  | 3351.8815 |  | 1337.52 | 2190.7 | 427.16 | 273.4 | 133.42 | 1612.48 |  | 12639.9895
travel and living costs
[10 empty] | planned | 15300
[10 empty] | in fact | 13808.4138
[10 empty] | living costs per worked hour | 4.0172
[10 empty] | Subcontractors budget, EUR | 201713.27
[10 empty] | Payments to subcontractor, EUR | 118251.6845
date of report
2024-09-12
|  | 30% | 60% | 10%
Contract amount SEK | 7883509.39 | 2365052.82 | 4730105.63 | 788350.94
exchange rate | 11.639
Contract amount EUR | 677335.63 | 203200.69 | 406401.38 | 67733.56
| 679584.08 | 203875.22 | 203875.22 | 203875.22 | 67958.42 |  |  | 679584.08
|  |  |  | 2.5% | 16989.6 |  |  | garantijas ieturējums
|  |  |  | 7.5% | 50968.82 |  |  | pēdējais maksājums
Buildup rēķini | nr. | SEK | EUR | 11.54 | [5 empty] | Iemaksātie avansi, gaidām preci
EasyFlat, dzīvošana 05 | 103506 | 31625 | 2740.4679 | [6 empty] | Produs
EasyFlat, dzīvošana 06 | 45479 | 37950 | 3288.5615 | [6 empty] | Kondair
EasyFlat, dzīvošana 07 | 45701 | 5060 | 438.4749 | [6 empty] | AJ Produkti
EasyFlat, dzīvošana 07 | 45874 | 22885 | 1983.1023 | [6 empty] | Salons Objekts
| 46009 | 12650 | 1096.1872 | 9546.7938 | [5 empty] | Stokker
SGM
High Competent Sweden AB | 6927 | 20000 | 1733.1023 | [7 empty] | 0
Artel AB, elektriķi 05 | 34659 | 158460 | 13731.3692
Artel AB, elektriķi 07 | 34678 | 50000 | 4332.7556
| 34680 | 10000 | 866.5511
Artel AB, elektriķi | 34683 | 263000 | 22790.2946
Motala, līgumssumma | 2024-05-08 | 250000 | 21663.7782
Strömfeldt Projektpartner AB | 2024-02-06 | 8000 | 693.2409
Strömfeldt Projektpartner AB | 2408/9 | 4800 | 415.9445
tretum |  | 5170 | 448.0069
BST sprinkleri | 92403721 | 257550 | 22318.0243
BST Brandskyddsteamet AB | 92404436 | 171450 | 14857.0191
Babbis Panagiotidis | 6297 | 20000 | 1733.1023
Larm Teletjanst | 23002 | 50000 | 4332.7556
Larm Teletjanst | 23155 | 4500 | 389.948
Larm Teletjanst | 1963-01-21 | 53200 | 4610.052 | 114915.9445
Optimera | 6759525-00 | 26229.32 | 2272.9047
| 69726354 | 1121.26 | 97.1629
| 69516680 | 1754.81 | 152.0633
| 69494797 | 716.32 | 62.0728
| 69452902 | 1324 | 114.7314
| 69452910 | 31830.27 | 2758.2556
| 69378826 | 1374.74 | 119.1282
| 69317709 | 1893.53 | 164.0841
| 69282242 | 20555.29 | 1781.221
| 69207942 | 1118.84 | 96.9532
| 69207959 | 28776.76 | 2493.6534
| 69188175 | 891.12 | 77.2201
| 69169027 | 52889.82 | 4583.1733
| 69118693 | 438.48 | 37.9965
| 69024412 | 15765.75 | 1366.1828
BigBag | 146647698 | 4135 | 358.3189
| 146484993 | 3090.08 | 267.7712
| 146913496 | 7939.06 | 687.9601
| 147421994 | 3129 | 271.1438
| 147277891 | 2244 | 194.4541
weDRAW AB | 240-4 | 27300 | 2365.6846
| 11591517 | 1934.56 | 167.6395
Cramo | 11605740 | 20264.56 | 1756.0277
Stockholms Stadt | 8500032230 | 1600 | 138.6482 | 6351.8198
| 2024-05-01 |  | 22245.8033 | 50851.5503
Optimera | 69844058 | 2427.59 | 210.3631 | 174802.398 | Buildup apmaksātie rēķini
| 69862811 | 14494.87 | 1256.0546 | 168554.4 | Buildup samaksāts
| 69954832 | 77933.7 | 6753.3536 | -6247.998
| 69935476 | 32215.41 | 2791.63
| 10124972 | 773.79 | 67.0529
| 10188738 | 1637.05 | 141.8588
| 10341782 | 1809.28 | 156.7834
| 10496925 | 52805.85 | 4575.8969
Flakt group | 407356858 | 20745 | 1797.6603
Ikea | 21102056283 | 12716.8 | 1101.9757
Cramo | 11647878 | 9101.28 | 788.6724
| 11617937 | 8149 | 706.1525
| 11626598 | 8107 | 702.513
BigBag | 147801898 | 2240 | 194.1075
| 147703896 | 2805 | 243.0676
| 147926398 | 2150.04 | 186.312
| 148268097 | 9900.03 | 857.8882
| 148454697 | 1595 | 138.2149
| 148582398 | 6759.05 | 585.7062
| 148653991 | 3487.01 | 302.1672
Bevego | 11704661 | 6567.06 | 569.0693
| 11706100 | 541.75 | 46.9454
weDRAW AB | 2402 | 27300 | 2365.6846
Stockholm Stadt | 8100062849 | 17100 | 1481.8024
| 2024-06-24 |  | 24173.4454
Stromfeldt | 2407/9 | 6400 | 554.5927
Optimera | 10585784 | 523.83 | 45.3925
| 10568293 | 3650.04 | 316.2946
| 10828523 | 593.57 | 51.4359
0
0
0
0
0
BigBag | 149008997 | 9685.06 | 839.26
| 149161499 | 6077.04 | 526.6066
| 149518698 | 7414.01 | 642.4619
| 147703896 | 2805 | 243.0676
| 10601979 | 787.61 | 68.2504
0
Bevego | 11715469 | 8763.6 | 759.4107
| 11714562 | 741 | 64.2114
| 11922068 | 3708 | 321.3172
| 2024-07-24 |  | 4432.3016 | 50851.5503
|  |  | 216172.8787 | 104250.7403
163401.8102

## FRA
FRA | Stenders store construction, Main-Taunus-Zentrum 1, 65843 Sulzbach (Taunus), Vācija, 15.05.2024-7.07.2024, 08.08.2024-15.08.2024
Object costs
|  | Maijs 2024 |  | Jūnijs 2024 |  | Jūlijs 2024 |  | Augusts |  | Septembris |  | Oktobris |  | Novembris |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 109865.0175 |  | 36621.6725 |  | 11376.66 |  | 1825.8 |  | 8066.3 |  | 4330.85 |  |  |  | 172086.3 |  | Contract amount EUR | 119402.13 | 15/05-19/05 | 20/05-26/05 | 27/05-02/06 | 03/06-07/06 | 10/06-16/06 | 17/06-23/06 | 24/06-30/06 | 01/07-07/07 | 08/07-14/07 | augusts | septembris | oktobris | total
Objekta tiešie izdevumi | Direct costs | 33204.9291 |  | 36213.2483 |  | 13896.5145 |  | 50774.4881 |  | 6787.7573 |  | 5174.8371 |  | 0 |  | 146051.7743 |  | Additional works, EUR | 52684.17 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 10230.35 | 11420.35 | 5225 | 17539.57 | 488.47 | 4778.74 | 1007.98 | 41283.37 | 254.8 | 5138.36 | 336.85 | 3520.89 |  | 0 | 17543.45 | 83681.28 | square m2 | 138.3 | 1: 226.1475; 2: 226.1475; 3: 226.1475; 4: 226.1475 |  | 904.59
materiālu piegādes izdevumi | delivery | 390 |  | 665.97 | [11 empty] | 1055.97 |  | object square | hours optimal/ m2 |  | 137.66 | 164.37 | 149.03 | 30.73 | 8.87 | 108.45 | 166.7 | 28.52 | 233.3 | 7.5 | 41.07 | 1076.2
apakšuzņēmēji | subcontractors | 800 |  | 11648.6 |  | 4290.27 |  | 40275.39 |  | 4883.56 |  | 3184.04 |  |  |  | 65081.86 |  | m2<50 | 13
darba algas | salaries | 4090.24 | 15350.0891 | 4638.501 | 13004.8583 | 3295.82 | 7195.5345 | 3778.8117 | 7121.6581 | 99.4 | 847.3173 | 477.3756 | 1240.3471 |  | 0 | 16380.1483 | 44759.8043 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 964.8876 |  | 1094.2224 |  | 777.4839 |  | 891.4217 |  | 23.4485 |  | 112.6129 |  | 0 |  | 3864.077
uzkrājums atvaļinājumam | vacation allowance | 404.4102 |  | 458.6179 |  | 325.8643 |  | 373.6187 |  | 9.8279 |  | 47.1991 |  | 0 |  | 1619.538 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 7690.5512 |  | 2563.5171 |  | 796.3662 |  | 127.806 |  | 564.641 |  | 303.1595 |  | 0 |  | 12046.041 |  | planned | 24441.7
komandējuma dienas naudas | travel allowance | 2200 |  | 4250 |  | 2000 |  | 1950 |  | 150 |  | 300 |  |  |  | 10850 |  | in fact | 18599.42
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 3428.35 | 6434.49 | 2480.95 | 5668.82 | 1214.14 | 1922.24 | 1696.4 | 3643.33 | 208 | 1186.57 | 346 | 1111.55 |  | 0 | 9373.84 | 19967
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1392.93 |  | 1481.38 | [5 empty] | 278.99 | [5 empty] | 3153.3 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) |  |  |  |  | 0 |  | 1273.87 |  | 384.49 |  | 697.95 |  |  |  | 2356.31
citi izdevumi | other expenses | 1613.21 |  | 1706.49 |  | 708.1 |  | 673.06 |  | 315.09 |  | 67.6 |  |  |  | 5083.55 |  | planned | 23617.58
peļņa bruto | profit/ loss | 76660.0884 | 69.78% | 408.4242 | 1.115% | -2519.8545 | -22.15% | -48948.6881 | -2681% | 1278.5427 | 15.85% | -843.9871 | -19.49% | 0 | #DIV/0! | 26034.5257 | 15.13% | in fact | 32713.7633
plānotā peļņa | planned profit | [14 empty] | 27167.83 | 22.75% | hours cost in fact | 30.3975
travel and living costs
Direct costs | actual costs | planned costs | [15 empty] | hours per m2 |  | 15/05-19/05 | 20/05-26/05 | 27/05-02/06 | 03/06-07/06 | 10/06-16/06 | 17/06-23/06 | 24/06-30/06 | 01/07-07/07 | 08/07-14/07 | augusts | septembris |  | total
Materials, incl.delivery, and subcontractors | 12.73% | 25.61% | [15 empty] | planned | 6.5408 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 30.65% | 26.5% | [15 empty] | in fact | 7.7816 | 1: 1500; 2: 1500; 3: 1500; 4: 1500 |  | 6000
Other costs | 58.23% | 47.89% | [15 empty] | m2 costs | 236.542 | 1: 4667.3; 3: 153.98; 4: 810.49; 6: 3151.84; 8: 1214.14; 10: 1667.43 |  | 11665.18
travel and living costs
[18 empty] | planned | 6000
[18 empty] | in fact | 12527.14
[18 empty] | living costs per worked hour | 11.6402
Subcontractors budget, EUR
[18 empty] | Payments to subcontractor, EUR | 65081.86
date of report
2024-12-10
|  |  | 30% | 60% | 10%
| FR_2024-04-1 | 119402.13 | 35820.64 | 71641.28 | 11940.21
+PVN
5 darba dienas

## OLA
OLA | Sinsay store ShC OLANIJA, located in Zeiferta street 6, Olaine, Latvia, LV-2114, 15/04/2024-14/06/2024
Object costs
|  | Aprīlis |  | Maijs |  | Jūnijs |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 32727.7625 |  | 65455.525 |  | 32727.7625 |  | 130911.05 |  | Contract amount EUR | 129183.05 | 15/04-21/04 | 22/04-28/04 | 29/04-05/05 | 06/05-12/05 | 13/05-19/05 | 20/05-26/05 | 27/05-02/06 | 03/06-07/06 | 08/06-14/06 |  |  | total
Objekta tiešie izdevumi | Direct costs | 18285.3526 |  | 27893.5911 |  | 72768.763 |  | 118947.7067 |  | Additional works, EUR | 1728 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 9375.2 | 9792.55 | 5417.24 | 8849.31 | 1146.74 | 65707.66 | 15939.18 | 84349.52 | square m2 | 600.6 | 126.6122 | 126.6122 | 126.6122 | 126.6122 | 126.6122 | 126.6122 | 126.6122 | 126.6122 | 126.6122 |  |  | 1139.51
materiālu piegādes izdevumi | delivery |  |  | 80 |  |  |  | 80 |  | object square | hours optimal/ m2 |  | 200.96 | 219.28 | 280.98 | 153.81 | 126.55 | 99.08 | 122.1 | 75.7 | 25.7 |  | 1304.16 | -164.65
apakšuzņēmēji | subcontractors | 417.35 |  | 3352.07 |  | 64560.92 |  | 68330.34 |  | m2<50 | 13
darba algas | salaries | 4284.424 | 8009.6726 | 10417.76 | 18487.2211 | 3464.9136 | 6915.813 | 18167.0976 | 33412.7067 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 1010.6956 |  | 2457.5496 |  | 817.3731 |  | 4285.6183
uzkrājums atvaļinājumam | vacation allowance | 423.6096 |  | 1030.0248 |  | 342.5829 |  | 1796.2173 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 2290.9434 |  | 4581.8868 |  | 2290.9434 |  | 9163.7735 |  | planned | 16356.41
komandējuma dienas naudas | travel allowance | [6 empty] | 0 |  | in fact | 16019.18
komandējuma izdevumi- naktsmītne | travel expenses (hotels) |  | 483.13 | 45 | 557.06 | 60 | 145.29 | 105 | 1185.48
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 100 | [5 empty] | 100 |  | Salaries and taxes
citi izdevumi | other expenses | 383.13 |  | 512.06 |  | 85.29 |  | 980.48 |  | planned | 23929.69
[10 empty] | in fact | 24248.9332
peļņa bruto | profit/ loss | 14442.4099 | 44.13% | 37561.9339 | 57.39% | -40041.0005 | -122.3% | 11963.3433 | 9.139% | hours cost in fact | #DIV/0!
plānotā peļņa | planned profit | [6 empty] | 17838.07 | 13.81%
[10 empty] | hours per m2 |  | 1: travel and living costs
Direct costs | actual costs | planned costs | [7 empty] | planned | 1.8973 | 15/04-21/04 | 22/04-28/04 | 29/04-05/05 | 06/05-12/05 | 13/05-19/05 | 20/05-26/05 | 27/05-02/06 | 03/06-07/06 | 08/06-14/06 |  |  | total
Materials, incl.delivery, and subcontractors | 13.47% | 14.69% | [7 empty] | in fact | 2.1714 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 28.09% | 21.49% | [7 empty] | m2 costs | #DIV/0! | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0
Other costs | 58.44% | 63.82% | [9 empty] | 7: 45 | 45
travel and living costs
[10 empty] | planned | 0
[10 empty] | in fact | 0
[10 empty] | living costs per worked hour | #DIV/0!
[10 empty] | Subcontractors budget, EUR | 66858.34
[10 empty] | Payments to subcontractor, EUR | 68330.34
date of report
2024-06-27
Avansi apakšuzņēmējiem
[6 empty] | ElektroLAt | 1272.24
[6 empty] | Ekosilti | 13414.86

## MAT
MAT | Matrožu iela 15, Rīga, 04/04/2024-30/05/2024, 14/06/2024-?
Object costs
|  | Aprīlis |  | Maijs |  | Jūnijs |  | Jūlijs |  | Augusts |  | Septembris |  | Total |  | General data |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 20405.59 |  | 25869.88 |  | 3456.89 |  | 6508.45 |  | 28068.3 |  | 3839.14 |  | 88148.25 |  | Contract amount EUR | 40811.18 | Time shedule, weeks | 04/04-14/04 | 15/04-21/04 | 22/04-28/04 | 29/04-05/05 | 06/05-12/05 | 13/05-19/05 | 20/05-26/05 | 27/05-30/05 | 14/06-23/06 | 24/06-30/06 |  | total
Objekta tiešie izdevumi | Direct costs | 17675.3423 |  | 22444.9956 |  | 6765.9834 |  | 2621.7121 |  | 10464.101 |  | 14470.4598 |  | 74442.5942 |  | Additional works, EUR | 47337.07 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 8661.27 | 8877.37 | 131.19 | 19945.94 | 2506.3 | 2702.44 |  | 1838.41 | 66.92 | 8347.04 | 789.21 | 14201.72 | 12154.89 | 55912.92 | square m2 |  |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 |  |  |  | 560
materiālu piegādes izdevumi | delivery | [12 empty] | 0 |  | object square | hours optimal/ m2 |  | 156.2 | 146.39 | 17.45 |  |  | 26.5 |  |  | 117 | 72.72 | 18.2 | 554.46
apakšuzņēmēji | subcontractors | 216.1 |  | 19814.75 |  | 196.14 |  | 1838.41 |  | 8280.12 |  | 13412.51 |  | 43758.03 |  | m2<50 | 13
darba algas | salaries | 5292.4252 | 8492.5723 | 364.23 | 2297.0556 | 2728.317 | 3883.6634 | 245.518 | 783.3021 |  | 1964.781 |  | 268.7398 | 8630.4902 | 17690.1142 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 1248.4831 |  | 85.9219 |  | 643.61 |  | 57.9177 |  | 0 |  | 0 |  | 2035.9326
uzkrājums atvaļinājumam | vacation allowance | 523.2727 |  | 36.0121 |  | 269.7542 |  | 24.2749 |  | 0 |  | 0 |  | 853.3138 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 1428.3913 |  | 1810.8916 |  | 241.9823 |  | 455.5915 |  | 1964.781 |  | 268.7398 |  | 6170.3775 |  | planned | 2498.17
komandējuma dienas naudas | travel allowance | [12 empty] | 0 |  | in fact | 12154.89
komandējuma izdevumi- naktsmītne | travel expenses (hotels) |  | 305.4 |  | 202 |  | 179.88 |  | 0 |  | 152.28 |  | 0 | 0 | 839.56
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | [12 empty] | 0 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | [12 empty] | 0 |  | planned | 3314.86
citi izdevumi | other expenses | 305.4 |  | 202 |  | 179.88 |  |  |  | 152.28 |  |  |  | 839.56 |  | in fact | 11519.7367
[14 empty] | 0 |  | hours cost in fact | 632.9526
peļņa bruto | profit/ loss | 2730.2477 | 13.38% | 3424.8844 | 13.24% | -3309.0934 | -95.72% | 3886.7379 | 59.72% | 17604.199 | 62.72% | -10631.3198 | -276.9% | 13705.6558 | 15.55%
plānotā peļņa | planned profit | [12 empty] | 23815 | 58.35% | hours per m2
[16 empty] | planned | #DIV/0! | Object address | 1: travel and living costs
Direct costs | actual costs | planned costs | [13 empty] | in fact | #DIV/0! | Time shedule, weeks | 04/04-14/04 | 15/04-21/04 | 22/04-28/04 | 29/04-05/05 | 06/05-12/05 | 13/05-19/05 | 20/05-26/05 | 27/05-30/05 | 14/06-23/06 | 24/06-30/06 |  | total
Materials, incl.delivery, and subcontractors | 75.11% | 35.71% | [13 empty] | m2 costs | #DIV/0! |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 23.76% | 47.38% | [27 empty] | 0
Other costs | 1.128% | 16.91% | [13 empty] | travel and living costs | [13 empty] | 0
[16 empty] | planned | 0
[16 empty] | in fact | 0
[16 empty] | living costs per worked hour | 0
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-09-20
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amross SIA Reply: Amross, GSC

## LEI
LEI | Calzedonia LEIDEN_HAARLEMERSTRAAT_114, 04/04/2024-(08/05/2024) 30/04/2024
Object costs
|  | Aprīlis |  | Jūnijs |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 72434.83 |  | 14891.4 |  | 87326.23 | 0 | Contract amount EUR | 72434.83 | 04/04-14/04 | 15/04-21/04 | 22/04-28/04 | 29/04-05/05 | 06/05-08/05 | [6 empty] | total
Objekta tiešie izdevumi | Direct costs | 74676.2725 |  | 2893.118 |  | 77569.3905 |  | Additional works, EUR | 14891.4 | 1 | 2 | 3 | 4 | 5 |  | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 22104.8 | 44965.9 | 50.23 | 1602.23 | 22155.03 | 46568.13 | square m2 | 110.76 | 168 | 168 | 168 | 168 | 168 | [6 empty] | 840
materiālu piegādes izdevumi | delivery | 2200 |  |  |  | 2200 |  | object square | hours optimal/ m2 | 300.75 | 232.63 | 199.22 | 50.72 | [7 empty] | 783.32 | 56.68
apakšuzņēmēji | subcontractors | 20661.1 |  | 1552 |  | 22213.1 |  | m2<50 | 13
darba algas | salaries | 7730.125 | 22048.3925 |  | 1042.398 | 7730.125 | 23090.7905 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 1823.5365 |  | 0 |  | 1823.5365
uzkrājums atvaļinājumam | vacation allowance | 764.2929 |  | 0 |  | 764.2929 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 5070.4381 |  | 1042.398 |  | 6112.8361 |  | planned | 11157.73
komandējuma dienas naudas | travel allowance | 6660 |  |  |  | 6660 |  | in fact | 24355.03
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 4845.23 | 7661.98 | 198 | 248.49 | 5043.23 | 7910.47
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1107.66 |  |  |  | 1107.66 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) |  |  |  |  | 0 |  | planned | 20324.98
citi izdevumi | other expenses | 1709.09 |  | 50.49 |  | 1759.58 |  | in fact | 16977.9544
[8 empty] | hours cost in fact | 21.6744
peļņa bruto | profit/ loss | -2241.4425 | -3.094% | 11998.282 | 80.57% | 9756.8395 | 11.17%
plānotā peļņa | planned profit |  |  |  |  | 23068.5 | 31.85% | hours per m2 |  | travel and living costs
[8 empty] | planned | 7.584
Direct costs | actual costs | planned costs | [5 empty] | in fact | 7.0722 | 04/04-14/04 | 15/04-21/04 | 22/04-28/04 | 29/04-05/05 | 06/05-08/05
Materials, incl.delivery, and subcontractors | 60.03% | 17.36% | [5 empty] | m2 costs | 153.286 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 29.77% | 31.63% | [7 empty] | 1: 1040; 2: 1040; 3: 1040; 4: 1300; 5: 1040 | 5200
Other costs | 10.2% | 51.49% | [5 empty] | travel and living costs |  | 1: 5493.15; 3: 452.59; 4: 7.15; 5: 198 | 6150.89
[8 empty] | planned | 5200
[8 empty] | in fact | 6150.89
[8 empty] | living costs per worked hour | 7.8523
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-06-27

## STO
STO | Crema de la Creme space in Stockman, 13.janvāra iela 8, Riga, 26/02/2024- (17/03/2024)02/05/2024
Object costs
|  | Februāris |  | Marts |  | Aprīlis/maijs |  | Total |  | General data |  | worked hours | [11 empty] | 0.56904
Objekta ieņēmumi kopā | Budget total | 22587.0633 |  | 45174.1067 |  |  |  | 67761.17 | 0 | Contract amount EUR | 50368.84 | marts | aprīlis | maijs | [8 empty] | total
Objekta tiešie izdevumi | Direct costs | 3581.0944 |  | 12287.1875 |  | 37096.93 |  | 52965.2119 |  | Additional works, EUR | 17392.32 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 1910 | 1910 |  | 9000 | 173.99 | 37096.93 | 2083.99 | 48006.93 | square m2 | 200 | marts 1: 730; maijs 4: 0; maijs 5: 0 | 730
materiālu piegādes izdevumi | delivery |  |  |  |  | 650 |  | 650 |  | object square | hours optimal/ m2 | [11 empty] | 0
apakšuzņēmēji | subcontractors |  |  | 9000 |  | 36272.94 |  | 45272.94 |  | m2<50 | 13
darba algas | salaries |  | 1581.0944 |  | 3162.1875 |  | 0 | 0 | 4743.2819 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 0 |  | 0 |  | 0 |  | 0 |  |  | 62088.49
uzkrājums atvaļinājumam | vacation allowance | 0 |  | 0 |  | 0 |  | 0 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 1581.0944 |  | 3162.1875 |  | 0 |  | 4743.2819 |  | planned | 9382.12
komandējuma dienas naudas | travel allowance | [6 empty] | 0 |  | in fact | 2733.99
komandējuma izdevumi- naktsmītne | travel expenses (hotels) |  | 90 |  | 125 |  | 0 | 0 | 215
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | [6 empty] | 0 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | [6 empty] | 0 |  | planned
citi izdevumi | other expenses | 90 |  | 125 |  |  |  | 215 |  | in fact | 0
[8 empty] | 0 |  | hours costs planned | 0
peļņa bruto | profit/ loss | 19005.9689 | 84.15% | 32886.9192 | 72.8% | -37096.93 | #DIV/0! | 14795.9581 | 21.84% | hours cost in fact | #DIV/0!
plānotā peļņa | planned profit | [6 empty] | 5061.51 | 10.05% |  |  | marts 1: travel and living costs
[10 empty] | hours per m2 | [12 empty] | total
Direct costs | actual costs | planned costs | [7 empty] | planned | 3.65 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Materials, incl.delivery, and subcontractors | 90.64% | [8 empty] | in fact | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
Salaries and taxes | 8.955% | [8 empty] | m2 costs | #DIV/0! | [11 empty] | 0
Other costs | 0.4059%
travel and living costs
planned
[10 empty] | in fact | 0
[10 empty] | living costs per worked hour | #DIV/0!
[10 empty] | Subcontractors budget, EUR | 39798.89
[10 empty] | Payments to subcontractor, EUR | 45272.94
date of report
2024-10-10
[10 empty] | elektrība | 10798.89
[10 empty] | GSS | 29000
55083.64
| 16525.09 | 30%
| 22033.46 | 40%
| 16525.09 | 30%
55083.64

## WDON
WDON | Calzedonia Sc Donauzentrum, Dr-Adolf-Schrf-Platz 4, EG 138c 1220 Wien, Austria 04/03/2024-17/03/2024
Object costs
|  | Marts 2024 |  |  |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 43500 | 173.03 | 43500 |  | 43500 |  | Contract amount EUR | 43500 | 04/03-10/03 | 10/03-17/03 | 01/05-07/05 | 08/05-14/05 | 15/05-21/05 | [6 empty] | total
Objekta tiešie izdevumi | Direct costs | 26123.8494 |  | 0 |  | 26123.8494 |  | Additional works, EUR |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 3742.55 | 7307.55 |  | 0 | 3742.55 | 7307.55 | square m2 | 63.83 | 1: 248.435; 2: 248.435; 3: 248.435; 4: 248.435 | 496.87
materiālu piegādes izdevumi | delivery | 920 |  |  |  | 920 |  | object square | hours optimal/ m2 | 1: 173.03; 2: 225.28 | 398.31 | 98.56
apakšuzņēmēji | subcontractors | 2645 |  |  |  | 2645 |  | m2<50 | 13
darba algas | salaries | 5623.342 | 15131.6894 |  | 0 | 5623.342 | 15131.6894 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 1326.5464 |  | 0 |  | 1326.5464
uzkrājums atvaļinājumam | vacation allowance | 555.9911 |  | 0 |  | 555.9911 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 3045 |  | 0 |  | 3045 |  | planned | 5386.93
| BUAK | 1080.81 |  |  |  | 1080.81
komandējuma dienas naudas | travel allowance | 3500 |  |  |  | 3500 |  | in fact | 4662.55
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 1428.19 | 3684.61 |  | 0 | 1428.19 | 3684.61
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1686.71 |  |  |  | 1686.71 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | [6 empty] | planned | 11962.85
citi izdevumi | other expenses | 569.71 |  |  |  | 569.71 |  | in fact | 12086.6894
[8 empty] | hours costs planned | 24.0764
peļņa bruto | profit/ loss | 17376.1506 | 39.95% | 43500 | 100% | 17376.1506 | 39.95% | hours cost in fact | 30.3449
plānotā peļņa | planned profit |  |  |  |  | 9724.12 | 22.35% |  |  | 1: travel and living costs
[8 empty] | hours per m2 |  | 1: 04/03-10/03; 2: 11/03-17/03; 3: 01/05-07/05; 4: 08/05-09/05; 5: 15/05-21/05 | total
Direct costs | actual costs | planned costs | [5 empty] | planned | 7.7843 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Materials, incl.delivery, and subcontractors | 27.97% | 15.95% | [5 empty] | in fact | 6.2402 | 1: 2740; 2: 2740; 3: 2740; 4: 2740 | 5480
Salaries and taxes | 57.92% | 35.42% | [5 empty] | m2 costs | 189.3575 | 1: 1115; 2: 1983.3 | 3098.3
Other costs | 14.1% | 48.63%
travel and living costs
[8 empty] | planned | 5480
[8 empty] | in fact | 3114.9
[8 empty] | living costs per worked hour | 7.8203
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-12-13

## KLA
KLA | Intimissimi shopping mall Akropolis, Taikos pr. 61, Klaipėda 91182, Lithuania 20/02/2024-26/02/2024
Object costs
|  | Februāris 2024 |  | Marts 2024 |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 12955.25 | 205.51 | 2797.7 |  | 15752.95 | 205.51 | Contract amount EUR | 12955.25 | 20/02-26/02 | [10 empty] | total
Objekta tiešie izdevumi | Direct costs | 8524.0513 |  | 819.7779 |  | 9343.8292 |  | Additional works, EUR | 2797.7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 1243.63 | 1748.44 | 56.04 | 56.04 | 1299.67 | 1804.48 | square m2 | 74.75 | 20/02-26/02 1: 193.35; 20/02-26/02 2: 24 | 217.35
materiālu piegādes izdevumi | delivery |  |  |  |  | 0 |  | object square | hours optimal/ m2 | 20/02-26/02 1: 180.51; 20/02-26/02 2: 25 | 205.51 | 11.84
apakšuzņēmēji | subcontractors | 504.81 |  |  |  | 504.81 |  | m2<50 | 13
darba algas | salaries | 2819.623 | 5480.4213 | 482.8 | 753.7379 | 3302.423 | 6234.1592 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 665.1491 |  | 113.8925 |  | 779.0416
uzkrājums atvaļinājumam | vacation allowance | 278.7818 |  | 47.7354 |  | 326.5172 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 906.8675 |  | 49.31 |  | 956.1775 |  | planned | 1328.27
komandējuma dienas naudas | travel allowance | 810 |  | 60 |  | 870 |  | in fact | 1299.67
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 670.86 | 1295.19 |  | 10 | 670.86 | 1305.19
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 40 |  |  |  | 40 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) |  |  |  |  | 0 |  | planned | 3294.95
citi izdevumi | other expenses | 584.33 |  | 10 |  | 594.33 |  | in fact | 5277.9818
peļņa bruto | profit/ loss | 4431.1987 | 34.2% | 1977.9221 | 70.7% | 6409.1208 | 40.69% | hours costs planned | 15.1597
plānotā peļņa | [5 empty] | 3920.32 | 30.26% | hours cost in fact | 25.6824 | 20/02-26/02 1: travel and living costs
[10 empty] | 20/02-26/02 1: 20/02-26/02 | total
Direct costs | actual costs | planned costs | [5 empty] | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Materials, incl.delivery, and subcontractors | 19.31% | 14.7% | [5 empty] | planned | 2.9077 | 20/02-26/02 1: 1310; 20/02-26/02 2: 1310; 20/02-26/02 3: 1310 | 1310
Salaries and taxes | 66.72% | 36.47% | [5 empty] | in fact | 2.7493 | 20/02-26/02 1: 710.66 | 710.66
Other costs | 13.97% | 48.83% | [5 empty] | m2 costs | 70.6085
travel and living costs
[8 empty] | planned | 1310
[8 empty] | in fact | 710.86
[8 empty] | living costs per worked hour | 3.459
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-03-28

## GRA
GRA | Intimissimi Herrengasse 28, Graz, Austria, 19/02/2024-03/03/2024
Object costs
|  | Februāris 2024 |  | Marts 2024 | [5 empty] | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 31143.8333 |  | 15571.9167 |  | 0 |  | #REF! |  | 46715.75 |  | Contract amount EUR | 41000 | 19/02-25/02 | 26/02-03/03 | [9 empty] | total
Objekta tiešie izdevumi | Direct costs | 23828.6332 |  | 12804.0553 |  | 0 |  | 0 |  | 38014.0685 |  | Additional works, EUR | 5715.75 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
mtr. un aprīkojuma iegāde | materials and equipment | 8642.67 | 9723.29 | 567.59 | 8475.64 |  | 0 |  | 0 | 9210.26 | 18198.93 | square m2 | 89.36 | 19/02-25/02 1: 252; 26/02-03/03 2: 252; 26/02-03/03 3: -14.74 | 489.05
mtr. piegādes izdevumi | delivery | 57.62 |  | 1090 | [5 empty] | 1147.62 |  | object square | hours optimal/ m2 | 19/02-25/02 1: 140; 26/02-03/03 2: 164.6; 26/02-03/03 3: 123.7 | 428.3 | 60.75
apakšuzņēmēji | subcontractors | 1023 |  | 6818.05 | [5 empty] | 7841.05 |  | m2<50 | 13
darba algas | salaries | 3676.4368 | 9837.2732 | 1475.309 | 3909.2353 |  | 0 |  | 0 | 5151.7458 | 15127.8885 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 867.2714 |  | 348.0254 |  | 0 |  | 0 |  | 1215.2968
uzkrājums atvaļinājumam | vacation allowance | 363.4967 |  | 145.8668 |  | 0 |  | 0 |  | 509.3634 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 2180.0683 |  | 1090.0342 |  | 0 |  | 0 |  | 3270.1025 |  | planned | 4507.18
| BUAK | [8 empty] | 1381.38
kom. dienas naudas | travel allowance | 2750 |  | 850 | [5 empty] | 3600 |  | in fact | 10357.88
kom. izdevumi- naktsmītne | travel expenses (hotels) | 1883.94 | 4268.07 | 124.21 | 419.18 |  | 0 |  | 0 | 2008.15 | 4687.25
kom. izdevumi- ceļš | travel expenses ( tickets, road costs) | 596.04 | [7 empty] | 596.04 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | [10 empty] | planned | 11367.99
citi izdevumi | other expenses | 1788.09 |  | 294.97 | [5 empty] | 2083.06 |  | in fact | 11857.786
peļņa bruto | profit/ loss | 7315.2001 | 23.49% | 2767.8614 | 17.77% | 0 | #DIV/0! | #REF! | #REF! | 8701.6815 | 18.63% | hours costs planned | 23.245
plānotā peļņa | planned profit | [8 empty] | 12812.76 | 31.25% | hours cost in fact | 27.6857 | 19/02-25/02 1: travel and living costs
[14 empty] | 19/02-25/02 | 26/02-03/03 | 13/03-19/03 | 20/03-26/03 | 27/03-02/04 | 03/04-09/04 | 10/04-12/04 | 23/04-30/04 | 01/05-04/05 | 0 | 0 | total
Direct costs | actual costs | planned costs | [9 empty] | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Materials, incl.delivery, and subcontractors | 47.87% | 13.29% | [9 empty] | planned | 5.4728 | 1: 2150; 2: 2150; 3: 2150; 4: 2150; 5: 2150 | 4300
Salaries and taxes | 39.8% | 33.53% | [9 empty] | in fact | 4.793 | 1: 2479.98; 2: 124.21 | 2604.19
Other costs | 12.33% | 17.73% | [9 empty] | m2 costs | 132.6968
travel and living costs
[12 empty] | planned | 4300
[12 empty] | in fact | 2604.19
[12 empty] | living costs per worked hour | 6.0803
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-06-13

## BRA
BRA | Calzedonia and Intimissimi SC SCHLOSS ARKADEN BRAUNSCHWEIG 04/02/2024-(02/03/2024/)07/03/2024
Object costs
|  | Februāris |  | Marts |  |  |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 136747.57 |  | 9121.36 |  |  |  | 145868.93 |  | Contract amount EUR | 136747.57 | 04/02-11/02 | 12/02-18/02 | 19/02-25/02 | 26/02-03/03 |  | maijs | [5 empty] | total
Objekta tiešie izdevumi | Direct costs | 60401.6674 |  | 39816.7693 |  | 0 |  | 100218.4367 |  | Additional works, EUR | 9121.36 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 17252.12 | 19461.34 | 1148.73 | 28201.74 |  | 0 | 18400.85 | 47663.08 | square m2 | 143.53 | 1: 373.505; 2: 373.505; 3: 373.505; 4: 373.505 | 1494.02
materiālu piegādes izdevumi | delivery | 1953.81 | [5 empty] | 1953.81 |  | object square | hours optimal/ m2 | 1: 230.57; 2: 390.56; 3: 273.16; 4: 342.2; 5: 208.23 | 1444.72 | 49.3
apakšuzņēmēji | subcontractors | 255.41 |  | 27053.01 |  |  |  | 27308.42 |  | m2<50 | 13
darba algas | salaries | 10770.1746 | 33148.0574 | 4960.1452 | 9170.6093 |  | 0 | 15730.3198 | 42318.6667 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 2540.6842 |  | 1170.0983 |  | 0 |  | 3710.7824
uzkrājums atvaļinājumam | vacation allowance | 1064.8687 |  | 490.4195 |  | 0 |  | 1555.2882 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 9572.3299 |  | 599.9464 |  | 0 |  | 10172.2763 |  | planned | 19260.53
komandējuma dienas naudas | travel allowance | 9200 |  | 1950 |  |  |  | 11150 |  | in fact | 20354.66
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 5064.85 | 7792.27 | 291.89 | 2444.42 |  | 0 | 5356.74 | 10236.69
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1453.5 |  | 1382.2 |  |  |  | 2835.7 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | 393.19 | [5 empty] | 393.19 |  | planned | 35013.72
citi izdevumi | other expenses | 880.73 |  | 770.33 |  |  |  | 1651.06 |  | in fact | 32146.3904
[10 empty] | hours costs planned | 23.4359
peļņa bruto | profit/ loss | 76345.9026 | 55.83% | -30695.4093 | -336.5% | 0 | #DIV/0! | 45650.4933 | 31.3% | hours cost in fact | 22.2509
plānotā peļņa | planned profit | [6 empty] | 27308.37 | 19.97% |  |  | 1: travel and living costs
[10 empty] | hours per m2 |  | 1: 04/02-11/02; 2: 12/02-18/02; 3: 19/02-25/02; 4: 26/02-03/03; 5: 0 | total
Direct costs | actual cost | planned costs | [7 empty] | planned | 10.4091 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Materials, incl.delivery, and subcontractors | 47.56% | 18.41% | [7 empty] | in fact | 10.0656 | 1: 2025; 2: 2025; 3: 2025; 4: 2025 | 8100
Salaries and taxes | 42.23% | 31.83% | [7 empty] | m2 costs | 223.9698 | 1: 5835.77; 2: 185.46; 3: 235.21; 4: 1804.18; 5: 131.89 | 8192.51
Other costs | 10.21% | 36.15%
travel and living costs
[10 empty] | planned | 8100
[10 empty] | in fact | 8192.44
[10 empty] | living costs per worked hour | 5.6706
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-04-02
| līguma summa | 30 | 60 | 10 |  |  |  | līguma samazinājums
Intimissimi | 81178.53 | 24353.56 | 48707.12 | 8117.86 | 81178.54 |  |  | 80294.59 | 883.94
Calzedonia | 57149.42 | 17144.83 | 34289.65 | 5714.93 | 57149.41 |  |  | 56452.98 | 696.44
KOPĀ: | 138327.95 | 41498.39 | 82996.77 | 13832.79 | 138327.95 |  |  | 136747.57 | 1580.38
7540.98
| līguma summa | jaunais līgums | samazinājums
Intimissimi | 81178.53 | 80294.59 | 883.94
Calzedonia | 57149.42 | 56452.98 | 696.44
KOPĀ: | 138327.95 | 136747.57 | 1580.38

## VIL
VIL | Calzedonia SC ATRIO Villach, Kärntner Str. 34, 9500 Villach, Austria, 16/01/2024-29/01/2024
Object costs
|  | Janvāris |  | Marts 22 |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 52875.23 |  |  |  | 52875.23 | 0 | Contract amount EUR | 48000 | 16/01-21/01 | 22/01-29/01 | [9 empty] | total
Objekta tiešie izdevumi | Direct costs | 36587.5052 |  | 0 |  | 36587.5052 |  | Additional works, EUR | 4875.23 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 8553.05 | 14102.44 |  | 0 | 8553.05 | 14102.44 | square m2 | 65.18 | 16/01-21/01 1: 281; 22/01-29/01 2: 281; 22/01-29/01 3: 34.5 | 597.08
materiālu piegādes izdevumi | delivery | 350 |  |  |  | 350 |  | object square | hours optimal/ m2 | 16/01-21/01 1: 181; 22/01-29/01 2: 305.56; 22/01-29/01 3: 35.62 | 522.18 | 74.9
apakšuzņēmēji | subcontractors | 5199.39 |  |  |  | 5199.39 |  | m2<50 | 13
darba algas | salaries | 6695.5698 | 17638.3252 |  | 0 | 6695.5698 | 17638.3252 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 1579.4849 |  | 0 |  | 1579.4849
uzkrājums atvaļinājumam | vacation allowance | 662.0044 |  | 0 |  | 662.0044 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 3701.2661 |  | 0 |  | 3701.2661 |  | planned | 5490
komandējuma dienas naudas | travel allowance | 5000 |  |  |  | 5000 |  | in fact | 8903.05
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2804.09 | 4846.74 |  | 0 | 2804.09 | 4846.74
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1311.44 |  |  |  | 1311.44 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | [6 empty] | planned | 13501.21
citi izdevumi | other expenses | 731.21 |  |  |  | 731.21 |  | in fact | 13937.0591
peļņa bruto | profit/ loss | 16287.7248 | 30.8% | 0 | #DIV/0! | 16287.7248 | 30.8% | hours costs planned | 22.6121
plānotā peļņa | [5 empty] | 11050.08 | 23.02% | hours cost in fact | 26.6901
travel and living costs
Direct costs | actual costs | planned costs | [5 empty] | hours per m2 |  | 16/01-21/01 1: 16/01-21/01; 22/01-29/01 2: 22/01-29/01 | total
Materials, incl.delivery, and subcontractors | 38.54% | 14.86% | [5 empty] | planned | 9.1605 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 48.21% | 36.54% | [5 empty] | in fact | 8.0114 | 16/01-21/01 1: 2440; 22/01-29/01 2: 2440 | 4880
Other costs | 13.25% | 48.6% | [5 empty] | m2 costs | 213.8242 | 16/01-21/01 1: 3557.18; 22/01-29/01 2: 448.37; 22/01-29/01 3: 110 | 4115.55
travel and living costs
[8 empty] | planned | 4880
[8 empty] | in fact | 4115.53
[8 empty] | living costs per worked hour | 7.8814
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-03-21

## KOB
KOB | Intimissimi SC Forum Mittelrhein Koblenz Zentralpl. 2, 56068 Koblenz, Germany, 23/01/2024-19(10)/02/2024
Object costs
|  | 2024-01-24 |  | 2024-02-24 |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 16000 | 207.61 | 32000 |  | 55924.07 | 207.61 | Contract amount EUR | 48000 | 23/01-28/01 | 29/01-04/02 | 05/02-10/02 | [8 empty] | total
Objekta tiešie izdevumi | Direct costs | 18017.0107 |  | 25111.8415 |  | 43128.8522 |  | Additional works, EUR | 7924.07 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 5525.26 | 5724.46 | 4264.26 | 5545.67 | 9789.52 | 11270.13 | square m2 | 66.2 | 23/01-28/01 1: 214; 29/01-04/02 2: 214; 05/02-10/02 3: 214; 05/02-10/02 4: 98.39 | 741.05
materiālu piegādes izdevumi | delivery |  |  | 750 |  | 750 |  | object square | hours optimal/ m2 | 23/01-28/01 1: 207.61; 29/01-04/02 2: 291.46; 05/02-10/02 3: 310.72; 05/02-10/02 4: 244.47 | 1054.26 | -313.21
apakšuzņēmēji | subcontractors | 199.2 |  | 531.41 |  | 730.61 |  | m2<50 | 13
darba algas | salaries | 3616.9104 | 7897.7507 | 7210.476 | 16614.3415 | 10827.3864 | 24512.0922 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 853.2292 |  | 1700.9513 |  | 2554.1805
uzkrājums atvaļinājumam | vacation allowance | 357.6112 |  | 712.9142 |  | 1070.5253 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 1120 |  | 2240 |  | 3360 |  | planned | 8968.78
komandējuma dienas naudas | travel allowance | 1950 |  | 4750 |  | 6700 |  | in fact | 10539.52
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 3167.07 | 4394.8 | 1092.3 | 2951.83 | 4259.37 | 7346.63
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1037.07 |  | 1573.89 |  | 2610.96 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | [6 empty] | planned | 16833.21
citi izdevumi | other expenses | 190.66 |  | 285.64 |  | 476.3 |  | in fact | 21152.0922
peļņa bruto | profit/ loss | -2017.0107 | -12.61% | 6888.1585 | 21.53% | 12795.2178 | 22.88% | hours costs planned | 22.7153
plānotā peļņa | planned profit |  |  |  |  | 12923.22 | 24.82% | hours cost in fact | 20.0634 | 23/01-28/01 1: travel and living costs
[10 empty] | 23/01-28/01 1: 23/01-28/01; 29/01-04/02 2: 29/01-04/02; 05/02-10/02 3: 05/02-10/02 | total
Direct costs | actual costs | planned costs | [5 empty] | hours per m2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Materials, incl.delivery, and subcontractors | 26.13% | 20.86% | [5 empty] | planned | 11.1941 | 23/01-28/01 1: 1333.3333; 29/01-04/02 2: 1333.3333; 05/02-10/02 3: 1333.3333 | 4000
Salaries and taxes | 56.83% | 39.15% | [5 empty] | in fact | 15.9254 | 23/01-28/01 1: 6870.33; 05/02-10/02 3: 1092.3; 05/02-10/02 4: 726.67 | 6870.33
Other costs | 17.03% | 39.81% | [5 empty] | m2 costs | 319.518
travel and living costs
[8 empty] | planned | 4000
[8 empty] | in fact | 6870.33
[8 empty] | living costs per worked hour | 6.5167
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-03-08

## SWR
SWA | Galeria Inno Liege Pl. de la République Francaise 15B-4000 LIEGE, Belgium
Object costs
|  | Janvāris |  | Februāris |  | Total |  | General data |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 13377.01 | 62.5 |  |  | 13377.01 | 62.5 | Contract amount EUR | 14988.39 | Time shedule, weeks | [11 empty] | total
Objekta tiešie izdevumi | Direct costs | 7143.7829 |  | 0 |  | 7143.7829 |  | Additional works, EUR | -1611.38 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 913.67 | 913.67 |  | 0 | 913.67 | 913.67 | square m2 | 25 |  | 1: 97.25 | 97.25
materiālu piegādes izdevumi | delivery |  |  |  |  | 0 |  | object square | hours optimal/ m2 |  | 1: 62.5 | 62.5 | 34.75
apakšuzņēmēji | subcontractors |  |  |  |  | 0 |  | m2<50 | 13
darba algas | salaries | 1838.9 | 4050.9029 |  | 0 | 1838.9 | 4050.9029 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 433.7965 |  | 0 |  | 433.7965
uzkrājums atvaļinājumam | vacation allowance | 181.8157 |  | 0 |  | 181.8157 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 936.3907 |  | 0 |  | 936.3907 |  | planned | 390
komandējuma dienas naudas | travel allowance | 660 |  |  |  | 660 |  | in fact | 913.67
komandējuma izdevumi- naktsmītne | travel expenses (hotels) |  | 2179.21 |  | 0 | 0 | 2179.21
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) |  |  |  |  | 0 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | 1506.19 |  |  |  | 1506.19 |  | planned | 3890
citi izdevumi | other expenses | 673.02 |  |  |  | 673.02 |  | in fact | 3114.5122
[8 empty] | hours costs planned | 40
peļņa bruto | profit/ loss | 6233.2271 | 46.6% | 0 | #DIV/0! | 6233.2271 | 46.6% | hours cost in fact | 49.8322
plānotā peļņa | planned profit |  |  |  |  | 4083.34 | 27.24%
[8 empty] | hours per m2 |  | Object address | 1: travel and living costs
Direct costs | actual costs | planned costs | [5 empty] | planned | 3.89 | Time shedule, weeks | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | total
Materials, incl.delivery, and subcontractors | 12.79% | 3.572% | [5 empty] | in fact | 2.5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 56.71% | 35.67% | [5 empty] | m2 costs | 124.5805 |  | 1: 3000 | 3000
Other costs | 30.5% | 60.76% | [8 empty] | 1: 0 | 0
[8 empty] | travel and living costs | 3000
[8 empty] | planned | 0
[8 empty] | in fact | 0
[8 empty] | living costs per worked hour | 0
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-02-20

## CALZ MOS
MOS | Calzedonia Mall of Scandinavia, 22/01/2024-31/01/2024
Object costs
|  | 2024-01-24 |  | 2024-02-02 |  | Marts-24 |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 55112.34 |  |  |  | 0 |  | 55112.34 |  | Contract amount EUR | 43564.77 | 22/01-28/01 | 29/01-31/01 | add.works | [8 empty] | total
Objekta tiešie izdevumi | Direct costs | 34945.0149 |  | 2349.0543 |  | 210.74 |  | 37504.8092 |  | Additional works, EUR | 11547.57 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 6999.1021 | 8389.1021 |  | 0 | 187.74 | 187.74 | 7186.8421 | 8576.8421 | square m2 | 52.25 | 22/01-28/01 1: 268.5; 29/01-31/01 2: 268.5; add.works 3: 70 | 537
materiālu piegādes izdevumi | delivery | [6 empty] | 0 |  | object square | hours optimal/ m2 | 22/01-28/01 1: 471; 29/01-31/01 2: 243.85; add.works 3: 83.1 | 797.95 | -260.95
apakšuzņēmēji | subcontractors | 1390 | [5 empty] | 1390 |  | m2<50 | 13
darba algas | salaries | 9241.218 | 19692.7828 | 1009.5632 | 2083.8643 |  | 0 | 10250.7812 | 21776.6471 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 2180.0033 |  | 238.156 |  | 0 |  | 2418.1593
uzkrājums atvaļinājumam | vacation allowance | 913.6977 |  | 99.8175 |  | 0 |  | 1013.5152 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 3857.8638 |  | 136.3276 |  | 0 |  | 3994.1914 |  | planned | 8824.21
komandējuma dienas naudas | travel allowance | 3500 |  | 600 |  |  |  | 4100 |  | in fact | 8576.8421
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2901.81 | 6863.13 |  | 265.19 |  | 23 | 2901.81 | 7151.32
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1847.95 | [5 empty] | 1847.95 |  | Salaries and taxes
komandējuma izdevumi (administrācija) | travel expenses (administration) | 1265.02 | [5 empty] | 1265.02 |  | planned | 11606.14
citi izdevumi | other expenses | 848.35 |  | 265.19 |  | 23 |  | 1136.54 |  | in fact | 17782.4557
[10 empty] | hours costs planned | 24.8525
peļņa bruto | profit/ loss | 20167.3251 | 36.59% | -2349.0543 | #DIV/0! | -210.74 | #DIV/0! | 17607.5308 | 31.95% | hours cost in fact | 22.2852
plānotā peļņa | planned profit | [6 empty] | 11172.37 | 25.65% |  |  | 22/01-28/01 1: travel and living costs
[10 empty] | hours per m2 |  | 22/01-28/01 1: 22/01-28/01; 29/01-31/01 2: 29/01-31/01 | total
Direct costs | actual costs | planned costs | [7 empty] | planned | 8.9378 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Materials, incl.delivery, and subcontractors | 22.87% | 27.24% | [7 empty] | in fact | 15.2718 | 22/01-28/01 1: 3100; 29/01-31/01 2: 3100 | 6200
Salaries and taxes | 58.06% | 35.83% | [7 empty] | m2 costs | 340.3341 | 22/01-28/01 1: 2362.44; 29/01-31/01 2: 2386.19 | 4748.63
Other costs | 19.07% | 36.93%
travel and living costs
[10 empty] | planned | 6200
[10 empty] | in fact | 4748.63
[10 empty] | living costs per worked hour | 5.951
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-02-22
|  | avanss 50% | gala maksājums 50%
Līgums SEK | 500725.29 | 250362.65 | 250362.64 |  |  |  |  | 500725.29
kurss | 11.2125
Līgums EUR | 44657.77 | 22328.89 | 22328.88 |  |  |  |  | 44657.77
Atjaunotais līgums SEK | 630202.4
| 56205.34 | 11547.57
Optimera | 66302845 | 3959.83
| 66314550 | 758.64
| 66326562 | 3218.12
| 66408881 | 1008.22
| 66635343 | 629.64
| 66568080 | 12801.68
| 66212341 | 1187.43
Big Bag | 142276195 | 2533
| 143175990 | 140.25
| 142781699 | 772.88
| 142781798 | 398.75
| 142276195 | 633.25
| 142506799 | 841.5
28883.19
2599.4871

## INT GAL
GAL | Intimissimi Stockholm Gallerian, 08/01/2024-17/01/2024
Object costs
|  | 2024-01-01 |  | 2023-02-01 |  | Marts 23 |  | Total |  | General data |  | worked hours
Objekta ieņēmumi kopā | Budget total | 58921.11 | 595.38 |  |  |  |  | 58921.11 | 595.38 | Contract amount EUR | 56957.32 | 08/01-14/01 | 15/01-17/01 | add.works | [8 empty] | total
Objekta tiešie izdevumi | Direct costs | 29972.9437 |  | 0 |  | 360.9 |  | 30333.8437 |  | Additional works, EUR | 1963.79 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 8794.9465 | 8794.9465 |  | 0 | 360.9 | 360.9 | 9155.8465 | 9155.8465 | square m2 | 79.53 | 08/01-14/01 1: 255.5; 15/01-17/01 2: 255.5; add.works 3: 25 | 511
materiālu piegādes izdevumi | delivery | [6 empty] | 0 |  | object square | hours optimal/ m2 | 08/01-14/01 1: 411.46; 15/01-17/01 2: 183.92 | 595.38 | -84.38
apakšuzņēmēji | subcontractors | [6 empty] | 0 |  | m2<50 | 13
darba algas | salaries | 6937.1544 | 16833.9972 |  | 0 |  | 0 | 6937.1544 | 16833.9972 | 50<m2<100 | 12
DD VSAOI | tax for salaries | 1636.4747 |  | 0 |  | 0 |  | 1636.4747
uzkrājums atvaļinājumam | vacation allowance | 685.8903 |  | 0 |  | 0 |  | 685.8903 |  | materials and equipment costs
administratīvie izdevumi 7% | administrative costs 7% | 4124.4777 |  | 0 |  | 0 |  | 4124.4777 |  | planned | 9685.85
komandējuma dienas naudas | travel allowance | 3450 | [5 empty] | 3450 |  | in fact | 9155.8465
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2184.2 | 4344 |  | 0 |  | 0 | 2184.2 | 4344
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1487.52 | [5 empty] | 1487.52 |  | Salaries and taxes
komandējuma izdevumi- administrācija | travel expenses (administration) | [8 empty] | planned | 14324.16
citi izdevumi | other expenses | 672.28 | [5 empty] | 672.28 |  | in fact | 12709.5195
peļņa bruto | profit/ loss | 28948.1663 | 49.13% | 0 | #DIV/0! | -360.9 | #DIV/0! | 28587.2663 | 48.52% | hours costs planned | 29.4736
plānotā peļņa | planned profit | [6 empty] | 16709.86 | 29.34% | hours cost in fact | 21.3469
Direct costs | actual costs | planned costs | [7 empty] | hours per m2
Materials, incl.delivery, and subcontractors | 30.18% | 24.07% | [7 empty] | planned | 6.4252 | 08/01-14/01 1: travel and living costs
Salaries and taxes | 55.5% | 35.59% | [7 empty] | in fact | 7.4862 | 08/01-14/01 1: 08/01-14/01; 15/01-17/01 2: 15/01-17/01 | total
Other costs | 14.32% | 43.45% | [7 empty] | m2 costs | 159.8079 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
[12 empty] | 08/01-14/01 1: 4150; 15/01-17/01 2: 4150 | 8300
[10 empty] | travel and living costs |  | 08/01-14/01 1: 3281.52; 15/01-17/01 2: 389.94 | 3671.46
[10 empty] | planned | 8300
[10 empty] | in fact | 3671.46
[10 empty] | living costs per worked hour | 6.167
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-02-20
|  | avanss 50% | gala maksājums 50%
Līgums SEK | 638633.98 | 319316.99 | 319316.99 |  |  |  |  | 638633.98
kurss | 11.2125
Līgums EUR | 56957.32 | 28478.66 | 28478.66 |  |  |  |  | 56957.32 |  | 660653.02
papilddarbi SEK | 22019.04 | [8 empty] | 58921.1166
papilddarbi EUR | 1963.794 | 58921.114 | [7 empty] | 58921.11
Optimera | 66017351 | 3336.24
| 66041252 | 2551.14
| 66041245 | 6229.35
| 66028739 | 1179.6
| 66052358 | 4861.41
| 66153842 | 451.84
| 66314568 | 3566.96
Glasbolaget | 3672 | 10000
| 3673 | 10229
Big Bag | 141972695 | 13817.31
56222.85
5060.0565