## Total 2023
objekts
| FUR | MUN2 | SAR | SAR2 | SW | ANT | OFF | BER | MAL | TAL | NEU | ARN | MEM | HAL | OLD | DOR | FAL | AUH | BOCH | BER2 | SIE | AMB | CHA | TAL2 | SIEC | FAL2
contract amount | 162000 | 175887.1 | 64000 | 22136.76 | 5650 | 55889.96 | 158000 | 75388.43 | 71337.13 | 16500 | 71273.73 | 60000 | 7000 | 63000 | 38521.98 | 75736.12 | 75100.2 | 86000 | 225634 | 405955.87 | 14005.39 | 70300.13 | 67542.6 | 94138.97 | 79000 | 18614.6
additional works | 6555 |  | 17621.74 | 8413.05 | 0 | 0 | 24166.3 | 11625 | 4528.76 | 0 | 800 | 5603.51 | 0 | 10297.39 | 2431.44 | 5069.4 | 5153.47 | 1600 | 25481.18 | 1600 |  | 0 | 18742.6 | 26296.98 | 3261.75 | 0
total income | 168555 | 175887.1 | 81621.74 | 30549.81 | 5650 | 55889.96 | 182166.3 | 87013.43 | 75865.89 | 16500 | 72073.73 | 65603.51 | 7000 | 73297.39 | 40953.42 | 80805.52 | 80253.67 | 87600 | 251115.18 | 407555.87 | 14005.39 | 70300.13 | 86285.2 | 120435.95 | 82261.75 | 18614.6
project manager | Jānis/Matīss | Alex | Matīss | Matīss | Alex | Jānis | Matīss | Alex | Alex/ Edgars? | Matīss | Edgars | Alex | Edgars | Mauro | Alex | Alex | Mauro/ Māris | Mauro, Edgars | Māris | Alens | Mauro | Mauro | Alexander | Jānis E. | Mauro | Alexander
planned hours | 1698 | 1206 | 708 | 313 |  | 711.85 | 1681 | 478 | 900.82 | 0 | 695 | 543 | 0 | 996 | 466 | 966 | 801 | 1010 | 0 | 2881 | 0 | 192 | 875 | 1217 | 1019.94 | 0
worked hours | 2232 | 1445 | 1117 | 377.5 | 0 | 902.5 | 1735 | 191.5 | 0 | 701 | 701 | 552 | 126 | 929.7 | 592 | 833 | 989 | 940 | 0 | 2881.29 | 143.7 | 396.29 | 1599.58 | 1518.82 | 682.811 | 272.99
stundu bilance | -534 | -239 | -409 | -64.5 |  | -190.65 | -54 | 286.5 | 900.82 | -701 | -6 | -9 | -126 | 66.3 | -126 | 133 | -188 | 70 | 0 | -0.29 | -143.7 | -204.29 | -724.58 | -301.82 | 337.129 | -272.99
| 11798.85 | 13227.4492 | 5713.5218 | 2138.4867 | 395.5 | 3912.2972 | 12751.641 | 6090.9401 | 5627.6255 | 1155 | 4989.1611 | 4200 | 490 | 5851.6346 | 2866.7394 | 5656.3864 | 5617.7569 | 6132 | 17578.0626 | 28491.5776 | 980.3773 | 4921.0091 | 6039.964 | 8430.5165 | 5758.3225 | 1303.022 | 172117.8415
profit % | 33.27% | 39.1% | 13.52% | 52.12% | -3.004% | 42.19% | 26.58% | 47.63% | 38.04% | 28.83% | 28.83% | 31.82% | -27.87% | 15.04% | 10.9% | 46.62% | 35.93% | 30.58% | 11.1% | 31.45% | 27.54% | 45.4% | 6.217% | 10.68% | 35.07% | 32.57%
profit EUR | 56074.3962 | 73892.0664 | 11034.0838 | 15921.4086 | -169.744 | 23582.1964 | 48419.5163 | 41443.603 | 28863.1637 | 5689.659 | 20544.9703 | 20876.0002 | -1950.9127 | 11025.6459 | 4463.4668 | 37671.3695 | 28834.1159 | 26784.3838 | 27882.6309 | 128180.7335 | 3857.136 | 31917.8205 | 5364.3674 | 12862.4011 | 28847.4825 | 6062.5849 | 697974.5461
construction works profit/ loss | 56074.3962 | 60815.6064 | 7489.0838 | 15921.4086 | -169.744 | 23582.1964 | 26694.3863 | 41443.603 | 28863.1637 | 5689.659 | 42899.2847 | 20876.0002 | -1950.9127 | 11025.6459 | 2135.9268 | 33822.3195 | 28834.1159 | 26784.3838 | -20208.3291 | 235187.8435 | 3857.136 | 31917.8205 | 5458.5074 | 60648.6911 | 29798.6725 | 6382.5849
construction works budget | 140106.2 | 175887.1 | 63878.74 | 30549.81 | 5650 | 55889.96 | 139167.58 | 87013.43 | 75865.89 | 16500 | 56766.49 | 50209.43 | 7000 | 73297.39 | 35087.95 | 71250.52 | 80253.67 | 82806 | 40216.81 | 407555.87 | 14005.39 | 70300.13 | 86285.2 | 120435.95 | 82261.75 | 18614.6
| 84031.8038 | 115071.4936 | 56389.6562 | 14628.4014 | 5819.744 | 32307.7636 | 112473.1937 | 45569.827 | 47002.7263 | 10810.341 | 13867.2053 | 29333.4298 | 8950.9127 | 62271.7441 | 32952.0232 | 37428.2005 | 50869.5541 | 50539.3162 | 60425.1391 | 172368.0265 | 10148.254 | 38382.3095 | 80826.6926 | 59787.2589 | 52463.0775 | 12232.0151
| 40.02% | 34.58% | 11.72% | 52.12% | -3.004% | 42.19% | 19.18% | 47.63% | 38.04% | 34.48% | 75.57% | 41.58% | -27.87% | 15.04% | 6.087% | 47.47% | 35.93% | 32.35% | -50.25% | 57.71% | 27.54% | 45.4% | 6.326% | 50.36% | 36.22% | 34.29%
subcontractors work profit/loss | 6716.7517 |  | 3545 |  |  |  | 21725.13 |  |  |  | 8629.475 | 2900.8 | 0 | 0 | 2327.54 | 3849.05 |  | -2264.48 | 81008.23
subcontractors budget | 28448.8 |  | 17743 |  |  |  | 42998.72 |  |  |  | 15307.24 | 15394.08 | 0 | 0 | 5865.47 | 9555 |  | 4794 | 210898.37 |  | 0 | 0 | 0 | 0 | 0 | 0
| 21732.0483 |  | 14198 |  |  |  | 21273.59 |  |  |  | 6677.765 | 12493.28 | 0 | 0 | 3537.93 | 5705.95 |  | 7058.48 | 129890.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 23.61% |  | 19.98% |  |  |  | 50.53% |  |  |  | 56.38% | 18.84% |  |  | 39.68% | 40.28% |  | -47.24% | 38.41% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Profit
Object | contract amount | additional works | object total | Profit (%) | Project manager
SAR2 | 22136.76 | 8413.05 | 30549.81 | 52.12% | Matīss | 15921.4086
BER | 75388.43 | 11625 | 87013.43 | 47.63% | Alexander | 41443.603
DOR | 75736.12 | 5069.4 | 80805.52 | 46.62% | Alexander | 37671.3695
AMB | 70300.13 |  | 70300.13 | 45.4% | Mauro | 31917.8205
ANT | 55889.96 | 0 | 55889.96 | 42.19% | Jānis | 23582.1964
MUN2 | 175887.1 | 13076.46 | 188963.56 | 39.1% | Alexander | 73892.0664
MAL | 71337.13 | 4528.76 | 75865.89 | 38.04% | Alexander | 28863.1637
FAL | 75100.2 | 5153.47 | 80253.67 | 35.93% | Māris, Mauro | 28834.1159
SIEC | 79000 | 3261.75 | 82261.75 | 35.07% | Mauro | 28847.4825
TAL | 16500 | 0 | 16500 | 34.48% | Matīss | 5689.659
FUR | 162000 | 6555 | 168555 | 33.27% | Jānis | 56074.3962
FAL2 | 18614.6 | 0 | 18614.6 | 32.57% | Alexander | 6062.5849
ARN | 60000 | 5603.51 | 65603.51 | 31.82% | Alexander | 20876.0002
BER2 | 405955.87 | 1600 | 407555.87 | 31.45% | Alens | 128180.7335
AUH | 86000 | 1600 | 87600 | 30.58% | Mauro, Edgars | 26784.3838
NEU | 71273.73 | 800 | 72073.73 | 28.83% | Edgars | 20775.5739
SIE | 14005.39 | 0 | 14005.39 | 27.54% | Mauro | 3857.136
OFF | 158000 | 24166.3 | 182166.3 | 26.58% | Matīss | 48419.5163
HAL | 63000 | 10297.39 | 73297.39 | 15.04% | Mauro | 11025.6459
SAR | 64000 | 17621.74 | 81621.74 | 13.52% | Matīss | 11034.0838
BOCH | 225634 | 25481.18 | 251115.18 | 11.1% | Māris | 27882.6309
OLD | 38521.98 | 2431.44 | 40953.42 | 10.9% | Alexander | 4463.4668
TAL2 | 94138.97 | 26296.98 | 120435.95 | 10.68% | Aleksandrs L., Jānis E. | 12862.4011
CHA | 67542.6 | 18742.6 | 86285.2 | 6.217% | Alexander | 5364.3674
SW | 5650 | 0 | 5650 | -3.004% | Alexander | -169.744
MEM | 7000 | 0 | 7000 | -27.87% | Edgars | -1950.9127
698205.1496

## 29
Object costs | [7 empty] | KPI
|  | Novembris |  | Decembris |  | Total |  | Object address | execution of contract | [10 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 0 |  | 0 |  | 0 | 0 | Time shedule, weeks | 31/10-6/11 | 7/11-13/11 | 14/11-20/11 | 21/11-27/11 | 28/11/-05/12 | [5 empty] | total | planned | 100% | Time shedule, weeks | 31/10-6/11 | 7/11-13/11 | 14/11-20/11 | 21/11-27/11 | 28/11/-05/12 | [6 empty] | total
Objekta tiešie izdevumi | Direct costs | 0 |  | 0 |  | 0 | 0 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | in fact | #DIV/0! |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment |  | 0 |  | 0 | 0 | 0 |  | 20% | 40% | 60% | 80% | 100% | [5 empty] | 100% | hours per m2 |  |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0
materiālu piegādes izdevumi | delivery |  |  |  |  | 0 | [12 empty] | 0% | planned | #DIV/0! | [12 empty] | 0
apakšuzņēmēji | subcontractors |  |  |  |  | 0 | [6 empty] | #DIV/0! | [5 empty] | #DIV/0! | in fact | #DIV/0!
darba algas | salaries |  | 0 |  | 0 | 0 | 0
DD VSAOI | tax for salaries | 0 |  | 0 |  | 0 | [13 empty] | Contract amount EUR
uzkrājums atvaļinājumam | vacation allowance | 0 |  | 0 |  | 0 | [13 empty] | Additional works, EUR
administratīvie izdevumi 7% | administrative costs 7% | 0 |  | 0 |  | 0
komandējuma dienas naudas | travel allowance |  |  |  |  | 0 | [13 empty] | square m2
komandējuma izdevumi- naktsmītne | travel expenses (hotels) |  | 0 |  | 0 | 0 | 0 | [12 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) |  |  |  |  | 0 | [13 empty] | m2<50 | 13
citi izdevumi | other expenses |  |  |  |  | 0 | [13 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
[8 empty] | Object address | materials and equipments costs | [10 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 31/10-6/11 | 7/11-13/11 | 14/11-20/11 | 21/11-27/11 | 28/11/-05/12 | [5 empty] | total | planned |  | Time shedule, weeks | 1: 31/10-6/11; 2: 7/11-13/11; 3: 14/11-20/11; 4: 21/11-27/11; 5: 28/11/-05/12 | total
Materials, incl.delivery, and subcontractors | #DIV/0! | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | in fact | 0 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | #DIV/0! | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | travel and living costs |  |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
Other costs | #DIV/0! | [17 empty] | 0 | planned | [13 empty] | 0
[20 empty] | in fact | 0
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
|  | 11672.4 | 11672.4 | 16574.808
|  | 18779.6 | 18779.6 | 26667.032
|  |  | CALZ | INT | TOTAL | INT | total
|  | contract | 74000 | 65224.74 | 139224.74 | 76000 | 150000
|  | 30% | 22200 | 19567.42 | 41767.42 | 22800 | 45000
|  | 70% | 51800 | 45657.32 | 97457.32 | 53200 | 105000
|  |  |  | 19567.42 | 41767.42

## 28
Levi's Outlet Berlin Wustermark Alter Spandauer Weg 1 14641 Wustermark Germany 27/10/2023-02/12/2023
Object costs | [7 empty] | KPI
[6 empty] | Total |  | Object address | execution of contract | [10 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 364465.27 |  |  |  | 364465.27 | 0 | Time shedule, weeks | 27/10-05/11 | 06/11-12/11 | 13/11-19/11 | 20/11-25/11 | 26/11-2/12 | [5 empty] | total | planned | 80% | Time shedule, weeks | 27/10-05/11 | 06/11-12/11 | 13/11-19/11 | 20/11-25/11 | 26/11-2/12 | [6 empty] | total
Objekta tiešie izdevumi | Direct costs | 0 |  | 0 |  | 0 | 0 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | in fact | 0% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment |  | 0 |  | 0 | 0 | 0 |  | 20% | 40% | 60% | 80% | 100% | [5 empty] | 100% | hours per m2 |  |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0
materiālu piegādes izdevumi | delivery |  |  |  |  | 0 | [12 empty] | 0% | planned | #DIV/0! | [12 empty] | 0
apakšuzņēmēji | subcontractors |  |  |  |  | 0 | [12 empty] | 0% | in fact | #DIV/0!
darba algas | salaries |  | 0 |  | 0 | 0 | 0
DD VSAOI | tax for salaries | 0 |  | 0 |  | 0 | [13 empty] | Contract amount EUR | 364465.27
uzkrājums atvaļinājumam | vacation allowance | 0 |  | 0 |  | 0 | [13 empty] | Additional works, EUR
administratīvie izdevumi 7% | administrative costs 7% | 0 |  | 0 |  | 0
komandējuma dienas naudas | travel allowance |  |  |  |  | 0 | [13 empty] | square m2
komandējuma izdevumi- naktsmītne | travel expenses (hotels) |  | 0 |  | 0 | 0 | 0 | [12 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) |  |  |  |  | 0 | [13 empty] | m2<50 | 13
citi izdevumi | other expenses |  |  |  |  | 0 | [13 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 364465.27 | 100% | 0 | #DIV/0! | 364465.27 | 100%
[8 empty] | Object address | materials and equipments costs | [10 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 27/10-05/11 | 06/11-12/11 | 13/11-19/11 | 20/11-25/11 | 26/11-2/12 | [5 empty] | total | planned |  | Time shedule, weeks | 1: 27/10-05/11; 2: 06/11-12/11; 3: 13/11-19/11; 4: 20/11-25/11; 5: 26/11-2/12 | total
Materials, incl.delivery, and subcontractors | #DIV/0! | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | in fact | 0 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | #DIV/0! | [7 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | travel and living costs |  |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
Other costs | #DIV/0! | [17 empty] | 0 | planned | [13 empty] | 0
[20 empty] | in fact | 0
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
|  |  | CALZ | INT | TOTAL
|  | contract, SEK | 32590.97 | 65224.74 | 97815.71
|  | 30% | 9777.29 | 19567.42 | 29344.71
|  | 40% | 13036.39 | 26089.9 | 39126.29
|  | 30% | 9777.29 | 19567.42 | 29344.71
BuildUp invoices 10/2022
optimera | 9810899 | 19937.67
| 54846415 | 23771.54
| 54949441 | 88.18
| 54949433 | 423.64
| 54865126 | 2827.29
| Total SEK | 47048.32
| Total EUR | 4234.3488
BuildUp invoices 11/2022
optimera | 55160170 | 3492.98
| 55145551 | 1256.02
| 55145544 | 769.6
| 55129308 | 5469.82
| 55309603 | 5055.66
| 55504898 | 1619.72
| 55252290 | 506.34
| 55268189 | 3765.85
| 55537336 | 892.88
| 55554422 | 721.22
| 55626949 | 539.45
| 55626931 | 877.68
| 55554414 | 588.84
| 55537328 | 3238.31
City Glas | 20122159 | 9750
Cramo | 10834637 | 999
| 10854596 | 488
| Total SEK | 40031.37
| Total EUR | 3602.8233

## 27
Object costs | [7 empty] | KPI
[6 empty] | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 0 |  | 0 |  | 0 | 0 | Time shedule, weeks | [6 empty] | total | planned | 100% | Time shedule, weeks | [11 empty] | total
Objekta tiešie izdevumi | Direct costs | 0 |  | 0 |  | 0 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | #DIV/0! |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment |  | 0 |  | 0 | 0 | 0 |  | 25% | 50% | 75% | 100% |  |  | 100% | hours per m2 |  |  | 1: 0; 2: 0; 3: 0; 4: 0
materiālu piegādes izdevumi | delivery |  |  |  |  | 0 | [8 empty] | 0% | planned | #DIV/0! | [12 empty] | 0
apakšuzņēmēji | subcontractors |  |  |  |  | 0 | [7 empty] | #DIV/0! | #DIV/0! | in fact | #DIV/0!
darba algas | salaries |  | 0 |  | 0 | 0 | 0
DD VSAOI | tax for salaries | 0 |  | 0 |  | 0 | [9 empty] | Contract amount EUR
uzkrājums atvaļinājumam | vacation allowance | 0 |  | 0 |  | 0 | [9 empty] | Additional works, EUR
administratīvie izdevumi 7% | administrative costs 7% | 0 |  | 0 |  | 0
komandējuma dienas naudas | travel allowance |  |  |  |  | 0 | [9 empty] | square m2
komandējuma izdevumi- naktsmītne | travel expenses (hotels) |  | 0 |  | 0 | 0 | 0 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) |  |  |  |  | 0 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses |  |  |  |  | 0 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | [6 empty] | total | planned |  | Time shedule, weeks | [11 empty] | total
Materials, incl.delivery, and subcontractors | #DIV/0! | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 0 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | #DIV/0! | [7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | travel and living costs |  |  | 1: 0; 2: 0; 3: 0; 4: 0 | 0
Other costs | #DIV/0! | [13 empty] | 0 | planned | [13 empty] | 0
[16 empty] | in fact | 0
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
Līgums | 30% | 60% | 10% | kontrole
344777.91 | 103433.37 | 206866.75 | 34477.79 | 344777.91
377423.34 | 113227 | 226454 | 37742.33 | 377423.33
11.493 | kurss 14/07
29998.95 | 8999.68 | 17999.37 | 2999.89 | 29998.94
32839.41 | 9851.82 | 19703.65 | 3283.94 | 32839.41
Kurss Māra aprēķinos
11.62
62151.57
686.79

## FAL (2)
FAL2 | Falconeri and Calzedonia, Stockholm, Wastermalm, Sweden 29/11/2023-15/12/2023
Object costs | [9 empty] | KPI
|  | Novembris/decembris | [5 empty] | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 18614.6 |  | 0 |  |  |  | 18614.6 | 0 | Time shedule, weeks | [6 empty] | total | planned | 100% | Time shedule, weeks | 29/11-03/12 | 04/12-10/12 | 11/12-17/12 | [8 empty] | total
Objekta tiešie izdevumi | Direct costs | 12552.0151 |  | 0 |  | 0 |  | 12552.0151 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 100% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 1780.44 | 2100.44 |  | 0 |  | 0 | 1780.44 | 2100.44 |  | 25% | 50% | 75% | 100% |  |  | 100% | hours per m2 |  |  | 29/11-03/12 1: 0; 04/12-10/12 2: 0; 11/12-17/12 3: 0; 11/12-17/12 4: 0
materiālu piegādes izdevumi | delivery | [6 empty] | 0 | [8 empty] | 0% | planned | #DIV/0! |  | 29/11-03/12 1: 82.13; 04/12-10/12 2: 109.56; 11/12-17/12 3: 81.3 | 272.99
apakšuzņēmēji | subcontractors | 320 | [5 empty] | 320 | [7 empty] | 0% | 0% | in fact | #DIV/0!
darba algas | salaries | 2999.1962 | 7556.2651 |  | 0 |  | 0 | 2999.1962 | 7556.2651
DD VSAOI | tax for salaries | 707.5104 |  |  |  | 0 |  | 707.5104 | [9 empty] | Contract amount EUR | 18614.6
uzkrājums atvaļinājumam | vacation allowance | 296.5365 |  |  |  | 0 |  | 296.5365 | [9 empty] | Additional works, EUR
administratīvie izdevumi 7% | administrative costs 7% | 1303.022 | [5 empty] | 1303.022
komandējuma dienas naudas | travel allowance | 2250 | [5 empty] | 2250 | [9 empty] | square m2
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 1530 | 2895.31 |  | 0 |  | 0 | 1530 | 2895.31 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 795.87 | [5 empty] | 795.87 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 569.44 | [5 empty] | 569.44 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 6062.5849 | 32.57% | 0 | #DIV/0! | 0 | #DIV/0! | 6062.5849 | 32.57%
[10 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 29/11-03/12 1: travel and living costs
Direct costs | % | [8 empty] | Time shedule, weeks | [6 empty] | total | planned |  | Time shedule, weeks | [11 empty] | total
Materials, incl.delivery, and subcontractors | 16.7339 | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 1780.44 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 60.1996 | [9 empty] | 0 | 0 | 0 | 0 |  |  | 0 | travel and living costs |  |  | 1: 0; 2: 0; 3: 0; 4: 0 | 0
Other costs | 23.0665 | [15 empty] | 0 | planned |  |  | 1: 2030.97 | 2030.97
[18 empty] | in fact | 2030.97 | bar: 2
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-02-08
Optimera | 65419624 | 540.76

## BER2
BER2 | Levis Berlin, Alter Spandauer Weg 1 14641 Wustermark Germany, 30/11/2023-20/12/2023
Object costs | [7 empty] | KPI
|  | Oktobris/ novembris |  | Decembris |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours | [11 empty] | 52413.7589
Objekta ieņēmumi kopā | Budget total | 271703.9133 |  | 135318.6233 |  | 407555.87 | 0 | Time shedule, weeks | 27/10-05/11 | 06/11-12/11 | 13/11-19/11 | 20/11-25/11 | 26/11-2/12 |  | total | planned | 100% | Time shedule, weeks | 30/10-05/11 | 06/11-12/11 | 13/11-19/11 | 20/11-25/11 | 26/11-3/12 | 4/12-10/12 | 11/12-17/12 | 18/12-20/12 |  |  |  | total | 18.1911
Objekta tiešie izdevumi | Direct costs | 173492.4345 |  | 105882.702 |  | 279375.1365 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 0.3941% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 44498.18 | 98904.38 | 16105.53 | 74066.44 | 60603.71 | 172970.82 |  | 20% | 40% | 60% | 80% | 100% |  | 100% | hours per m2 |  |  | 360.125 | 360.125 | 360.125 | 360.125 | 360.125 | 360.125 | 360.125 | 360.125 |  |  |  | 2881
materiālu piegādes izdevumi | delivery | 650 |  | 4710 |  | 5360 | [8 empty] | 0% | planned | 6.5477 |  | 226.48 | 443.2 | 469.38 | 476.6 | 382.7 | 538.57 | 245.39 | 98.97 |  |  |  | 2881.29
apakšuzņēmēji | subcontractors | 53756.2 |  | 53250.91 |  | 107007.11 |  |  |  | 0.3941% |  |  |  |  | 0.3941% | in fact | 6.5484
darba algas | salaries | 17012.7786 | 53827.4545 | 8882.1 | 27077.882 | 25894.8786 | 80905.3365
DD VSAOI | tax for salaries | 4013.3145 |  | 2095.2874 |  | 6108.6019 | [9 empty] | Contract amount EUR | 405955.87
uzkrājums atvaļinājumam | vacation allowance | 1682.0874 |  | 878.191 |  | 2560.2784 | [9 empty] | Additional works, EUR | 1600
administratīvie izdevumi 7% | administrative costs 7% | 19019.2739 |  | 9472.3036 |  | 28491.5776
komandējuma dienas naudas | travel allowance | 12100 |  | 5750 |  | 17850 | [9 empty] | square m2 | 440
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 12939.98 | 20760.6 | 687.49 | 4738.38 | 13627.47 | 25498.98 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 2913.37 |  | 1675.42 |  | 4588.79 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 4907.25 |  | 2375.47 |  | 7282.72 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 98211.4789 | 36.15% | 29435.9213 | 21.75% | 128180.7335 | 31.45%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 27/10-05/11 | 06/11-12/11 | 13/11-19/11 | 20/11-25/11 | 26/11-2/12 |  | total | planned | 69489 | Time shedule, weeks | 30/10-05/11 | 06/11-12/11 | 13/11-19/11 | 20/11-25/11 | 26/11-3/12 | 4/12-10/12 | 11/12-17/12 | 18/12-20/12 |  |  |  | total
Materials, incl.delivery, and subcontractors | 61.9135 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 65963.71 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 28.9594 | [7 empty] | 17372.25 | 17372.25 | 17372.25 | 17372.25 |  |  | 69489 | travel and living costs |  |  | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 |  |  |  | 10400
Other costs | 9.1271 | [13 empty] | 0 | planned | 10400 |  | 7223.22 | 2876.16 | 4059.71 | 1694.15 |  | 1819.42 | 325.69 | 217.8 |  |  |  | 18216.15
[16 empty] | in fact | 18216.15
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-03-04

## SIEC
SIEC | Calzedonia and Intimissimi Galerie (City-Galerie Siegen) Am Bahnhof 40, 57072 Siegen, Vācija, 31/10-27/11/2023
Object costs | [7 empty] | KPI
|  | Oktobris/novembris |  | Decembris |  | Total |  | Object address | execution of contract | [10 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 82261.75 |  |  |  | 82261.75 | 1019.94 | Time shedule, weeks | 31/10-6/11 | 7/11-13/11 | 14/11-20/11 | 21/11-27/11 | [6 empty] | total | planned | 100% | Time shedule, weeks | 31/10-6/11 | 7/11-13/11 | 14/11-19/11 | 20/11-27/11 | 28/11-30/11 | [6 empty] | total
Objekta tiešie izdevumi | Direct costs | 47770.4285 |  | 5643.839 |  | 53414.2675 | 682.811 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | in fact | 104.1% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 11009.67 | 13315.01 | 531.5 | 1307.35 | 11541.17 | 14622.36 |  | 25% | 50% | 75% | 100% | [6 empty] | 100% | hours per m2 |  |  | 1: 203.988; 2: 203.988; 3: 203.988; 4: 203.988; 5: 203.988 | 1019.94
materiālu piegādes izdevumi | delivery | 2130 |  |  |  | 2130 | [12 empty] | 100% | planned | 7.9521 |  | 1: 155.37; 2: 213.71; 3: 121.13; 4: 192.601; 5: 163.51; 6: 61.67 | 682.811
apakšuzņēmēji | subcontractors | 175.34 |  | 775.85 |  | 951.19 | [7 empty] | 4.129% |  |  |  |  | 4.129% | in fact | 5.3236
darba algas | salaries | 9905.1119 | 27229.3885 | 1600.34 | 2886.089 | 11505.4519 | 30115.4775
DD VSAOI | tax for salaries | 2336.6159 |  | 377.5202 |  | 2714.1361 | [13 empty] | Contract amount EUR | 79000
uzkrājums atvaļinājumam | vacation allowance | 979.3382 |  | 158.2288 |  | 1137.567 | [13 empty] | Additional works, EUR | 3261.75
administratīvie izdevumi 7% | administrative costs 7% | 5758.3225 |  | 0 |  | 5758.3225
komandējuma dienas naudas | travel allowance | 8250 |  | 750 |  | 9000 | [13 empty] | square m2 | 128.26
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 4636 | 7226.03 | 802.17 | 1450.4 | 5438.17 | 8676.43 | [12 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1029.35 |  |  |  | 1029.35 | [13 empty] | m2<50 | 13
citi izdevumi | other expenses | 1560.68 |  | 648.23 |  | 2208.91 | [13 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 34491.3215 | 41.93% | -5643.839 | #DIV/0! | 28847.4825 | 35.07%
[8 empty] | Object address | materials and equipments costs | [10 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 31/10-6/11 | 7/11-13/11 | 14/11-20/11 | 21/11-27/11 | [6 empty] | total | planned | 13878.94 | Time shedule, weeks | 1: 31/10-6/11; 2: 7/11-13/11; 3: 14/11-20/11; 4: 21/11-27/11 | total
Materials, incl.delivery, and subcontractors | 27.3754 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | in fact | 13671.17 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 56.381 | [7 empty] | 2313.1567 | 2313.1567 | 2313.1567 | 2313.1567 | 2313.1567 | 2313.1567 |  |  |  |  | 13878.94 | travel and living costs |  |  | 31/10-6/11 1: 1500; 7/11-13/11 2: 1500; 14/11-20/11 3: 1500; 21/11-27/11 4: 1500; 21/11-27/11 5: 1500; 21/11-27/11 6: 1500 | 7500
Other costs | 16.2437 | [17 empty] | 0 | planned | 7500 |  | 31/10-6/11 1: 3407.21; 7/11-13/11 2: 33.5; 14/11-20/11 3: 1320; 21/11-27/11 5: 802.17 | 5562.88
[20 empty] | in fact | 6467.52
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-02-12

## TAL2
TAL2 | SC Viru Keskus Viru valjak 406 10111 Tallinn, 23/10/21023-23/11/2023
Object costs | [7 empty] | KPI
|  | Oktobris |  | Novembris |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 24087.19 |  | 96348.76 |  | 120435.95 | 0 | Time shedule, weeks | 23/10-29/10 | 30/10-5/11 | 6/11-12/11 | 13/11-19/11 | 20/11-23/11 |  | total | planned | 100% | Time shedule, weeks | 23/10-29/10 | 30/10-5/11 | 6/11-12/11 | 13/11-19/11 | 20/11-23/11 | [6 empty] | total
Objekta tiešie izdevumi | Direct costs | 19364.9911 |  | 88208.5578 |  | 107573.5489 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 127.9% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 9604.8 | 10144.8 | 3607.87 | 54604.16 | 13212.67 | 64748.96 |  | 20% | 40% | 60% | 80% | 100% |  | 100% | hours per m2 |  |  | 1: 243.4; 2: 243.4; 3: 243.4; 4: 243.4; 5: 243.4 | 1217
materiālu piegādes izdevumi | delivery | 540 |  | 3210 |  | 3750 | [8 empty] | 100% | planned | 11.4887 |  | 1: 226; 2: 167.88; 3: 268.12; 4: 374.94; 5: 436.12; 6: 45.76 | 1518.82
apakšuzņēmēji | subcontractors |  |  | 47786.29 |  | 47786.29 | [6 empty] | 27.93% |  | 27.93% | in fact | 14.338
darba algas | salaries | 2626.1622 | 6991.4311 | 14043.6154 | 32009.4378 | 16669.7776 | 39000.8689
DD VSAOI | tax for salaries | 619.5117 |  | 3312.8889 |  | 3932.4005 | [9 empty] | Contract amount EUR | 94138.97
uzkrājums atvaļinājumam | vacation allowance | 259.6539 |  | 1388.5203 |  | 1648.1743 | [9 empty] | Additional works, EUR | 26296.98
administratīvie izdevumi 7% | administrative costs 7% | 1686.1033 |  | 6744.4132 |  | 8430.5165
komandējuma dienas naudas | travel allowance | 1800 |  | 6520 |  | 8320 | [9 empty] | square m2 | 105.93
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 1658.75 | 2228.76 | 929.37 | 1594.96 | 2588.12 | 3823.72 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 191 |  | 107.08 |  | 298.08 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 379.01 |  | 558.51 |  | 937.52 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 4722.1989 | 19.6% | 8140.2022 | 8.449% | 12862.4011 | 10.68%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 23/10-29/10 | 30/10-5/11 | 6/11-12/11 | 13/11-19/11 | 20/11-23/11 |  | total | planned | 12388 | Time shedule, weeks | 1: 23/10-29/10; 2: 30/10-5/11; 3: 6/11-12/11; 4: 13/11-19/11; 5: 20/11-23/11 | total
Materials, incl.delivery, and subcontractors | 60.1904 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 16962.67 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 36.2551 | [7 empty] | 2064.6667 | 2064.6667 | 2064.6667 | 2064.6667 | 2064.6667 | 2064.6667 | 12388 | travel and living costs |  |  | 1: 1180; 2: 1180; 3: 1180; 4: 1180; 5: 1180; 6: 1180 | 5900
Other costs | 3.5545 | [13 empty] | 0 | planned | 5900 |  | 1: 1849.75; 2: 16; 3: 145.5; 4: 236; 5: 203.35; 6: 435.6 | 2886.2
[16 empty] | in fact | 2886.2
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-01-09
|  | 30% | 40% | 30%
Calzedonia | 39746.19 | 11923.86 | 15898.48 | 11923.85 | 39746.19
Intimissimi | 54392.78 | 16317.83 | 21757.11 | 16317.84 | 54392.78
Kopā | 94138.97 | 28241.69 | 37655.59 | 28241.69 | 94138.97
Papilddarbi | 26296.98
Apakšuzņēmēji | 24053.55

## CHA
CHA | Chanel, Jakobsbergsgatan 6, 111 44 Stockholm, Sweden, 02/10-23/11/2023
Object costs | [9 empty] | KPI
|  | Oktober |  | Novembris |  | Decembris |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 35155 |  | 48770.2 |  | 2360 |  | 86285.2 | 875 | Time shedule, weeks | 02/10-08/10 | 09/10-15/10 | 16/10-22/10 | 23/10-29/10 | 30/10-5/11 |  | total | planned | 100% |  | Time shedule, weeks | 02/10-08/10 | 09/10-15/10 | 16/10-22/10 | 23/10-29/10 | 30/10-5/11 | 06/11-12/11 | 13/11-19/11 | 20/11-26/11 | 2023-12-01 |  |  | total
Objekta tiešie izdevumi | Direct costs | 36933.712 |  | 41145.9571 |  | 2841.1636 |  | 80920.8326 | 1599.58 |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 127.7% |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 9035.6193 | 11515.6193 | 10989.3228 | 12908.8128 | 269.6419 | 663.7819 | 20294.584 | 25088.214 |  | 25% | 50% | 75% | 100% |  |  | 100% | hours per m2 |  |  |  | 1: 175; 2: 175; 3: 175; 4: 175; 5: 175 | 875
materiālu piegādes izdevumi | delivery | 2480 |  | 1919.49 |  | 300 |  | 4699.49 | [8 empty] | 100% | planned | 6.4815 |  |  | 51.96 | 214.9 | 239 | 97.82 | 186.22 | 175.12 | 386.56 | 175 | 73 |  |  | 1599.58
apakšuzņēmēji | subcontractors |  |  |  |  | 94.14 |  | 94.14 | [5 empty] | 27.75% |  |  | 27.75% | in fact | 11.8487
darba algas | salaries | 6850.79 | 16455.0927 | 10789.2736 | 23215.1343 | 1025.24 | 1833.6616 | 18665.3036 | 41503.8886
DD VSAOI | tax for salaries | 1616.1014 |  | 2545.1896 |  | 241.8541 |  | 4403.1451 | [9 empty] | Contract amount EUR | 67542.6
uzkrājums atvaļinājumam | vacation allowance | 677.3513 |  | 1066.7571 |  | 101.3675 |  | 1845.4759 | [9 empty] | Additional works, EUR | 18742.6
administratīvie izdevumi 7% | administrative costs 7% | 2460.85 |  | 3413.914 |  | 165.2 |  | 6039.964
komandējuma dienas naudas | travel allowance | 4850 |  | 5400 |  | 300 |  | 10550 | [9 empty] | square m2 | 135
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 3685.24 | 8963 | 2548.26 | 5022.01 |  | 343.72 | 6233.5 | 14328.73 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 2318.75 |  | 1385.11 |  | 294.95 |  | 3998.81 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 2959.01 |  | 1088.64 |  | 48.77 |  | 4096.42 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | -1778.712 | -5.06% | 7624.2429 | 15.63% | -481.1636 | -20.39% | 5364.3674 | 6.217%
[10 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  |  | Object address | 1: travel and living costs
Direct costs | % | [8 empty] | Time shedule, weeks | 02/10-08/10 | 09/10-15/10 | 16/10-22/10 | 23/10-29/10 | 30/10-5/11 |  | total | planned | 20657.84 |  | Time shedule, weeks | 02/10-08/10 | 09/10-15/10 | 16/10-22/10 | 23/10-29/10 | 30/10-5/11 | 06/11-12/11 | 13/11-19/11 | 20/11-26/11 | 2023-12-01 |  |  | total
Materials, incl.delivery, and subcontractors | 31.0034 | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 24994.074 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 51.2895 | [9 empty] | 5164.46 | 5164.46 | 5164.46 | 5164.46 |  |  | 20657.84 | travel and living costs |  |  |  | 1: 0; 2: 0; 3: 0; 4: 0 | 0
Other costs | 17.7071 | [15 empty] | 0 | planned |  |  |  | 1: 3685.24; 2: 1293.61; 4: 958.99; 5: 3999.12; 9: 296 | 10232.96
[18 empty] | in fact | 10232.96
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-01-09
BuildUp invoices | [17 empty] | Additonal costs | 9930.2 |  |  | 1: 2023-11-07
Cramo | 11322711 | 1558 | Ikea | 13213.6 | [13 empty] | Mdf arround pillar | 1015 | 1 | bar: 1
[18 empty] | Change floor lewel on rised floor | 2925 | 2
[18 empty] | Change Ceiling treatment room | 1040 | 3 | bar: 1
[18 empty] | foldable table in BOH | 750 | 4 | bar: 1
optimera | 63773618 | 10106.5 | 64563604 | 2956.91 | [13 empty] | Make cuts in floor for cable pipe | 445 | 5 | bar: 1
| 63787733 | 2539.21 | 64587173 | 8274.09 | [13 empty] | Ventilation | 0 | 6 | bar: 1
| 63946016 | 424.86 | 64630353 | 3508.09 | [13 empty] | additional work request for ventilation extract grills installation in Ceiling GF | 1890 | 7 | bar: 1
| 63946008 | 869.04 | 64758576 | 1045.95 | [13 empty] | Ikea | 1865.2 | 8 | bar: 1
| 64015100 | 812.24 | 64830938 | 1512.28 | [13 empty] | Change white tiles to make treatment room size | 1500 | 9 | bar: 1
| 64116551 | 1277.49 | 64914518 | 2434.23 | [13 empty] | work acceleration on week 46 | 7042.4 | 10
| 64147721 | 1436.36 | 64845084 | 1273.52 | [14 empty] | 270 | 11
| 64163322 | 2811.07 | 65282923 | 870.22 | [14 empty] | 18742.6
9967.4
Circla | 146391 | 2190 | 147027 | 2354.75 | [14 empty] | 8775.2
| 146217 | 1232 | 147340 | 1556
|  |  | 147516 | 3326
|  |  | 147559 | 4851
|  |  | 147730 | 774
|  |  | 147803 | 1309
|  |  | 147872 | 1210
Glasbolaget |  |  | 3669 | 2632.8
Bigbag |  |  |  |  | 140617291 | 2568
| Total SEK | 25256.77 |  | 53102.44 |  | 2568
| Total EUR | 2273.1093 |  | 4645.8828 |  | 224.6719

## AMB
AMB | Postbank Amberg O0141_PB_KoMiMo_Amberg Kaiser-Ludwig-Ring 9 92224 Amberg, 09/10/2023-10/11/2023
Object costs | [7 empty] | KPI
|  | Oktober |  | November/ december |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 56240.104 |  | 14060.026 |  | 70300.13 | 0 | Time shedule, weeks | 09/10-15/10 | 16/10-22/10 | 23/10-29/10 | 30/10-5/11 | 6/11-10/11 |  | total | planned | 100% | Time shedule, weeks | 09/10-15/10 | 16/10-22/10 | 23/10-29/10 | 30/10-5/11 | 6/11-10/11 | [6 empty] | total
Objekta tiešie izdevumi | Direct costs | 32156.3777 |  | 6225.9318 |  | 38382.3095 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 0% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 8415.23 | 10733.8 | 56.94 | 1606.44 | 8472.17 | 12340.24 | [7 empty] | 0% | hours per m2 |  |  | 1: 38.4; 2: 38.4; 3: 38.4; 4: 38.4; 5: 38.4 | 192
materiālu piegādes izdevumi | delivery | 175 |  |  |  | 175 | [8 empty] | 0% | planned | 4.6829 |  | 1: 160.41; 2: 213.37; 3: 22.51 | 396.29
apakšuzņēmēji | subcontractors | 2143.57 |  | 1549.5 |  | 3693.07 | [8 empty] | 0% | in fact | 9.6656
darba algas | salaries | 5765.0373 | 15281.8177 |  | 984.2018 | 5765.0373 | 16266.0195
DD VSAOI | tax for salaries | 1359.9723 |  | 0 |  | 1359.9723 | [9 empty] | Contract amount EUR | 70300.13
uzkrājums atvaļinājumam | vacation allowance | 570.0008 |  | 0 |  | 570.0008 | [9 empty] | Additional works, EUR
administratīvie izdevumi 7% | administrative costs 7% | 3936.8073 |  | 984.2018 |  | 4921.0091
komandējuma dienas naudas | travel allowance | 3650 |  |  |  | 3650 | [9 empty] | square m2 | 41
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2839.85 | 6140.76 | 1113.59 | 3635.29 | 3953.44 | 9776.05 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 2166.03 |  | 930.57 |  | 3096.6 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 1134.88 |  | 1591.13 |  | 2726.01 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 24083.7263 | 42.82% | 7834.0942 | 55.72% | 31917.8205 | 45.4%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 09/10-15/10 | 16/10-22/10 | 23/10-29/10 | 30/10-5/11 | 6/11-10/11 |  | total | planned | 7999.61 | Time shedule, weeks | 1: 09/10-15/10; 2: 16/10-22/10; 3: 23/10-29/10; 4: 30/10-5/11; 5: 6/11-12/12 | total
Materials, incl.delivery, and subcontractors | 32.1509 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 8647.17 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 42.3789 | [7 empty] | 1999.9025 | 1999.9025 | 1999.9025 | 1999.9025 |  |  | 7999.61 | travel and living costs |  |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0 | 0
Other costs | 25.4702 | [13 empty] | 0 | planned |  |  | 1: 5046.89; 5: 1552.57 | 6599.46
[16 empty] | in fact | 6599.46
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2024-02-08

## SIE
SIE | Lewi's demolition works City - Galerie (City-Galerie Siegen) Am Bahnhof 40, 57072 Siegen, Vācija, 18/09/2023-24/09/2023
Object costs | [7 empty] | KPI
|  | Septembris 2023 |  |  |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 14005.39 |  | 3501.3475 |  | 14005.39 | 0 | Time shedule, weeks | [6 empty] | total | planned | 0% | Time shedule, weeks | [11 empty] | total
Objekta tiešie izdevumi | Direct costs | 10148.254 |  | 0 |  | 10148.254 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 0% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 826.3 | 1811.8 |  | 0 | 826.3 | 1811.8 | [7 empty] | 0% | hours per m2 |  |  | 1: 0; 2: 0; 3: 0; 4: 0
materiālu piegādes izdevumi | delivery |  |  |  |  | 0 | [8 empty] | 0% | planned | #DIV/0! |  | 1: 143.7 | 143.7
apakšuzņēmēji | subcontractors | 985.5 |  |  |  | 985.5 | [8 empty] | 0% | in fact | #DIV/0!
darba algas | salaries | 1618.6635 | 4990.924 |  | 0 | 1618.6635 | 4990.924
DD VSAOI | tax for salaries | 381.8427 |  | 0 |  | 381.8427 | [9 empty] | Contract amount EUR | 14005.39
uzkrājums atvaļinājumam | vacation allowance | 160.0405 |  | 0 |  | 160.0405 | [9 empty] | Additional works, EUR
administratīvie izdevumi 7% | administrative costs 7% | 980.3773 |  | 0 |  | 980.3773
komandējuma dienas naudas | travel allowance | 1850 |  |  |  | 1850 | [9 empty] | square m2
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 1330 | 3345.53 |  | 0 | 1330 | 3345.53 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1646.82 |  |  |  | 1646.82 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 368.71 |  |  |  | 368.71 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 3857.136 | 27.54% | 3501.3475 | 100% | 3857.136 | 27.54%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | [6 empty] | total | planned |  | Time shedule, weeks | [11 empty] | total
Materials, incl.delivery, and subcontractors | 17.8533 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 0 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 49.1801 | [7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | travel and living costs |  |  | 1: 0; 2: 0; 3: 0; 4: 0 | 0
Other costs | 32.9666 | [13 empty] | 0 | planned |  |  | 1: 2976.82 | 2976.82
[16 empty] | in fact | 2976.82
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2023-10-12
Māris/ Kristaps 17/10/2022
ceļš uz (Māris, Kristaps) | 361.48
ceļš no (Kristaps) | 116.95
ceļš no (Māris, uz Zviedriju) | 51.99
auto noma | 288.98
viesnīca Best Western 17/10/2022 (Māris) | 142
darbs?
materiāli?
961.4

## BOCH
BOCH |  | Levi's Bochum Ruhrpark GSS (28/08/2023-06/10/2023)
Object costs | [7 empty] | KPI
|  | Septembris 2023 |  | Oktobris 2023 |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 125557.59 |  | 125557.59 |  | 251115.18 |  | Time shedule, weeks | [6 empty] | total | planned | 0% | Time shedule, weeks | 28/08-03/09 | 04/09-10/09 | 11/09-17/09 | 18/09-24/09 | 25/09-01/10 | 02/10-06/10 | [5 empty] | total
Objekta tiešie izdevumi | Direct costs | 65105.8574 |  | 158126.6916 |  | 223232.5491 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 11.29% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 19754.08 | 46504.08 | -728.15 | 136679.26 | 19025.93 | 183183.34 |  | 33% | 66% | 100% |  |  |  | 100% | hours per m2 |  |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0
materiālu piegādes izdevumi | delivery |  |  | 1350 |  | 1350 |  |  | 33% | 66% | 100% |  |  |  | 100% | planned | #DIV/0! | [12 empty] | 0
apakšuzņēmēji | subcontractors | 26750 |  | 136057.41 |  | 162807.41 |  |  |  |  | 11.29% |  |  |  | 11.29% | in fact | #DIV/0!
darba algas | salaries | 3136.78 | 14475.9174 | 1114.7 | 10776.9016 | 4251.48 | 25252.8191
DD VSAOI | tax for salaries | 739.9664 |  | 262.9577 |  | 1002.9241 | [9 empty] | Contract amount EUR | 225634
uzkrājums atvaļinājumam | vacation allowance | 310.1397 |  | 110.2126 |  | 420.3523 | [9 empty] | Additional works, EUR | 25481.18
administratīvie izdevumi 7% | administrative costs 7% | 8789.0313 |  | 8789.0313 |  | 17578.0626
komandējuma dienas naudas | travel allowance | 1500 |  | 500 |  | 2000 | [9 empty] | square m2
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 1420.13 | 4125.86 |  | 10670.53 | 1420.13 | 14796.39 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1778.49 |  | 670.53 |  | 2449.02 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 927.24 |  | 10000 |  | 10927.24 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 60451.7326 | 48.15% | -32569.1016 | -25.94% | 27882.6309 | 11.1%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks |  |  | 0 | 2022-06-06 |  |  | total | planned | 0 | Time shedule, weeks | 1: 28/08-03/09; 2: 04/09-10/09; 3: 11/09-17/09; 4: 18/09-24/09; 5: 25/09-01/10; 6: 02/10-06/10 | total
Materials, incl.delivery, and subcontractors | 82.0594 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 19025.93 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 11.3123 | [7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | travel and living costs |  |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0 | 0
Other costs | 6.6282 | [13 empty] | 0 | planned | [13 empty] | 0
[16 empty] | in fact | 3869.15
[16 empty] | Subcontractors budget, EUR | 210898.37
[16 empty] | Payments to subcontractor, EUR | 129890.14
date of report
2024-02-27
Apakšuzņēmēji | kopā | 162807.65
ELEKTROMEISTER PETER SEYRING | 2023 092591 25/09/2023 | 2750
| 2023 100606 06/10/2023 | 1283.78
4033.78
ELEKTRO LAT SIA | LE49/10-2023, 03/10/2023 | 15651.51
| LE52/10-2023 23/10/2023 | 2981.23
18632.74
R82 SIA | 1908 16/10/2023 | 1200
Systeex Brandschutzsysteme Gmbh | 1023830759 13/10/2023 | 3976.59
GSS SIA | GS23075 02/10/2023 | 10973.5
| GS23076 16/10/2023 | 48000
| GS23079 06/11/2023 | 27000
| GS23086 15/12/2023 | 43916.64
129890.14
Redooo GMBH | 10003245 24/10/2023 | 428.15
| 10003422 15/11/2023 | 267.95
696.1
EL Support | 86/2023 26/10/2023 | 2008.8
| 82/2023 16/10/2023 | 2369.5
4378.3
Transports | kopā | 1350
SPARTA LOGISTISCS | 40777 04/10/2023 | 480
| 40834 06/10/2023 | 620
| 40950 13/10/2023 | 250
1350
Materiāli | kopā | 19026.01
B+M BAUSTOFF METAL | 2-2699107 28/09/2023 | 6406.31
| 2-2699106 28/09/2023 | 446.74
6853.05
ELEKTRO GM SIA | 04898 13/09/2023 | 5124.83
Boels Rental | 3422144661 21/09/2023 | 491.9
| 3422144641 21/09/2023 | 780.18
1272.08
Falcon | 2031177 23/08/2023 | 6504.2
-728.15
5776.05

## AUH
AUH | Intimissimi and Calzedonia Auhof Center Albert-Schweitzer-Gasse 6, 1140 Wien Austria 22/08/2023-05/09/2023
Object costs | [7 empty] | KPI
|  | augusts |  | septembris |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 65700 |  | 21900 |  | 87600 |  | Time shedule, weeks | 22/08-28/08 | 29/08-04/09 | 05/09-07/09 | 05/09-07/09 |  |  | total | planned | 100% | Time shedule, weeks | 22/08-28/08 | 29/08-04/09 | 05/09-07/09 | [8 empty] | total
Objekta tiešie izdevumi | Direct costs | 45139.0797 |  | 15676.5365 |  | 60815.6162 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 1.86% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 11467.99 | 13329.69 | 437.59 | 9577.19 | 11905.58 | 22906.88 |  | 33% | 66% | 100% | 100% |  |  | 100% | hours per m2 |  |  | 22/08-28/08 1: 336.6667; 29/08-04/09 2: 336.6667; 05/09-07/09 3: 336.6667; 05/09-07/09 4: 252.5 | 1010
materiālu piegādes izdevumi | delivery |  |  | 725 |  | 725 | [8 empty] | 0% | planned | 8.2402 |  | 22/08-28/08 1: 453.5; 29/08-04/09 2: 317; 05/09-07/09 3: 169.5 | 940
apakšuzņēmēji | subcontractors | 1861.7 |  | 8414.6 |  | 10276.3 |  |  |  |  | 1.86% |  |  |  | 1.86% | in fact | 7.6691
darba algas | salaries | 9789.7167 | 24166.0397 | 1063.7821 | 4602.9065 | 10853.4987 | 28768.9462
DD VSAOI | tax for salaries | 2309.3942 |  | 250.9462 |  | 2560.3404 | [9 empty] | Contract amount EUR | 86000
uzkrājums atvaļinājumam | vacation allowance | 967.9289 |  | 105.1783 |  | 1073.1071 | [9 empty] | Additional works, EUR | 1600
administratīvie izdevumi 7% | administrative costs 7% | 4599 |  | 1533 |  | 6132
komandējuma dienas naudas | travel allowance | 6500 |  | 1650 |  | 8150 | [9 empty] | square m2 | 122.57
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 5006.55 | 7643.35 |  | 1496.44 | 5006.55 | 9139.79 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 2046.15 |  |  |  | 2046.15 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 590.65 |  | 1496.44 |  | 2087.09 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 20560.9203 | 31.3% | 6223.4635 | 28.42% | 26784.3838 | 30.58%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 22/08-28/08 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 22/08-28/08 | 29/08-04/09 | 05/09-07/09 |  |  |  | total | planned | 10100.47 | Time shedule, weeks | 22/08-28/08 1: 22/08-28/08; 29/08-04/09 2: 29/08-04/09; 05/09-07/09 3: 05/09-07/09 | total
Materials, incl.delivery, and subcontractors | 37.6661 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 12630.58 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 47.3052 | [7 empty] | 2525.1175 | 2525.1175 | 2525.1175 | 2525.1175 |  |  | 10100.47 | travel and living costs |  |  | 22/08-28/08 1: 2171.5; 29/08-04/09 2: 2171.5; 05/09-07/09 3: 2171.5; 05/09-07/09 4: 2171.5 | 8686
Other costs | 15.0287 | [13 empty] | 0 | planned | 8686 |  | 22/08-28/08 1: 4769.77; 29/08-04/09 2: 2282.68 | 7052.45
[16 empty] | in fact | 7052.45
[16 empty] | Subcontractors budget, EUR | 4794
[16 empty] | Payments to subcontractor, EUR | 7058.48
date of report
2023-09-28

## FAL
FAL | Falconeri, Sturegatan 4, 114 35 Stockholm, Sweden 04/09/2023-02/10/2023, 29/11/2023-30/11/2023
Object costs | [9 empty] | KPI
|  | Septembris |  | Oktobris |  | Novembris |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 75100.2 |  | 5153.47 |  |  |  | 80253.67 | 0 | Time shedule, weeks | [6 empty] | total | planned | 100% |  | Time shedule, weeks | 04/09-10/09 | 11/09-17/09 | 18/09-24/09 | 25/09-01/10 | 02/10-06/10 | 2023-11-01 | [5 empty] | total
Objekta tiešie izdevumi | Direct costs | 45339.0418 |  | 6080.5123 |  | 0 |  | 51419.5541 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 6.862% |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 10854.474 | 11409.474 | 1172.16 | 1842.16 |  | 0 | 12026.634 | 13251.634 |  | 25% | 50% | 75% | 100% |  |  | 100% | hours per m2 |  |  |  | 1: 200.25; 2: 200.25; 3: 200.25; 4: 200.25 | 801
materiālu piegādes izdevumi | delivery | 405 |  | 270 |  |  |  | 675 | [8 empty] | 0% | planned | 9.5676 |  |  | 1: 209; 2: 209; 3: 209; 4: 216; 5: 146 | 989
apakšuzņēmēji | subcontractors | 150 |  | 400 |  |  |  | 550 | [7 empty] | 6.862% | 6.862% | in fact | 11.8132
darba algas | salaries | 9523.0225 | 23368.0777 | 2079.306 | 3986.1423 |  | 0 | 11602.3285 | 27354.2201
DD VSAOI | tax for salaries | 2246.481 |  | 490.5083 |  |  |  | 2736.9893 | [9 empty] | Contract amount EUR | 75100.2
uzkrājums atvaļinājumam | vacation allowance | 941.5603 |  | 205.5851 |  |  |  | 1147.1454 | [9 empty] | Additional works, EUR | 5153.47
administratīvie izdevumi 7% | administrative costs 7% | 5257.014 |  | 360.7429 |  |  |  | 5617.7569
komandējuma dienas naudas | travel allowance | 5400 |  | 850 |  |  |  | 6250 | [9 empty] | square m2 | 83.72
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 5023.84 | 10561.49 |  | 252.21 |  | 0 | 5023.84 | 10813.7 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 2085.48 |  | 204.29 |  |  |  | 2289.77 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 3452.17 |  | 47.92 |  |  |  | 3500.09 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 29761.1582 | 39.63% | -927.0423 | -17.99% | 0 | #DIV/0! | 28834.1159 | 35.93%
[10 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  |  | Object address | 1: travel and living costs
Direct costs | % | [8 empty] | Time shedule, weeks | [6 empty] | total | planned | 7530 |  | Time shedule, weeks | 1: 04/09-10/09; 2: 11/09-17/09; 3: 18/09-24/09; 4: 25/09-02/10; 5: 02/10-06/10; 6: 2023-11-01 | total
Materials, incl.delivery, and subcontractors | 25.7716 | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 12026.634 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 53.1981 | [9 empty] | 1882.5 | 1882.5 | 1882.5 | 1882.5 |  |  | 7530 | travel and living costs |  |  |  | 1: 1190; 2: 1190; 3: 1190; 4: 1190 | 5950
Other costs | 21.0303 | [15 empty] | 0 | planned | 5950 |  |  | 1: 4539.49; 2: 674.92; 3: 223.11; 4: 1671.52; 5: 204.29 | 7313.33
[18 empty] | in fact | 7313.33 | bar: 2
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2023-11-28
Līgums | 30% | 60% | 10% | kontrole
723835.79 | 217150.74 | 434301.47 | 72383.58 | 723835.79 |  |  |  | 723835.79
11.476 | kurss 20/07 | https://sdw.ecb.europa.eu/curConverter.do?sourceAmount=1.0&sourceCurrency=SEK&targetCurrency=EUR&inputDate=20-07-2023&submitConvert.x=73&submitConvert.y=6
63073.88 | 18922.16 | 37844.32 | 6307.4 | 63073.88 |  |  |  | 63073.88
Kurss Māra aprēķinos
11.62
62292.24
781.64
Līgums- atjaunots piedāvājums 17/08/23
774406.35
Līgums- atjaunots piedāvājums 18/09/2023
862112.72 | 75100.2 | 37844.32 | 210660.51
75100.2 |  | 18922.16 | [15 empty] | 5
|  | 18333.72 | pēdējais maksājums | [14 empty] | 4.8
72288.5058 | ECB kurss |  | -12026.32
Līgums- atjaunots piedāvājums 17/10/2023
938132.26 | 81722.4 | 75100.2 | 938132.26
81722.4 |  | 1700 | radiatoru restes
|  | 4922.2 | pēdējais maksājums par papilddarbiem
81123.1341 | ECB Kurss |  | -4922.2
Līgums- atjaunots piedāvājums 24/10/2023
921271.96 | 80253.67 | 75100.2 | 808327.44 | [14 empty] | Agreement amount
80253.67 |  | 1700 | radiatoru restes | [14 empty] | 921271.96 | EUR 80253.67
|  | 3453.47 | pēdējais maksājums par papilddarbiem
78694.1112 | ECB Kurss | 1468.73 | kredītrēķins
[18 empty] | Invoices | amount EUR | payment term |  | 1: payment recieved EUR
[18 empty] | 2023 1/FAL | 18922.16 | 2023-05-08 |  | 1: 18/08/2023; 2: 18922.16
[18 empty] | 2023 2/FAL | 37844.32 | 18/10/2023 |  | 1: 13/10/2023; 2: 37844.32
Buildup rēķini | 53575.89 | 11.5325 | [15 empty] | 2023 3/FAL | 18333.72 | 2023-04-11
|  | 4645.644 | [15 empty] | 2023 4/FAL | 1700 | 20/10/2023
Optimera, 63628846 | 2279.17
Optimera, 63548770 | 2308.37 | [16 empty] | 2023 5/FAL | 4922.2 | 18/11/2023
Optimera, 63548788 | 193.42 | [16 empty] | 2023 6/FAL | -1468.73 | 18/11/2023
Optimera, 63231930 | 2793.31 | [16 empty] | Total invocies amount EUR | 80253.67 | Total paid amount EUR26/10/203 |  | 2: 56766.48
Optimera, 62851019 | 5350.58
Optimera, 62984349 | 3480.5
Optimera, 62865639 | 1572.64
Optimera, 62939905 | 1752.26
Optimera, 62954821 | 5653.97
Optimera, 62970108 | 1950.67
Circla, 144440 | 2852
Circla, 144403 | 5564
Circla, 144352 | 4553
Circla, 144311 | 944
Circla , 145490 | 671
Circla, 144968 | 5140
Circla, 145447 | 2888
Circla, 144676 | 3629

## DOR
DOR | Calzedonia DORTMUND WESTENHELLWEG 24, 13/08-28/08
Object costs | [9 empty] | KPI | [25 empty] | 16730.3742
|  | Augusts | [5 empty] | Total |  | Object address | execution of contract | [9 empty] | execution of the contract |  | Object address | worked hours | [11 empty] | 20.0845
Objekta ieņēmumi kopā | Budget total | 80805.52 |  |  |  | 56563.864 |  | 80805.52 | 0 | Time shedule, weeks | 13/08-20/08 | 01/08-07/08 | 08/08-14/08 | 15/08-21/08 | 22/08-28/08 | 21/08-28/08 |  |  |  | total | planned | 100% | Time shedule, weeks | 13/08-20/08 | 01/08-07/08 | 08/08-14/08 | 15/08-21/08 | 22/08-28/08 | 21/08-28/08 | [5 empty] | total
Objekta tiešie izdevumi | Direct costs | 43134.1505 |  | 0 |  | 0 |  | 43134.1505 |  |  | 1 | 2 | 3 | 4 | 5 | 3 | 4 | 5 |  |  | in fact | 106.7% |  | 1 | 2 | 3 | 4 | 5 | 3 | 4 | 5 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 6176.73 | 13352.68 |  | 0 |  | 0 | 6176.73 | 13352.68 |  | 5% |  |  |  |  | 35% | 65% | 100% |  | 100% | hours per m2 |  |  | 1: 483; 3: 483; 4: 483; 5: 483 | 966
materiālu piegādes izdevumi | delivery | 1470 | [5 empty] | 1470 | [11 empty] | 100% | planned | 11.2 |  | 1: 415; 3: 418 | 833
apakšuzņēmēji | subcontractors | 5705.95 | [5 empty] | 5705.95 | [11 empty] | 6.694% | in fact | 9.658
darba algas | salaries | 9734.1 | 23349.1905 |  | 0 |  | 0 | 9734.1 | 23349.1905
DD VSAOI | tax for salaries | 2296.2742 |  | 0 |  | 0 |  | 2296.2742 | [12 empty] | Contract amount EUR | 75736.12
uzkrājums atvaļinājumam | vacation allowance | 962.4299 |  | 0 |  | 0 |  | 962.4299 | [12 empty] | Additional works, EUR | 5069.4
administratīvie izdevumi 7% | administrative costs 7% | 5656.3864 |  | 0 |  | 0 |  | 5656.3864
komandējuma dienas naudas | travel allowance | 4700 | [5 empty] | 4700 | [12 empty] | square m2 | 86.25
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 4168.15 | 6432.28 |  | 0 |  | 0 | 4168.15 | 6432.28 | [11 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1657.23 | [5 empty] | 1657.23 | [12 empty] | m2<50 | 13
citi izdevumi | other expenses | 606.9 | [5 empty] | 606.9 | [12 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 37671.3695 | 46.62% | 0 | #DIV/0! | 56563.864 | 100% | 37671.3695 | 46.62%
[10 empty] | Object address | materials and equipments costs | [9 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [8 empty] | Time shedule, weeks | 13/08-20/08 | 01/08-07/08 | 08/08-14/08 | 15/08-21/08 | 22/08-28/08 | 21/08-28/08 | 05/09-11/09 | 12/09-18/09 | 19/09-21/09 | total | planned | 10520 | Time shedule, weeks | 1: 13/08-20/08; 2: 01/08-07/08; 3: 08/08-14/08; 4: 15/08-21/08; 5: 22/08-28/08; 3: 21/08-28/08 | total
Materials, incl.delivery, and subcontractors | 30.9562 | [9 empty] | 1 | 2 | 3 | 4 | 5 | 3 | 4 | 5 |  |  | in fact | 7646.73 |  | 1 | 2 | 3 | 4 | 5 | 3 | 4 | 5 | 9 | 10 | 11
Salaries and taxes | 54.1316 | [9 empty] | 2630 |  |  |  |  | 2630 | 2630 | 2630 |  | 10520 | travel and living costs |  |  | 1: 4800; 3: 4800; 4: 4800; 5: 4800 | 9600
Other costs | 14.9123 | [18 empty] | 0 | planned | 9600 |  | 1: 4447.99; 3: 1377.38 | 5825.37
[21 empty] | in fact | 5825.37
[21 empty] | Subcontractors budget, EUR | 9555
[21 empty] | Payments to subcontractor, EUR | 5705.95
date of report
2023-09-15

## OLD
OLD | Calzedonia, Lange Strasse 70, Oldenburg, Germany, 30/07-11/08
Object costs | [9 empty] | KPI | [22 empty] | 17897.772
|  | Jūlijs 2022 |  | Augusts |  | Septembris 2022 |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours | [11 empty] | 30.2327
Objekta ieņēmumi kopā | Budget total | 0 |  | 40953.42 |  |  |  | 40953.42 |  | Time shedule, weeks | 30/07-06/08 | 07/08-11/08 |  |  |  |  | total | planned | 100% | Time shedule, weeks | 30/07-06/08 | 07/08-11/08 | 0 | 0 | [7 empty] | total
Objekta tiešie izdevumi | Direct costs | 8272.9202 |  | 28217.033 |  | 0 |  | 36489.9532 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 106.3% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 2651 | 2651 | 3949.12 | 8087.05 |  | 0 | 6600.12 | 10738.05 |  | 25% | 75% | 100% |  |  |  | 100% | hours per m2 |  |  | 30/07-06/08 1: 233; 07/08-11/08 2: 233 | 466
materiālu piegādes izdevumi | delivery |  |  | 600 |  |  |  | 600 | [8 empty] | 100% | planned | 8.0414 |  | 30/07-06/08 1: 290.5; 07/08-11/08 2: 301.5 | 592
apakšuzņēmēji | subcontractors |  |  | 3537.93 |  |  |  | 3537.93 | [8 empty] | 6.312% | in fact | 10.2157
darba algas | salaries | 1142.39 | 2174.8302 | 10345.41 | 19725.503 |  | 0 | 11487.8 | 21900.3332
DD VSAOI | tax for salaries | 269.4898 |  | 2440.4822 |  | 0 |  | 2709.972 | [9 empty] | Contract amount EUR | 38521.98
uzkrājums atvaļinājumam | vacation allowance | 112.9504 |  | 1022.8714 |  | 0 |  | 1135.8218 | [9 empty] | Additional works, EUR | 2431.44
administratīvie izdevumi 7% | administrative costs 7% | 0 |  | 2866.7394 |  | 0 |  | 2866.7394
komandējuma dienas naudas | travel allowance | 650 |  | 3050 |  |  |  | 3700 | [9 empty] | square m2 | 57.95
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2016 | 3447.09 |  | 404.48 |  | 0 | 2016 | 3851.57 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1292.16 |  | 161.98 |  |  |  | 1454.14 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 138.93 |  | 242.5 |  |  |  | 381.43 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | -8272.9202 | #DIV/0! | 12736.387 | 31.1% | 0 | #DIV/0! | 4463.4668 | 10.9%
[10 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 30/07-06/08 1: travel and living costs
Direct costs | % | [8 empty] | Time shedule, weeks | 30/07-06/08 | 07/08-11/08 | 0 | 0 |  |  | total | planned | 5385 | Time shedule, weeks | 30/07-06/08 1: 30/07-06/08; 07/08-11/08 2: 07/08-11/08; 0 3: 0; 0 4: 0 | total
Materials, incl.delivery, and subcontractors | 29.4274 | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 7200.12 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 60.0174 | [9 empty] | 1346.25 | 2692.5 | 1346.25 |  |  |  | 5385 | travel and living costs |  |  | 30/07-06/08 1: 1762.5; 07/08-11/08 2: 1762.5; 0 3: 1762.5 | 3525
Other costs | 10.5552 | [15 empty] | 0 | planned | 3525 |  | 30/07-06/08 1: 3089.9; 07/08-11/08 2: 380.24 | 3470.14
[18 empty] | in fact | 3470.14
[18 empty] | Subcontractors budget, EUR | 5865.47
[18 empty] | Payments to subcontractor, EUR | 3537.93
date of report
2023-09-15

## HAL
HAL | Intimissimi , Leipziger Strasse,11 Halle - Saal , 19/07/2023-22/08/2023
Object costs | [7 empty] | KPI | [22 empty] | 27680.7958
|  | July |  | August |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours | [11 empty] | 29.7739
Objekta ieņēmumi kopā | Budget total | 29318.956 |  | 54275.824 |  | 73297.39 |  | Time shedule, weeks | 18/07-24/07 | 25/07-31/07 | 01/08-06/08 | 07/08-13/08 | 14/08-20/08 | 21/08-22/08 | total | planned | 100% | Time shedule, weeks | 18/07-23/07 | 24/07-30/07 | 31/07-06/08 | 07/08-13/08 | 14/08-20/08 | 21/08-22/08 | [5 empty] | total
Objekta tiešie izdevumi | Direct costs | 30059.0723 |  | 32212.6718 |  | 62271.7441 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 116.3% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 8120.82 | 8281.9 | 4979.85 | 9237.2 | 13100.67 | 17519.1 |  | 20% | 40% | 60% | 80% | 90% | 100% | 100% | hours per m2 |  |  | 1: 199.2; 2: 199.2; 3: 199.2; 4: 199.2; 5: 199.2 | 996
materiālu piegādes izdevumi | delivery |  |  | 1875 |  | 1875 | [7 empty] | 100% | 100% | planned | 6.4971 |  | 1: 145; 2: 190; 3: 133.5; 4: 201.7; 5: 259.5 | 929.7
apakšuzņēmēji | subcontractors | 161.08 |  | 2382.35 |  | 2543.43 | [7 empty] | 16.35% | 16.35% | in fact | 6.0646
darba algas | salaries | 5738.22 | 13611.5423 | 9215.09 | 21399.3518 | 14953.31 | 35010.8941
DD VSAOI | tax for salaries | 1353.6461 |  | 2173.8397 |  | 3527.4858 | [9 empty] | Contract amount EUR | 63000
uzkrājums atvaļinājumam | vacation allowance | 567.3493 |  | 911.1144 |  | 1478.4637 | [9 empty] | Additional works, EUR | 10297.39
administratīvie izdevumi 7% | administrative costs 7% | 2052.3269 |  | 3799.3077 |  | 5851.6346
komandējuma dienas naudas | travel allowance | 3900 |  | 5300 |  | 9200 | [9 empty] | square m2 | 153.3
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 5836.25 | 8165.63 | 776.06 | 1576.12 | 6612.31 | 9741.75 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1934.85 |  | 617.27 |  | 2552.12 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 394.53 |  | 182.79 |  | 577.32 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | -740.1163 | -2.524% | 22063.1522 | 40.65% | 11025.6459 | 15.04%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 18/07-24/07 | 25/07-31/07 | 01/08-06/08 | 07/08-13/08 | 14/08-20/08 | 21/08-22/08 | total | planned | 13034 | Time shedule, weeks | 1: 18/07-23/07; 2: 24/07-30/07; 3: 31/07-06/08; 4: 07/08-13/08; 5: 14/08-20/08; 6: 21/08-22/08 | total
Materials, incl.delivery, and subcontractors | 28.1333 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 14975.67 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 56.2228 | [7 empty] | 3258.5 | 3258.5 | 3258.5 | 3258.5 |  |  | 13034 | travel and living costs |  |  | 1: 1080; 2: 1080; 3: 1080; 4: 1350; 5: 1350 | 5400
Other costs | 15.6439 | [13 empty] | 0 | planned | 5400 |  | 1: 4134.64; 2: 3635.98; 3: 526.37; 4: 60.7; 5: 807.21 | 9164.9
[16 empty] | in fact | 9164.9
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2023-09-15

## MEM
MEM | Calzedonia and Intimissimi Weinmarkt 1, 87700 Memmingen, Germany, 09/07-18/07
Object costs | [7 empty] | KPI
|  | Jūlijs |  |  |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 7000 |  | 1750 |  | 7000 |  | Time shedule, weeks | 08/07-12/07 | [5 empty] | total | planned | 100% | Time shedule, weeks | 08/07-12/07 | [10 empty] | total
Objekta tiešie izdevumi | Direct costs | 8950.9127 |  | 0 |  | 8950.9127 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 0% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 581.24 | 2361.4 |  | 0 | 581.24 | 2361.4 |  | 100% | [5 empty] | 100% | hours per m2 |  |  | 08/07-12/07 1: 0
materiālu piegādes izdevumi | delivery |  |  |  |  | 0 | [8 empty] | 0% | planned | 0 |  | 08/07-12/07 1: 126 | 126
apakšuzņēmēji | subcontractors | 1780.16 |  |  |  | 1780.16 | [8 empty] | 0% | in fact | 126
darba algas | salaries | 2152.01 | 4512.4427 |  | 0 | 2152.01 | 4512.4427
DD VSAOI | tax for salaries | 507.6592 |  | 0 |  | 507.6592 | [9 empty] | Contract amount EUR | 7000
uzkrājums atvaļinājumam | vacation allowance | 212.7735 |  | 0 |  | 212.7735 | [9 empty] | Additional works, EUR
administratīvie izdevumi 7% | administrative costs 7% | 490 |  | 0 |  | 490
komandējuma dienas naudas | travel allowance | 1150 |  |  |  | 1150 | [9 empty] | square m2 | 138.95
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 1515.27 | 2077.07 |  | 0 | 1515.27 | 2077.07 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 237 |  |  |  | 237 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 324.8 |  |  |  | 324.8 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | -1950.9127 | -27.87% | 1750 | 100% | -1950.9127 | -27.87%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 08/07-12/07 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 04/07-10/07 | 11/07-17/07 | 18/07-24/07 | 0 |  |  | total | planned |  | Time shedule, weeks | 08/07-12/07 1: 08/07-12/07 | total
Materials, incl.delivery, and subcontractors | 26.3817 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 581.24 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 50.4132 | [7 empty] | 0 | 0 | 0 | 0 |  |  | 0 | travel and living costs |  |  | 08/07-12/07 1: 0 | 0
Other costs | 23.2051 | [13 empty] | 0 | planned |  |  | 08/07-12/07 1: 2130.96 | 2130.96
[16 empty] | in fact | 2130.96
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2023-08-04
NL | 1498.044 | 5988.55
materiāli | 76.11
algas | -315.896
komandējuma nauda | 480
dzīvošana | 1342.22
ceļš | 341.67

## ARN
ARN |  | Calzedonia, Vijzelstraat 1C, 6811 ES Arnhem, Netherlands 01/07/2023-25/07/2023
Object costs | [7 empty] | KPI
|  | Jūlijs |  |  |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 60000 |  |  |  | 65603.51 | 0 | Time shedule, weeks | 30/06-09/07 | 10/07-16/07 | 17/07-23/07 | 24/07-30/07 |  |  | total | planned | 100% | Time shedule, weeks | 30/06-09/07 | 10/07-16/07 | 17/07-23/07 | 24/07-30/07 | [7 empty] | total
Objekta tiešie izdevumi | Direct costs | 44727.5098 |  | 0 |  | 44727.5098 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 109.3% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 6617.67 | 20985.67 |  | 0 | 6617.67 | 20985.67 |  | 25% | 50% | 75% | 100% |  |  | 100% | hours per m2 |  |  | 30/06-09/07 1: 135.75; 10/07-16/07 2: 135.75; 17/07-23/07 3: 135.75; 24/07-30/07 4: 135.75 | 543
materiālu piegādes izdevumi | delivery | 770 |  |  |  | 770 | [8 empty] | 100% | planned | 6.1224 |  | 30/06-09/07 1: 150; 10/07-16/07 2: 168; 17/07-23/07 3: 206; 24/07-30/07 4: 28 | 552
apakšuzņēmēji | subcontractors | 13598 |  |  |  | 13598 | [8 empty] | 9.339% | in fact | 6.2239
darba algas | salaries | 3037.38 | 14374.2098 |  | 0 | 3037.38 | 14374.2098
DD VSAOI | tax for salaries | 716.5179 |  | 0 |  | 716.5179 | [9 empty] | Contract amount EUR | 60000
uzkrājums atvaļinājumam | vacation allowance | 300.3118 |  | 0 |  | 300.3118 | [9 empty] | Additional works, EUR | 5603.51
administratīvie izdevumi 7% | administrative costs 7% | 4200 |  | 0 |  | 4200
komandējuma dienas naudas | travel allowance | 6120 |  |  |  | 6120 | [9 empty] | square m2 | 88.69
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 6363.65 | 9367.63 |  | 0 | 6363.65 | 9367.63 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1566.79 |  |  |  | 1566.79 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 1437.19 |  |  |  | 1437.19 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 15272.4902 | 25.45% | 0 | #DIV/0! | 20876.0002 | 31.82%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 30/06-09/07 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 30/06-09/07 | 10/07-16/07 | 17/07-23/07 | 24/07-30/07 |  |  | total | planned | 6400 | Time shedule, weeks | 30/06-09/07 1: 30/06-09/07; 10/07-16/07 2: 10/07-16/07; 17/07-23/07 3: 17/07-23/07; 24/07-30/07 4: 24/07-30/07 | total
Materials, incl.delivery, and subcontractors | 46.9189 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 7387.67 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 32.1373 | [7 empty] | 1600 | 1600 | 1600 | 1600 |  |  | 6400 | travel and living costs |  |  | 30/06-09/07 1: 1500; 10/07-16/07 2: 1500; 17/07-23/07 3: 1500; 24/07-30/07 4: 1500 | 6000
Other costs | 20.9438 | [13 empty] | 0 | planned | 6000 |  | 30/06-09/07 1: 4955.82; 10/07-16/07 2: 1006.74; 17/07-23/07 3: 1022.94; 24/07-30/07 4: 197.9 | 7183.4
[16 empty] | in fact | 7183.4
[16 empty] | Subcontractors budget, EUR | 15394.08
[16 empty] | Payments to subcontractor, EUR | 12493.28
date of report
2023-08-03

## NEU
NEU | Postbank Neumarkt, 30/05-5/07/2023
Object costs | [9 empty] | KPI
|  | Maijs |  | Jūnijs |  | Jūlijs |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 3563.6865 |  | 60582.6705 |  | 7127.373 |  | 71273.73 | 0 | Time shedule, weeks | 30/05-04/06 | 05/06-11/06 | 12/06-18/06 | 19/06-25/06 |  |  | total | planned | 100% | Time shedule, weeks | 30/05-04/06 | 05/06-11/06 | 12/06-18/06 | 19/06-25/06 | [7 empty] | total
Objekta tiešie izdevumi | Direct costs | 3645.2914 |  | 24136.7518 |  | 22946.7165 |  | 50728.7597 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 0% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 910.27 | 910.27 | 4472.68 | 4847.28 | 3682.58 | 8968.49 | 9065.53 | 14726.04 |  | 25% | 50% | 75% | 100% |  |  | 100% | hours per m2 |  |  | 30/05-04/06 1: 139; 05/06-11/06 2: 139; 12/06-18/06 3: 139; 19/06-25/06 4: 139; 19/06-25/06 5: 139 | 695
materiālu piegādes izdevumi | delivery | [6 empty] | 0 | [8 empty] | 0% | planned | 8.3035 |  | 30/05-04/06 1: 57; 05/06-11/06 2: 157; 12/06-18/06 3: 247; 19/06-25/06 4: 45; 19/06-25/06 5: 195 | 701
apakšuzņēmēji | subcontractors |  |  | 374.6 |  | 5285.91 |  | 5660.51 | [8 empty] | 0% | in fact | 8.3751
darba algas | salaries | 484.22 | 1195.7814 | 3869.3986 | 13005.5518 | 3586.92 | 7836.6365 | 7940.5386 | 22037.9697
DD VSAOI | tax for salaries | 114.2275 |  | 912.7911 |  | 846.1544 |  | 1873.173 | [9 empty] | Contract amount EUR | 71273.73
uzkrājums atvaļinājumam | vacation allowance | 47.8758 |  | 382.5752 |  | 354.646 |  | 785.0969 | [9 empty] | Additional works, EUR | 800
administratīvie izdevumi 7% | administrative costs 7% | 249.4581 |  | 4240.7869 |  | 498.9161 |  | 4989.1611
komandējuma dienas naudas | travel allowance | 300 |  | 3600 |  | 2550 |  | 6450 | [9 empty] | square m2 | 83.7
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 887.85 | 1539.24 | 2979.54 | 6283.92 | 3058.33 | 6141.59 | 6925.72 | 13964.75 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 152.83 |  | 3007.59 |  | 1791.59 |  | 4952.01 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 498.56 |  | 296.79 |  | 1291.67 |  | 2087.02 | [9 empty] | 50<m2<100 | 12
0
peļņa bruto | profit/ loss | -81.6049 | -2.29% | 36445.9187 | 60.16% | -15819.3435 | -222% | 20544.9703 | 28.83%
[10 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 30/05-04/06 1: travel and living costs
Direct costs | % | [8 empty] | Time shedule, weeks | 30/05-04/06 | 05/06-11/06 | 12/06-18/06 | 19/06-25/06 | 11/07-14/07 |  | total | planned | 11041.63 | Time shedule, weeks | 30/05-04/06 1: 30/05-04/06; 05/06-11/06 2: 05/06-11/06; 12/06-18/06 3: 12/06-18/06; 19/06-25/06 4: 19/06-25/06 | total
Materials, incl.delivery, and subcontractors | 29.029 | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 9065.53 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 43.4428 | [9 empty] | 2208.326 | 2208.326 | 2208.326 | 2208.326 | 2208.326 |  | 11041.63 | travel and living costs |  |  | 30/05-04/06 1: 0; 05/06-11/06 2: 0; 12/06-18/06 3: 0; 19/06-25/06 4: 0; 19/06-25/06 5: 0 | 0
Other costs | 27.5283 | [15 empty] | 0 | planned |  |  | 30/05-04/06 1: 3825.82; 05/06-11/06 2: 893.27; 12/06-18/06 3: 2298.72; 19/06-25/06 4: 558.41; 19/06-25/06 5: 5056.63 | 12632.85
[18 empty] | in fact | 12632.85
[18 empty] | Subcontractors budget, EUR | 15307.24
[18 empty] | Payments to subcontractor, EUR | 6677.765
date of report
2023-09-15

## TAL
TAL |  | SC Viru Keskus Viru valjak 406 10111 Tallinn, Intimissimi, 06/05-12/05
Object costs | [7 empty] | KPI
|  | 2023-05-01 |  |  |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 16500 |  |  |  | 16500 |  | Time shedule, weeks | 09/05-15/05 | 16/05-22/05 | 23/05-29/05 | 30/05-05/06 | 06/06-12/06 | 13/06-21/06 | total | planned | 100% | Time shedule, weeks | 09/05-15/05 | 16/05-22/05 | 23/05-29/05 | 30/05-05/06 | 06/06-12/06 | 13/06-21/06 | [5 empty] | total
Objekta tiešie izdevumi | Direct costs | 10810.341 |  | 0 |  | 10810.341 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 100% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 1155.83 | 2775.83 |  | 0 | 1155.83 | 2775.83 |  | 20% | 40% | 60% | 80% | 100% |  | 100% | hours per m2 |  |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0
materiālu piegādes izdevumi | delivery |  |  |  |  | 0 |  |  | 20% | 40% | 60% | 80% | 100% |  | 100% | planned | 0 |  | 1: 191.5 | 191.5
apakšuzņēmēji | subcontractors | 1620 |  |  |  | 1620 | [7 empty] | 0% | 0% | in fact | 2.9462
darba algas | salaries | 3216.655 | 6258.501 |  | 0 | 3216.655 | 6258.501
DD VSAOI | tax for salaries | 758.8089 |  | 0 |  | 758.8089 | [9 empty] | Contract amount EUR | 16500
uzkrājums atvaļinājumam | vacation allowance | 318.0371 |  | 0 |  | 318.0371 | [9 empty] | Additional works, EUR
administratīvie izdevumi 7% | administrative costs 7% | 1155 |  | 0 |  | 1155
komandējuma dienas naudas | travel allowance | 810 |  |  |  | 810 | [9 empty] | square m2 | 65
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 1347.42 | 1776.01 |  | 0 | 1347.42 | 1776.01 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 253.24 |  |  |  | 253.24 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 175.35 |  |  |  | 175.35 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 5689.659 | 34.48% | 0 | #DIV/0! | 5689.659 | 34.48%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 09/05-15/05 | 16/05-22/05 | 23/05-29/05 | 30/05-05/06 | 06/06-12/06 | 13/06-21/06 | total | planned |  | Time shedule, weeks | 1: 09/05-15/05; 2: 16/05-22/05; 3: 23/05-29/05; 4: 30/05-05/06; 5: 06/06-12/06; 6: 13/06-21/06 | total
Materials, incl.delivery, and subcontractors | 25.6775 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 1155.83 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 57.8937 | [7 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | travel and living costs
Other costs | 16.4288 | [13 empty] | 0 | planned | 0 |  | 1: 1347.42 | 1347.42
[16 empty] | in fact | 1347.42
Subcontractors budget, EUR
[16 empty] | Payments to subcontractor, EUR | 1620
date of report
2023-06-05

## MAL
MAL | Calzedonia / Intimissimi SC Emporia, Hyllie Boulevard 19, 215 32 Malmö, Sweden 17/04/2023-09/05/2023
Object costs | [7 empty] | KPI
|  | Aprīlis |  | Maijs |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 40197.325 | 216.5 | 40197.325 |  | 75865.89 |  | Time shedule, weeks | 17/04-23/04 | 24/04-30/04 | 01/05-07/05 | 08/05-09/05 |  |  | total | planned | 100% | Time shedule, weeks | 17/04-23/04 | 24/04-30/04 | 01/05-07/05 | 08/05-14/05 | 15/05-21/05 | [6 empty] | total
Objekta tiešie izdevumi | Direct costs | 27147.6396 |  | 19855.0866 |  | 47002.7263 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 106.3% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 6484.19 | 6954.19 | 3945.78 | 4525.78 | 10429.97 | 11479.97 |  | 25% | 50% | 75% | 100% |  |  | 100% | hours per m2 |  |  | 1: 225.205; 2: 225.205; 3: 225.205; 4: 225.205 | 900.82
materiālu piegādes izdevumi | delivery | 470 |  | 580 |  | 1050 | [8 empty] | 100% | planned | 4.7753 |  | 1: 216.5; 2: 334.5; 3: 277.5; 4: 109.5 | 938
apakšuzņēmēji | subcontractors |  |  |  |  | 0 | [5 empty] | 6.348% |  |  | 6.348% | in fact | 4.9724
darba algas | salaries | 6254.6314 | 14832.3196 | 4401.219 | 11388.4366 | 10655.8504 | 26220.7563
DD VSAOI | tax for salaries | 1475.4675 |  | 1038.2476 |  | 2513.7151 | [9 empty] | Contract amount EUR | 71337.13
uzkrājums atvaļinājumam | vacation allowance | 618.4079 |  | 435.1573 |  | 1053.5652 | [9 empty] | Additional works, EUR | 4528.76
administratīvie izdevumi 7% | administrative costs 7% | 2813.8128 |  | 2813.8128 |  | 5627.6255
komandējuma dienas naudas | travel allowance | 3670 |  | 2700 |  | 6370 | [9 empty] | square m2 | 188.64
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 3373.28 | 5361.13 | 972.1 | 3940.87 | 4345.38 | 9302 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1590.53 |  | 2574.51 |  | 4165.04 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 397.32 |  | 394.26 |  | 791.58 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 13049.6854 | 32.46% | 20342.2384 | 50.61% | 28863.1637 | 38.04%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 17/04-23/04 | 24/04-30/04 | 01/05-07/05 | 08/05-09/05 |  |  | total | planned | 8527 | Time shedule, weeks | 1: 17/04-23/04; 2: 24/04-30/04; 3: 01/05-07/05; 4: 08/05-09/05; 5: 15/05-21/05 | total
Materials, incl.delivery, and subcontractors | 24.4241 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 10429.97 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 55.7856 | [7 empty] | 2131.75 | 2131.75 | 2131.75 | 2131.75 |  |  | 8527 | travel and living costs |  |  | 1: 2750; 2: 2750; 3: 2750; 4: 2750 | 11000
Other costs | 19.7903 | [13 empty] | 0 | planned | 11000 |  | 1: 4785.74; 2: 139.42; 4: 2280.65 | 7205.81
[16 empty] | in fact | 7205.81
Subcontractors budget, EUR
[16 empty] | Payments to subcontractor, EUR | 0
date of report
2023-06-05
|  | SEK | EUR | 30% SEK | 30%EUR | 60% SEK | 60% EUR |  | 10% SEK | 10% EUR
| Calzedonia | 345000 | 30459.54 | 103500 | 9137.86 | 207000 | 18275.73 |  | 34500 | 3045.95 | 345000 | 30459.54
| Intimissimi | 463000 | 40877.59 | 138900 | 12263.28 | 277800 | 24526.55 |  | 46300 | 4087.76 | 463000 | 40877.59
|  | 808000 | 71337.13 | 242400 | 21401.14 | 484800 | 42802.28 | 0 | 80800 | 7133.71 | 808000 | 71337.13
| Invoices according agreement | Calzedonia | Intimissimi | invoice amount total EUR | payment received
| 2023 1/MAL | 9137.86 | 12263.28 | 21401.14 | 26/04/2023
| 2023 2/MAL | 18275.73 | 24526.55 | 42802.28 | 30/05/2023
| 2023 3/MAL | 3045.95 | 4087.76 | 7133.71 | 13/06/2023
| Total | 30459.54 | 40877.59 | 71337.13
| Additonally works | Calzedonia | Intimissimi | invoice amount total EUR
| 2023 4/MAL | 3100 | 1428.76 | 4528.76 | 2023-02-06
| agreement amount | advance received, invoice Nr. 2023 1/MAL | 2023 2/MAL | 2023 3/MAL | invoice 2023 3/MAL to pay
Calzedonia | 30459.54 | 9137.86 | 18275.73 | 12183.81 | 3045.95
Intimissimi | 40877.59 | 12263.28 | 24526.55 | 16351.04 | 4087.76
| 71337.13 | 21401.14 | 42802.28 | 28534.85 | 7133.71

## BER
BER | Willy-Brandt-Platz 2, 12529 Schönefeld, Germany, 29/05/2023-16/06/2023
Object costs | [7 empty] | KPI
|  | Maijs 23 |  | Jūnijs 23 |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 29004.4767 | 412.5 | 58008.9533 |  | 87013.43 | 412.5 | Time shedule, weeks |  |  | 25/04-01/05 | 02/05-08/05 |  |  | total | planned | 100% | Time shedule, weeks | 29/05-04/06 | 05/06-11/06 | 12/06-16/06 | [8 empty] | total
Objekta tiešie izdevumi | Direct costs | 14153.4483 |  | 31416.3787 |  | 45569.827 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 115.4% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 4969.66 | 6604.6 | 1482.11 | 17168.43 | 6451.77 | 23773.03 |  | 100% | [5 empty] | 100% | hours |  |  | 29/05-04/06 1: 159.3333; 05/06-11/06 2: 159.3333; 12/06-16/06 3: 159.3333 | 478
materiālu piegādes izdevumi | delivery | 929.94 |  | 1350 |  | 2279.94 |  |  | 100% | [5 empty] | 100% | planned | 478 |  | 29/05-04/06 1: 145.5; 05/06-11/06 2: 155; 12/06-16/06 3: 112 | 412.5
apakšuzņēmēji | subcontractors | 705 |  | 14336.32 |  | 15041.32 | [8 empty] | 15.42% | in fact | 412.5
darba algas | salaries | 1051.865 | 3784.3133 | 3187.19 | 11014.7987 | 4239.055 | 14799.112
DD VSAOI | tax for salaries | 248.135 |  | 751.8581 |  | 999.9931 | [9 empty] | Contract amount EUR | 75388.43
uzkrājums atvaļinājumam | vacation allowance | 104 |  | 315.1238 |  | 419.1238 | [9 empty] | Additional works, EUR | 11625
administratīvie izdevumi 7% | administrative costs 7% | 2030.3134 |  | 4060.6267 |  | 6090.9401
komandējuma dienas naudas | travel allowance | 350 |  | 2700 |  | 3050 | [9 empty] | square m2 | 80.54
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2261.68 | 3764.535 |  | 3233.15 | 2261.68 | 6997.685 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1018.285 |  | 305.98 |  | 1324.265 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 484.57 |  | 2927.17 |  | 3411.74 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 14851.0284 | 51.2% | 26592.5746 | 45.84% | 41443.603 | 47.63%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 29/05-04/06 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 0 |  | 25/04-01/05 | 02/05-08/05 |  |  | total | planned | 10832.59 | Time shedule, weeks | 29/05-04/06 1: 29/05-04/06; 05/06-11/06 2: 05/06-11/06; 12/06-16/06 3: 12/06-16/06 | total
Materials, incl.delivery, and subcontractors | 52.1684 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 8731.71 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 32.4757 | [13 empty] | 10832.59 | travel and living costs |  |  | 29/05-04/06 1: 933.3333; 05/06-11/06 2: 933.3333; 12/06-16/06 3: 933.3333 | 2800
Other costs | 15.356 | [13 empty] | 0 | planned | 2800 |  | 29/05-04/06 1: 3256.795; 05/06-11/06 2: 305.98 | 3562.775
[16 empty] | in fact | 3562.775
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2023-07-07

## OFF
OFF | Calzedonia and Intimissimi Offenburg, Hauptstrasse 80, Germany, 01/03/2023- 06/04/2023 (20/05/2023!)
Object costs | [11 empty] | KPI
|  | Marts |  | Aprīlis |  | Maijs |  | Jūnijs |  | Total |  | Object address | execution of contract | [5 empty] | execution of the contract | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 79000 |  | 79000 |  | 24166.3 |  | 0 |  | 182166.3 |  | Time shedule, weeks | 01/03-05/03 | 06/03-12/03 | 13/03-19/03 | 20/03-26/03 | 27/03-02/04 |  | total | planned | 100% | Time shedule, weeks | 01/03-05/03 | 06/03-12/03 | 13/03-19/03 | 20/03-26/03 | 27/03-02/04 | 03/04-09/04 | 10/04-12/04 | 23/04-30/04 | 01/05-04/05 | 15/05-20/05 | jūnijs | total
Objekta tiešie izdevumi | Direct costs | 70826.6172 |  | 49110.3128 |  | 12161.9145 |  | 1647.9392 |  | 133746.7837 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 115.3% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
mtr. un aprīkojuma iegāde | materials and equipment | 18095.04 | 27366.04 | 1826.68 | 30886.62 | 921.19 | 5092.78 | 67.18 | 67.18 | 20910.09 | 63412.62 |  | 20% | 40% | 60% | 80% | 100% |  | 20% | hours per m2 |  |  | 1: 336; 2: 336; 3: 336; 4: 336; 5: 336 | 1681
mtr. piegādes izdevumi | delivery | 1770 |  | 98.9 | [5 empty] | 1868.9 | [8 empty] | 0% | planned | 10.8929 |  | 176 | 67 | 345 | 333 | 356 | 228 | 33 | 73.5 | 50.5 | 73 |  | 1735
apakšuzņēmēji | subcontractors | 7501 |  | 28961.04 |  | 4171.59 |  |  |  | 40633.63 | [8 empty] | 15.3% | in fact | 11.2429
darba algas | salaries | 10591.8368 | 31367.6872 | 4526.2358 | 15271.4928 | 1373.9302 | 4825.5245 | 665.3714 | 1188.1192 | 17157.3742 | 52652.8237
DD VSAOI | tax for salaries | 2498.6143 |  | 1067.739 |  | 324.1101 |  | 156.9611 |  | 4047.4246 | [9 empty] | Contract amount EUR | 158000
uzkrājums atvaļinājumam | vacation allowance | 1047.2361 |  | 447.518 |  | 135.8432 |  | 65.7866 |  | 1696.3839 | [9 empty] | Additional works, EUR | 24166.3
administratīvie izdevumi 7% | administrative costs 7% | 5530 |  | 5530 |  | 1691.641 |  | 0 |  | 12751.641
kom. dienas naudas | travel allowance | 11700 |  | 3700 |  | 1300 |  | 300 |  | 17000 | [9 empty] | square m2 | 154.32
kom. izdevumi- naktsmītne | travel expenses (hotels) | 9128.05 | 12092.89 | 455.44 | 2952.2 | 1239 | 2243.61 | 289 | 392.64 | 11111.49 | 17681.34 | [8 empty] | object square | hours optimal/ m2
kom. izdevumi- ceļš | travel expenses ( tickets, road costs) | 2317.86 |  | 1654.92 |  | 503.95 |  | 103.64 |  | 4580.37 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 646.98 |  | 841.84 |  | 500.66 |  |  |  | 1989.48 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 8173.3828 | 10.35% | 29889.6872 | 37.84% | 12004.3855 | 49.67% | -1647.9392 | #DIV/0! | 48419.5163 | 26.58%
[12 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [10 empty] | Time shedule, weeks | 01/03-05/03 | 06/03-12/03 | 13/03-19/03 | 20/03-26/03 | 27/03-02/04 |  | total | planned | 23107.85 | Time shedule, weeks | 01/03-05/03 | 06/03-12/03 | 13/03-19/03 | 20/03-26/03 | 27/03-02/04 | 03/04-09/04 | 10/04-12/04 | 23/04-30/04 | 01/05-04/05 | 15/05-20/05 | jūnijs | total
Materials, incl.delivery, and subcontractors | 47.4124 | [11 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 22778.99 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 39.3675 | [11 empty] | 4621.57 | 4621.57 | 4621.57 | 4621.57 | 4621.57 |  | 23107.85 | travel and living costs |  |  | 1: 2780; 2: 2780; 3: 2780; 4: 2780; 5: 2780 | 13900
Other costs | 13.22 | [11 empty] | 8277.64 | [5 empty] | 8277.64 | planned | 13900 |  | 9984.66 | 125 |  | 85 | 1251.25 | 535.17 | 1218.41 | 1337.78 |  | 761.95 | 289 | 15588.22
[20 empty] | in fact | 15588.22
[20 empty] | Subcontractors budget, EUR | 42998.72
[20 empty] | Payments to subcontractor, EUR | 21273.59
date of report
2023-07-07
ELEKTRIĶU IZMAKSAS | 21273.59 | 30894.4
CEĻŠ+DZĪVOŠANA
ALGA+TAX
KOMANDĒJUMA DIENAS NAUDAS
MATERIĀLI | 3627.69
APAKŠUZŅĒMĒJI- EI Support | 13883.48
APAKŠUZŅĒMĒJI- PETER SEYRING | 3762.42

## ANT
ANT | Intimissimi Antverpen Korte Gasthuisstraat, Belgium, 20/02/2023-08/03/2023
Object costs | [9 empty] | KPI
|  | Februāris |  | Marts |  |  |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 37259.9733 |  | 18629.9867 |  |  |  | 55889.96 |  | Time shedule, weeks | 20/02-26/02 | 27/02-05/03 | 06/03-08/23 | 11/04/-17/04 | 18/04-21/04 | maijs | total | planned | 100% | Time shedule, weeks | 20/02-26/02 | 27/02-05/03 | 06/03-08/23 | 11/04/-15/04 | 18/04-21/04 | maijs | [5 empty] | total
Objekta tiešie izdevumi | Direct costs | 20611.5007 |  | 11696.2629 |  | 0 |  | 32307.7636 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 100% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 2973.91 | 4073.18 | 945.96 | 1938.13 |  | 0 | 3919.87 | 6011.31 |  | 30% | 60% | 100% | 100% |  |  | 100% | hours per m2 |  |  | 1: 237.2833; 2: 237.2833; 3: 237.2833; 4: 177.9625 | 711.85
materiālu piegādes izdevumi | delivery |  |  | 539 |  |  |  | 539 | [8 empty] | 0% | planned | 8.559 |  | 1: 405; 2: 428.5; 3: 69 | 902.5
apakšuzņēmēji | subcontractors | 1099.27 |  | 453.17 |  |  |  | 1552.44 | [8 empty] | 0% | in fact | 10.8513
darba algas | salaries | 4260.355 | 12074.8007 | 2090.24 | 7394.0929 |  | 0 | 6350.595 | 19468.8936
DD VSAOI | tax for salaries | 1005.0177 |  | 493.0876 |  | 0 |  | 1498.1054 | [9 empty] | Contract amount EUR | 55889.96
uzkrājums atvaļinājumam | vacation allowance | 421.2298 |  | 206.6662 |  | 0 |  | 627.896 | [9 empty] | Additional works, EUR
administratīvie izdevumi 7% | administrative costs 7% | 2608.1981 |  | 1304.0991 |  | 0 |  | 3912.2972
komandējuma dienas naudas | travel allowance | 3780 |  | 3300 |  |  |  | 7080 | [9 empty] | square m2 | 83.17
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 3160.65 | 4463.52 | 714.77 | 2364.04 |  | 0 | 3875.42 | 6827.56 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 860.23 |  | 940.86 |  |  |  | 1801.09 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 442.64 |  | 708.41 |  |  |  | 1151.05 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 16648.4726 | 44.68% | 6933.7238 | 37.22% | 0 | #DIV/0! | 23582.1964 | 42.19%
[10 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [8 empty] | Time shedule, weeks | 20/02-26/02 | 27/02-05/03 | 06/03-08/23 | 11/04/-17/04 | 18/04-21/04 | maijs | total | planned | 6517.26 | Time shedule, weeks | 1: 20/02-26/02; 2: 27/02-05/03; 3: 06/03-08/23; 4: 11/04/-15/04; 5: 18/04-21/04 | total
Materials, incl.delivery, and subcontractors | 18.6064 | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 4458.87 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 60.2607 | [9 empty] | 2172.42 | 2172.42 | 2172.42 | 1629.315 |  |  | 6517.26 | travel and living costs |  |  | 1: 2533.3333; 2: 2533.3333; 3: 2533.3333; 4: 1900 | 7600
Other costs | 21.1329 | [15 empty] | 0 | planned | 7600 |  | 1: 3746.63; 2: 787.08; 3: 1142.47 | 5676.18
[18 empty] | in fact | 5676.18
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
27/04/2023
ELEKTRIĶU IZMAKSAS | 2493.761
CEĻŠ+DZĪVOŠANA | 1099.15
ALGA+TAX | 716.031
KOMANDĒJUMA DIENAS NAUDAS | 600
MATERIĀLI | 78.58
APAKŠUZŅĒMĒJI- ELEKTRO LAT
APAKŠUZŅĒMĒJI- PETER SEYRING

## SW
SW | Zviedrija, 06/02/2023-09/02/2023
Object costs | [7 empty] | KPI
|  |  |  | Marts 22 |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 5650 |  |  |  | 5650 | 0 | Time shedule, weeks | 06/02-09/02 | [5 empty] | total | planned | 100% | Time shedule, weeks | 06/02-09/02 | [10 empty] | total
Objekta tiešie izdevumi | Direct costs | 5819.744 |  | 0 |  | 5819.744 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 100% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 610.92 | 610.92 |  | 0 | 610.92 | 610.92 |  | 100% | [5 empty] | 100% | hours per m2 |  |  | 06/02-09/02 1: 0; 06/02-09/02 2: 0; 06/02-09/02 3: 0; 06/02-09/02 4: 0
materiālu piegādes izdevumi | delivery |  |  |  |  | 0 |  |  | 100% | [5 empty] | 100% | planned | #DIV/0! | [12 empty] | 0
apakšuzņēmēji | subcontractors |  |  |  |  | 0 |  |  | 0% | [5 empty] | 0% | in fact | #DIV/0!
darba algas | salaries | 1548.17 | 3461.954 |  | 0 | 1548.17 | 3461.954
DD VSAOI | tax for salaries | 365.2133 |  | 0 |  | 365.2133 | [9 empty] | Contract amount EUR | 5650
uzkrājums atvaļinājumam | vacation allowance | 153.0707 |  | 0 |  | 153.0707 | [9 empty] | Additional works, EUR
administratīvie izdevumi 7% | administrative costs 7% | 395.5 |  | 0 |  | 395.5
komandējuma dienas naudas | travel allowance | 1000 |  |  |  | 1000 | [9 empty] | square m2
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 646.13 | 1746.87 |  | 0 | 646.13 | 1746.87 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1100.74 |  |  |  | 1100.74 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses |  |  |  |  | 0 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | -169.744 | -3.004% | 0 | #DIV/0! | -169.744 | -3.004%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 06/02-09/02 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 06/02-09/02 | [5 empty] | total | planned | 0 | Time shedule, weeks | 06/02-09/02 1: 06/02-09/02 | total
Materials, incl.delivery, and subcontractors | 10.4974 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 610.92 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 59.4864 | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | travel and living costs | [13 empty] | 0
Other costs | 30.0163 | [7 empty] | 610.92 | [5 empty] | 610.92 | planned |  |  | 06/02-09/02 1: 1742.5 | 1742.5
[16 empty] | in fact | 1742.5
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2023-03-03

## SAR2
SAR2 | SAARBRUESKEN, Bahnhofstrasse 1 , Germany, 11/02/2023-20/02/2023
Object costs | [7 empty] | KPI
|  | 2022-02-22 |  |  |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 30549.81 | 377.5 |  |  | 30549.81 | 377.5 | Time shedule, weeks | 10/02-20/02 | [5 empty] | total | planned | 100% | Time shedule, weeks | 10/02-20/02 | [10 empty] | total | 112171.55
Objekta tiešie izdevumi | Direct costs | 14628.4014 |  | 0 |  | 14628.4014 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 138% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 225.09 | 1964.66 |  | 0 | 225.09 | 1964.66 |  | 100% | [5 empty] | 100% | hours per m2 |  |  | 10/02-20/02 1: 313 | 313
materiālu piegādes izdevumi | delivery | 487.5 |  |  |  | 487.5 |  |  | 100% | [5 empty] | 100% | planned | 2.2005 |  | 10/02-20/02 1: 377.5 | 377.5
apakšuzņēmēji | subcontractors | 1252.07 |  |  |  | 1252.07 |  |  | 38% | [5 empty] | 38% | in fact | 2.654
darba algas | salaries | 4191.13 | 9982.6897 |  | 0 | 4191.13 | 9982.6897
DD VSAOI | tax for salaries | 988.6876 |  | 0 |  | 988.6876 | [9 empty] | Contract amount EUR | 22136.76
uzkrājums atvaļinājumam | vacation allowance | 414.3854 |  | 0 |  | 414.3854 | [9 empty] | Additional works, EUR | 8413.05
administratīvie izdevumi 7% | administrative costs 7% | 2138.4867 |  | 0 |  | 2138.4867
komandējuma dienas naudas | travel allowance | 2250 |  |  |  | 2250 | [9 empty] | square m2 | 142.24
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2042.93 | 2681.0517 |  | 0 | 2042.93 | 2681.0517 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 151.3917 |  |  |  | 151.3917 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 486.73 |  |  |  | 486.73 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 15921.4086 | 52.12% | 0 | #DIV/0! | 15921.4086 | 52.12% | [23 empty] | 26955.4924 | 24.03%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 10/02-20/02 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | 10/02-20/02 | [5 empty] | total | planned | 255.25 | Time shedule, weeks | 10/02-20/02 1: 10/02-20/02 | total
Materials, incl.delivery, and subcontractors | 13.4304 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 712.59 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 68.2418 | [7 empty] | 255.25 | 255.25 | 255.25 | 0 |  |  |  | travel and living costs |  |  | 10/02-20/02 1: 2750 | 2750
Other costs | 18.3277 | [13 empty] | 0 | planned | 2750 |  | 10/02-20/02 1: 2194.3217 | 2194.3217
[16 empty] | in fact | 2194.3217
[16 empty] | Subcontractors budget, EUR | 1500
[16 empty] | Payments to subcontractor, EUR | 1252.07
date of report
2023-03-03

## SAR
SAR | SAARBRUESKEN, Bahnhofstrasse 51, Germany, 11/01/2023-14/02/2023
Object costs | [7 empty] | KPI
|  | Janvāris |  | Februāris |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 40810.87 | 596 | 40810.87 |  | 81621.74 | 596 | Time shedule, weeks |  |  |  |  | 14/03-17/03 |  | total | planned | 100% | Time shedule, weeks | 11/01-15/01 | 16/01-22/01 | 23/01-29/01 | 30/01-05/02 | 06/02-12/02 | [6 empty] | total
Objekta tiešie izdevumi | Direct costs | 38097.0233 |  | 32490.6329 |  | 70587.6562 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 127.5% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 14718.2333 | 15008.6533 | 10533.36 | 15879.83 | 25251.5933 | 30888.4833 |  | 25% | 50% | 75% | 100% |  |  | 100% | hours per m2 |  |  | 1: 141.6; 2: 141.6; 3: 141.6; 4: 141.6; 5: 141.6 | 708
materiālu piegādes izdevumi | delivery |  |  | 676.47 |  | 676.47 |  |  | 25% | 50% | 75% | 100% |  |  | 100% | planned | 9.112 |  | 1: 92; 2: 225; 3: 279; 4: 120; 5: 401 | 1117 | 38156.2328
apakšuzņēmēji | subcontractors | 290.42 |  | 4670 |  | 4960.42 | [6 empty] | 27.53% |  | 27.53% | in fact | 14.3758 | [13 empty] | 34.1596
darba algas | salaries | 5444.9255 | 17374.4949 | 4291.24 | 12934.5879 | 9736.1655 | 30309.0828
DD VSAOI | tax for salaries | 1284.4579 |  | 1012.3035 |  | 2296.7614 | [9 empty] | Contract amount EUR | 64000
uzkrājums atvaļinājumam | vacation allowance | 538.3507 |  | 424.2835 |  | 962.6342 | [9 empty] | Additional works, EUR | 17621.74
administratīvie izdevumi 7% | administrative costs 7% | 2856.7609 |  | 2856.7609 |  | 5713.5218
komandējuma dienas naudas | travel allowance | 7250 |  | 4350 |  | 11600 | [9 empty] | square m2 | 77.7
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 3847.52 | 5713.875 | 1514.925 | 3676.215 | 5362.445 | 9390.09 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 738.605 |  | 1246.1 |  | 1984.705 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 1127.75 |  | 915.19 |  | 2042.94 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 2713.8467 | 6.65% | 8320.2371 | 20.39% | 11034.0838 | 13.52%
[8 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [6 empty] | Time shedule, weeks | [6 empty] | total | planned | 7562.42 | Time shedule, weeks | 1: 11/01-15/01; 2: 16/01-22/01; 3: 23/01-29/01; 4: 30/01-05/02; 5: 06/02-12/02 | total
Materials, incl.delivery, and subcontractors | 43.759 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 25928.0633 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 42.9382 | [7 empty] | 1890.605 | 1890.605 | 1890.605 | 1890.605 |  |  | 7562.42 | travel and living costs |  |  | 1: 1110; 2: 1110; 3: 1110; 4: 1110; 5: 1110 | 5550
Other costs | 13.3027 | [13 empty] | 0 | planned | 5550 |  | 1: 3590.34; 2: 476.395; 4: 579.39; 5: 2700.925 | 7347.05
[16 empty] | in fact | 7347.05
[16 empty] | Subcontractors budget, EUR | 17743
| administrative costs 7% | [14 empty] | Payments to subcontractor, EUR | 14198
date of report
23/03/2023
ELEKTRIĶU IZMAKSAS | 14198.767 | 13133.4
CEĻŠ+DZĪVOŠANA | 1583.525
ALGA+TAX | 2630.712
KOMANDĒJUMA DIENAS NAUDAS | 2450
MATERIĀLI | 2706.36
APAKŠUZŅĒMĒJI- ELEKTRO LAT
APAKŠUZŅĒMĒJI- PETER SEYRING | 4828.17

## MUN2
MUN2 | Flughafen München Terminalstr. West 85356 München-Flughafen Zentralgebäude, Ebene 03 Raum 330RG
Object costs | [9 empty] | KPI
|  | 2023-01-01 |  | 2023-02-01 |  | Marts 23 |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 62987.8533 | 727 | 62987.8533 |  | 62987.8533 |  | 188963.56 | 727 | Time shedule, weeks | [6 empty] | total | planned | 100% | Time shedule, weeks | 11/01-15/01 | 16/01-22/01 | 23/01-29/01 | 30/01-05/02 | 06/02-12/02 | 13/02-19/02 | 20/02-26/02 | 27/02-05/03 | 06/03-09/03 |  |  | total
Objekta tiešie izdevumi | Direct costs | 34488.321 |  | 16458.4969 |  | 51524.6757 |  | 115071.4936 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 107.4% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 13108.97 | 13267.37 | 3956.47 | 5783.97 | 6485.39 | 31948.36 | 23550.83 | 50999.7 | [7 empty] | 100% | hours per m2 |  |  | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 |  |  | 1206
materiālu piegādes izdevumi | delivery | 158.4 |  | 1827.5 |  | 2320 |  | 4305.9 | [8 empty] | 100% | planned | 8.8029 |  | 195 | 317.5 | 214.5 | 88 |  |  | 36 | 136 | 458 |  |  | 1445 | 50501.5636
apakšuzņēmēji | subcontractors |  |  |  |  | 23142.97 |  | 23142.97 | [8 empty] | 7.435% | in fact | 10.5474 | [13 empty] | 34.9492
darba algas | salaries | 5230.25 | 16490.341 | 866.91 | 6266.2769 | 6296.99 | 16814.1957 | 12394.15 | 39570.8136
DD VSAOI | tax for salaries | 1233.816 |  | 204.5041 |  | 1485.4599 |  | 2923.78 | [9 empty] | Contract amount EUR | 175887.1
uzkrājums atvaļinājumam | vacation allowance | 517.1253 |  | 85.7131 |  | 622.596 |  | 1225.4344 | [9 empty] | Additional works, EUR | 13076.46
administratīvie izdevumi 7% | administrative costs 7% | 4409.1497 |  | 4409.1497 |  | 4409.1497 |  | 13227.4492
komandējuma dienas naudas | travel allowance | 5100 |  | 700 |  | 4000 |  | 9800 | [9 empty] | square m2 | 137
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 2346 | 4730.61 | 2484 | 4408.25 | 1745.25 | 2762.12 | 6575.25 | 24500.98 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 1692.52 |  | 1247.05 | 719.85 | 915.93 |  | 3855.5 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 692.09 |  | 677.2 |  | 100.94 |  | 1470.23 | [9 empty] | 50<m2<100 | 12
agent commision | [5 empty] | 12600 |  | 12600
peļņa bruto | profit/ loss | 28499.5323 | 45.25% | 46529.3564 | 73.87% | 11463.1777 | 18.2% | 73892.0664 | 39.1%
[10 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [8 empty] | Time shedule, weeks | [6 empty] | total | planned | 32215 | Time shedule, weeks | 11/01-15/01 | 16/01-22/01 | 23/01-29/01 | 30/01-05/02 | 06/02-12/02 | 13/02-19/02 | 20/02-26/02 | 27/02-05/03 | 06/03-09/03 |  |  | total
Materials, incl.delivery, and subcontractors | 44.32 | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 27856.73 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 34.388 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | travel and living costs |  |  | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 |  |  | 7200
Other costs | 21.292 | [15 empty] | 0 | planned | 7200 |  | 1: 3241.93; 2: 522.09; 3: 274.5; 6: 390.76; 7: 3263.96; 9: 2737.27 | 10430.51
[18 empty] | in fact | 10430.51
Subcontractors budget, EUR
Payments to subcontractor, EUR
date of report
2023-06-04

## FUR
FUR | Rudolf-Breitscheid-Straße 4, 90762 Fürth, Germany
Object costs | [9 empty] | KPI
|  | 2022-12-01 |  | 2023-01-01 |  | 2023-02-23 |  | Total |  | Object address | execution of contract | [6 empty] | execution of the contract |  | Object address | worked hours
Objekta ieņēmumi kopā | Budget total | 81000 |  | 81000 |  | 6555 |  | 168555 |  | Time shedule, weeks | [6 empty] | total | planned | 100% | Time shedule, weeks | 06/12-11/12 | 12/12-18/12 | 19/12-25/12 | 26/12-01/01 | 02/01-08/01 | 09/01-15/01 | 16/01-22/01 | 23/01-29/01 | 30/01-? |  |  | total
Objekta tiešie izdevumi | Direct costs | 54671.3832 |  | 38491.9936 |  | 19317.227 |  | 112480.6038 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 104% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
materiālu un aprīkojuma iegāde | materials and equipment | 11345.19 | 15015.69 | 6489.9867 | 6839.9867 | 938.95 | 10964.17 | 18774.1267 | 32819.8467 | [7 empty] | 100% | hours per m2 |  |  | 242.5714 | 242.5714 | 242.5714 |  | 242.5714 | 242.5714 | 242.5714 | 242.5714 |  |  |  | 1698
materiālu piegādes izdevumi | delivery | 2418.4 | [5 empty] | 2418.4 | [8 empty] | 100% | planned | 10.6994 |  | 388.5 | 394.5 | 73 | 66 | 92.5 | 255.5 | 242 | 296 | 424 |  |  | 2232 | 76882.7872
apakšuzņēmēji | subcontractors | 1252.1 |  | 350 |  | 10025.22 |  | 11627.32 | [8 empty] | 4.046% | in fact | 14.0643 | [13 empty] | 34.4457
darba algas | salaries | 9370.7788 | 25827.8532 | 9839.5995 | 26853.622 | 2847.81 | 6460.027 | 22058.1883 | 59141.5022
DD VSAOI | tax for salaries | 2210.5667 |  | 2321.1615 |  | 671.7984 |  | 5203.5266 | [9 empty] | Contract amount EUR | 162000
uzkrājums atvaļinājumam | vacation allowance | 926.5076 |  | 972.8609 |  | 281.5687 |  | 2180.9372 | [9 empty] | Additional works, EUR | 6555
administratīvie izdevumi 7% | administrative costs 7% | 5670 |  | 5670 |  | 458.85 |  | 11798.85
komandējuma dienas naudas | travel allowance | 7650 |  | 8050 |  | 2200 |  | 17900 | [9 empty] | square m2 | 158.7
komandējuma izdevumi- naktsmītne | travel expenses (hotels) | 6097.21 | 13827.84 | 2446.42 | 4798.385 | 555.7 | 1893.03 | 9099.33 | 20519.255 | [8 empty] | object square | hours optimal/ m2
komandējuma izdevumi- ceļš | travel expenses ( tickets, road costs) | 6322.05 |  | 1562.295 |  | 257.61 |  | 8141.955 | [9 empty] | m2<50 | 13
citi izdevumi | other expenses | 1408.58 |  | 789.67 |  | 1079.72 |  | 3277.97 | [9 empty] | 50<m2<100 | 12
peļņa bruto | profit/ loss | 26328.6168 | 32.5% | 42508.0064 | 52.48% | -12762.227 | -194.7% | 56074.3962 | 33.27%
[10 empty] | Object address | materials and equipments costs | [6 empty] | materials and equipment costs |  | Object address | 1: travel and living costs
Direct costs | % | [8 empty] | Time shedule, weeks | [6 empty] | total | planned | 23559 | Time shedule, weeks | 06/12-11/12 | 12/12-18/12 | 19/12-25/12 | 26/12-01/01 | 02/01-08/01 | 09/01-15/01 | 16/01-22/01 | 23/01-29/01 | 30/01-? |  |  | total
Materials, incl.delivery, and subcontractors | 29.1782 | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | in fact | 21192.5267 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Salaries and taxes | 52.5793 | [16 empty] | travel and living costs |  |  | 2142.8571 | 2142.8571 | 2142.8571 |  | 2142.8571 | 2142.8571 | 2142.8571 | 2142.8571 |  |  |  | 15000
Other costs | 18.2425 | [16 empty] | planned | 15000 |  | 5414.22 | 4943.15 |  | 1810.21 |  | 905.72 | 271.355 | 1119.63 | 2777.3 |  |  | 17241.585
[18 empty] | in fact | 17241.585
[18 empty] | Subcontractors budget, EUR | 28448.8
[18 empty] | Payments to subcontractor, EUR | 21732.0483
date of report
23/03/2023
ELEKTRIĶU IZMAKSAS | 21732.0483 | 28448.8
CEĻŠ+DZĪVOŠANA | 2449.465
ALGA+TAX | 6117.8533
komandējuma dienas naudas | 1800
MATERIĀLI | 2371.31
APAKŠUZŅĒMĒJI- ELEKTRO LAT | 1247.68
APAKŠUZŅĒMĒJI- PETER SEYRING | 7745.74